REGIONAL PROJECT/PROGRAMME PROPOSAL

PART I: PROJECT/PROGRAMME INFORMATION

Title of Project/Programme:	Increasing the resilience of both displaced persons and host communities to climate change-related water challenges in Jordan & Lebanon

Countries: 					Jordan, Lebanon

Thematic Focal Area: 				Transboundary water management and food security

Type of Implementing Entity: 			Multilateral

Implementing Entity: 				United Nations Human Settlements Programme

Executing Entities: 				Lebanon: UNICEF; BWE; LRA; LARI; UN-ESCWA

Jordan: UNICEF; Johud, Badia fund; WAJ; PRI

Amount of Financing Requested: 	USD 13,968,139

Project Background and Context

Introduction to the problems and needs

There is little exploration of how urban systems respond to the impacts of climate change combined with a rapid influx of new and often long-term residents. Considering the scale and nature of impacts of climate change and the Syrian crisis in the Mashreq region, an adequate response approach is needed, including concrete adaptation response measures and planning approaches that work in such context.

The Mashreq region is part of the most water scarce region in the world and both urban and rural areas face water challenges. However, some urban areas, especially in Lebanon and Jordan, experience extreme pressure on water availability, both in quantity and quality, exacerbated by climate change, the unprecedented influx of Displaced Persons (DPs), especially from Syria and groundwater overextraction and pollution challenges.

The overall aim of this project is to better respond to climate change impacts and vulnerabilities in the context of the Syrian crisis in Jordan and Lebanon. This is done by demonstrating what concrete adaptation measures (see comp 3) respond to the needs of both DPs and host communities, and especially women and youth, while avoiding any tension over resources and employment opportunities.

The project will focus on responding to climate change-related water challenges by taking a sustainable water management approach. This means it aims to reduce the demand of unsustainable water sources such as over-extracted (and often polluted) groundwater, while increasing water supply options from non-conventional and more sustainable sources, incl. rainwater harvesting and the reuse of treated waste water (see comp 3).

The project will promote the replication and upscaling of the demonstrated techniques and approaches, also beyond Jordan and Lebanon (see comp 4), and to demonstrate how water can be assessed, planned and managed more efficiently at the municipal level (i.e. establish urban-rural linkages) and sustainably (by mainstreaming climate change and gender in municipal master plans) (see comp 1).

During project preparation, DPs in the target areas have been identified as the most vulnerable group due to their socio-economic situation and their dependence on often water-vulnerable sectors, especially the agriculture sector. However, to avoid supporting possible increased tension between DPs and host communities, the project also targets host community members. Assessment and planning processes under component 1 and capacity building activities under component 2 will target both DP and host community groups to avoid and even reduce any tension over scare resources and job opportunities.

Arab region context

The Arab region is full of potential. Over the past decades, the region has seen significant economic and social progress. However, climate risks threaten to derail these development gains. This could disrupt efforts to build peace, cause a spike in ‘eco-migrants,’ and undermine efforts to end hunger, poverty and inequality by 2030.

The Arab region is home to high levels of conflict and the world’s largest population of refugees and displaced people. Simultaneously, it is now the planet’s most water-scarce and food-import-dependent region, and the only region where malnutrition rates have been rising. The Arab region contains 14 of the world’s 20 most water-stressed countries. In fact, the region’s annual internal water resources amount only 6 percent of its average annual precipitation, against a world average of 38 percent. Overexploitation of natural resources in the region has led to severe ecosystem degradation. Poor land and water management are reducing the potential provision of already limited natural resource services.

Urbanization and population growth are putting severe strains on dwindling natural resources. The population of the Arab countries, estimated at approximately 407 million (2016), with 100 million considered to be in poverty, is expected to reach approximately 635 million by 2050. Middle East North Africa (MENA) is the only region in the world where poverty increased between 2011 and 2016; and poverty is projected to increase further by 2030. With low human development index (HDI) rankings for many Arab countries and rampant poverty, the region is also facing internal conflicts over scarce natural resources such as conflicts between rain-fed farmers and pastoralists.

The impacts of climate change are exacerbating the existing challenges of sustainably managing limited natural resources. Current climate change projections show that by the year 2025, the water supply in the Arab region will be 15 percent of the levels in 1960. By 2030 the predominant effects of climate change will include a decrease in precipitation, a drastic rise in average temperatures and an increase in seawater intrusion into coastal aquifers as sea levels rise and groundwater overexploitation continues. Climate change will also have disproportionate consequences for women, poor and marginalized communities who are especially at risk due to their dependence on natural resources.

Lebanon and Jordan socio-demographic, economic and environmental context

The Syrian crisis

Now in its ninth year, the Syrian crisis has had a profound humanitarian, socio-economic, and political impact on the population in both Syria and its neighbouring countries. In recent years, millions of people have been displaced and migrated from Syria. Lebanon and Jordan are among the top DPs host countries: Lebanon is the seventh largest hosting country in the world (156 refugees per 1,000 inhabitants) and Jordan the tenth (72 refugees per 1,000 inhabitants). This has placed unprecedented strain on the country’s economy, infrastructure, and public services. Although some moved to camps, most (82  percent in Lebanon and 83.5 percent Jordan) settle in cities, often in informal communities. Unfortunately, due to lack of planning and resources to respond to this large influx, many find themselves in communities that lack basic infrastructure and services, of which water challenges are seen as a major problem, often leading to health and livelihood issues (as most DPs work in agriculture and this sector is heavily dependent on water availability) and social unrest. Moreover, the majority of DPs from Syria live under the poverty line and lack legal residency making it difficult for them to secure income.

At the programmatic level, the Regional, Refugee and Resilience Plan (3RP) responds to the Syrian crisis and is conceptualized of two inter-connected components. The refugee component addresses the protection and humanitarian assistance needs of refugees living in camps, in settlements and in local communities in all sectors, as well as the most vulnerable members of impacted communities. The 3RP resilience component addresses the resilience, stabilization and development needs of impacted and vulnerable communities in all sectors, strengthens the capacities of national and sub-national service delivery systems, strengthens the ability of governments to lead the crisis response, and provides the strategic, technical and policy support to advance national responses.

Despite support from the National governments, civil society and the international community, the needs of affected communities are outpacing the resources and capacities of partners, and coping mechanisms of the most vulnerable are being severely tested. As there are limited numbers of Syrian DPs returning, there are worrying signs of heightened tensions and host-community fatigue. In this context, it is essential for the international community to maintain its solidarity and support, especially since there is a lack and decline in funding for support to countries like Jordan and Lebanon that face DPs crisis. The regional approach of this project aligns with the 3RP sector objectives, especially for the WASH sector (see annex 1 for more info).

Lebanon context

Lebanon is located on the eastern basin of the Mediterranean Sea, with a surface area of 10,452 km2, a coastline extending on 225 km and a landscape characterized by mostly mountainous areas. Economic trends in Lebanon remain sluggish, with all segments of the economy struggling and competitiveness being undermined by the loss of major trading routes and regional markets, especially against the most recent political turmoil and demonstrations. Against this background, in 2017, Lebanon began developing its vision for stability and sustainable long-term growth and job creation, which is accompanied by important sectoral and structural reforms as well as a major infrastructure programme, the Capital Investment Plan (CIP).

The CIP calls for over $20 billion in funding for 250 projects scheduled over the next decade, until 2030, focusing on investments in priority sectors, such as water, energy, transportation, and solid waste, among others. However, Lebanon faces important challenges, especially related to water resource management and the Syrian crisis.

Environmental and water challenges: Water resources in Lebanon are under stress. Available water, including from rivers and springs, storage dams and groundwater, exceed projected water demand. In 2010, total water supply reached 1,377 (MCM)/year originating from surface water (46 percent), groundwater (51 percent), and used storage (3 percent). Groundwater is over-extracted (0.7 BCM against total recharge of 0.5 BCM). In 2012, Lebanon was already using two thirds of its available water resources. This rate of water withdrawal is very high compared to global standards (averaging 10-30 percent), and includes a substantial component of resource mining, depleting Lebanon’s water capital. In addition, widespread pollution and substandard water infrastructure are restricting the ability of the government to meet water demands in the future.

Lebanon is also generating ever increasing quantities of domestic and industrial wastewater, all of which requires treatment. The country has invested in wastewater facilities over the last two decades. As a result of this investment, about two-thirds of the population is connected to sewer networks but only 8 percent of wastewater reaches the operational wastewater treatment plants and is treated. A considerable amount of the installed treatment capacity is not being exploited.

The environmental costs of this situation are severe. Most wastewater collected is discharged without treatment, into watercourses and the sea. Where there is no network, cesspits are used with considerable seepage into groundwater. Few industries pre-treat their effluent, so harmful waste is discharged into the sewer system or the environment. While all the water resources are being impacted by bacteriological contamination, in agricultural areas, the runoff and infiltration of fertilizer and pesticide residues is exposing these water resources to further environmental degradation. Furthermore, runoff from urban areas may contain heavy metals and hydrocarbons, which could impact the quality of receiving waters.

The negative environmental impacts of poor wastewater collection and treatment have the knock-on effects of increasing health costs, polluting water resources and soils, and reducing income from amenities and tourism. This situation is the result of years of political instability, poor planning and scattered responsibilities within the sector.

Demographic challenge: With a total population of 6,848,925 million in 2018,￼ Lebanon’s population has almost doubled since 2000. The largest increase took place during the last decade, especially because of the large influx of DPs since the Syrian Crisis started in 2011. This relatively high population growth rate puts pressure on government spending to deliver basic public services, and to stimulate economic development.

Economic and fiscal challenges: Economic growth (at constant factor process) for 2020 is expected to be -0.1 percent and 0.3 at constant market prices. This will be mainly driven by the agriculture and industry sectors. Public finances remain structurally weak and are expected to worsen, and are in urgent need of reforms. Public debt continued to rise (155.6 percent of GDP expected in 2020), due to low growth and a relatively high cost of debt financing. However, these estimates remain uncertain due to the mass protests that swept across Lebanon shortly after the government announced new tax measures on 17 October and which are still ongoing.

DPs crisis: one of the key issues facing Lebanon is the economic and social impact of the Syrian crisis. According to government and independent sources, up to 1.5 million Syrians, about a quarter of the Lebanese population, have taken refuge in Lebanon since the conflict erupted in March 2011. This has strained Lebanon’s public finances, service delivery, and the environment. 76 percent of the Syrian DP households subsisted below the poverty line and more than 50 percent of Syrian households live in extreme poverty. The crisis also worsened poverty incidence among Lebanese citizens as well as widen income inequality. In particular, it is estimated that as a result of the Syrian crisis, some 200,000 additional Lebanese have been pushed into poverty, adding to the erstwhile 1 million poor. An additional 250,000 to 300,000 Lebanese citizens are estimated to have become unemployed, most of them unskilled youth.

The Syrian conflict and the influx of DPs to Lebanon coincided with a period of severe water shortage, further stressing the scarce water resources and the under-developed water and wastewater infrastructure in the country. By the end of 2014, the incremental increase in domestic water demand for refugees was expected to reach 43 to 70 MCM, corresponding to an increase in water demand of 8 to 12 percent at the national level, with the Bekaa having the highest share. As for the wastewater generation rates, DPs contribution was an increase of 34 to 56 MCM by the end of the year 2014, resulting in an increase of 8 to 14 percent in wastewater generation at the national level with the Bekaa having the highest share.

Host community fatigue is became more and more pronounced, and tensions between and within communities have been on the rise. Perceived competition for lower-skilled jobs was identified as a key driver for these tensions. Between 2014 and 2017, the percentage of Lebanese who did not report any inter-community tensions dropped from 40 to 2 per cent. Most DPs (around 85 percent) settle in urban areas. The Bekaa valley, which is relatively close to Syria, hosts most of the Syrian DPs.

Jordan context

Jordan is located about 80 km to the East of the Mediterranean Sea. Located at the heart of the Middle East, Jordan is a middle income county shaped by its Geography, history, Geopolitics and scarcity in natural resources. Over the past ten years, Jordan has had success pursuing structural reforms in education, health and privatization and liberalization. The Government of Jordan has introduced social protection systems and reformed subsidies, creating the conditions for public-private partnerships in infrastructure and making tax reforms. However, the country faces important challenges. Macroeconomic vulnerabilities persist mainly due to its energy import dependency. Regional tensions and their recent extension to Iraq and Syria are weighing down on the Jordanian economy through a widening trade deficit and weaker investor confidence. According to the Department of Statistics unemployment rates reached 19.2 percent in the second quarter of 2019, male unemployment is at 17.1 while female unemployment is at 27.2 percent, youth unemployment (ages15-24) according to ILOSTAT database was estimated at 36.7 percent in 2019. Dependency on remittances from Gulf economies are additional threats to economic stability.

Environmental and water challenge: Issues in Jordan are to some extent similar to those in Lebanon. However, Jordan is even a more water scarce country. In fact, it is the second most water scarce country in the world. Water demand distinctly exceeds supply as the annual water availability per capita has declined significantly, from 3,600 m³ per capita in 1946 to only 145 m³ in 2008. If supply remains constant, per capita domestic consumption is projected to fall to 90m³ per person per year by 2025, putting Jordan in the category of having an absolute water shortage that could constrain economic growth and potentially endanger public health. Jordan requires about 1,400 MCM annually (2014) but has, on average, only 848 MCM of freshwater supply available for various uses. Non-revenue water accounts for approximately 50% of total water consumption. In 2014, 229.3 Million Cubic Meters (MCM) were lost, out of the 428.1 MCM delivered for municipal needs, the MoWI strategy includes the reduction of non-revenue water from 52% to 25% by 2025. The increased demand for water has caused over abstraction of water resources to reach 160 percent in 2014. According to the Ministry of Water, of Jordan’s 12 groundwater basins, 10 are being pumped at a deficit. Overall, groundwater is being extracted at twice the rate that it is replenished. In 2017, 50.3 percent of the Jordanian population had 24 h/week of piped water supply or less and 49.7 percent of Jordanians were listed with higher than 24 hsupply/week. This trend will make some areas unliveable, reduce agriculture lands and put more pressure on already scarce water resources, potentially increasing displacement, the continuous risk of social unrest and conflicts and migration to host settlements already struggling to provide basic services.

Demographic challenge: With a total population of 10,558,717 in 2020, Jordan’s population has grown very rapidly, doubling more than ten times in 55 years. The largest increase took place during the last decade, especially because of the large influx of DPs since the Syrian Crisis started in 2011. This relatively high population growth rate puts pressure on government spending to deliver basic public services, and to stimulate economic development.

Economic and fiscal challenges: The elevated level of debt equivalent to 94.23 percent of Jordan’s GDP in 2018 is of concern. As for the water sector, increased financing needs of the Water Authority of Jordan (WAJ), which is government owned, continues to pressure this debt situation as operation and maintenance cost recovery is not expected until 2021. Economic growth for 2019 is expected to be 2.4 percent.

DPs crisis: Jordan has a long history of accommodating DPs. However, the scale of the current DPs crisis compounds the existing socio-economic and environmental pressures in Jordan. There has been an increased competition for access to public utilities (water and electricity), education, health services, infra, and employment, as well as pressure on the already limited carrying capacity of Jordan’s natural resources. Similar to Lebanon, most DPs (around 83.5 percent) settle in urban areas. The Northern governorates of Irbid, Mafraq and Zarqa saw the largest influx of refugees relative to the total population, leading to increased demand for public services. Each Syrian refugee costs the water sector around 620 US$/year.

Climate change

Lebanon

As mentioned in Lebanon’s Intended Nationally Determined Contributions (INDC): ‘adaptation is a priority for Lebanon. Being a developing country with scarce water resources and high population density, Lebanon is already facing and will continue to face, significant challenges as a result of climate change. The government of Lebanon recognizes that the more sustainable its development path is, the easier it will be to build resilience to climate change impacts.’ Priority sectors are water, forestry & agriculture and biodiversity.

Climate: Lebanon has a Mediterranean-type climate characterized by hot and dry summers and wet and cool winters, with an average annual temperature of 15 ̊C. Lebanon has an arid / semi-arid climate, which makes it poor in water resources availability.

Climate change projections: According to climate models, temperatures are expected to increase with 1.7°C by mid-century and up to 3.2°C by 2100 and a decrease in precipitation of 4 to 11 percent with drier conditions by the end of the century (up to 5.8 mm decrease in average monthly precipitation). Projections also show increasing trends of warming, reaching up to 43 additional days with maximum daily temperature higher than 35°C and an increase in number of consecutive dry days when precipitation is less than 1.0 mm by the end of the century, causing the seasonal prolongation and geographical expansion of drought periods. This combination of significantly less wet and substantially warmer conditions will result in hotter and drier climate.

Climate change impacts (on vulnerable sectors and areas), including the water sector: The projected changes in rainfall will put tremendous pressure on national water security and produce knock-on effects in sectors such as agriculture, where around 70 percent of the available water is being used for irrigation. The decline in precipitation will also negatively affect the recharge of rivers and groundwater. Snow will melt earlier in spring, affecting spring recharging and decreasing water availability for irrigation in summer. Annual drought periods are expected to start 15 days to 1 month earlier and will be 9 days longer by 2040 and 18 days longer by 2090. The already dry regions, such as the Bekaa, Hermel, and the South, will experience the sharpest effects. In Zahle, projections show a 6-15 percent decrease in the annual total rainfall (mm)/number of days by 2098 under the SRES A1B scenario. Anticipated changes in climate would reduce the nation’s exploitable supplies of water by about 8 percent in 2040, and 29 percent in 2080. (This is even aggravated by the fact that water demand in Lebanon increased 28 percent between 2011 - 2017, which is directly linked to the Syrian crisis.Jordan

As mentioned in Jordan’s National Climate Change Policy: ‘Jordan faces potential serious impacts on its natural ecosystems, on its river basins and watersheds, on biodiversity—then cascading to impacts on food productivity, water resources, human health, public infrastructure, and human settlements. Climate change will have serious implications on the country’s efforts to eradicate poverty and realize sustainable development for current and future generations— ultimately making climate change an issue of intergenerational equity. Climate change scenarios indicate that Jordan and the Middle East could suffer from reduced agricultural productivity and water availability among other negative impacts.’

Climate: Jordan is located about 80 km to the East of the Mediterranean Sea with a predominantly Mediterranean climate; hot and dry summers and wet and cool winters. Jordan is divided into three main climatic regions: the Ghor region (lowlands), Highlands, badia and Desert region.

Climate change projections: Climate models show a consistent trend towards a drier climate and annual precipitation tends to decrease significantly with time. The mean and maximum temperatures over the full country of Jordan will be 2-4 degrees higher, precipitation will be 15-20 percent lower and potential evapotranspiration about 150 mm higher by the end of the century. In 2070-2100 the cumulated precipitation could decrease by 15 percent. The decrease would be more marked in the western part of the country. Simultaneously, the mean, maximum and minimum air temperature tends to increase significantly by 0.02, 0.01, and 0.03 °C/year, respectively. On the other hand, the relative humidity tends to increase significantly by an average of 0.08 percent/year. In addition, projection show that heat waves and drought events, dry days will be more frequent.

Climate change impacts (on vulnerable sectors and areas), including the water sector: Previous studies and strategic documents (i.e. Jordan’s SNC (2009) and National Climate Change Policy (2013), Jordan’s TNC (2014)) have identified scarcity of water resources as one of the major barrier facing sustainable development in Jordan; a situation that will be magnified by climate change, leading to more water stress. Due to climate change-induced drought, the average agricultural production declined by 25–50 percent in 1999–2000 and agricultural production entirely failed in many areas of land. Furthermore, wheat production declined by 12–20 percent of the total average, and the productivity of rangelands declined by 50 percent. In that season, agricultural production losses as a result of drought were estimated at around US$57 million. More recently, the latest figures show that rainfall in September 2014 was less than half the average expected. Water-related impacts also include reduced total water availability, less reliable seasonal patterns, increasing intensity of droughts during which reservoirs are not refilled, and reduced groundwater recharge. Flood events will also be more likely, in 2018 flash floods claimed 35 lives and affected 150,000 people.  High rainfall events also increase erosion which causes losses of soil water storage and siltation of reservoirs. Higher temperatures cause higher evaporative demand and hence higher irrigation water demand. Higher temperatures also affect the efficiency of wastewater treatment plants. Jordan has been subjected to additional water stress due to the influx of displaced peoples, especially from Syria. There are indications of pollution of the main aquifer lying beneath the Zaatari camp due to wastewater leakages. Besides that, groundwater, including the Amman-Zarqa aquifer, is being overpumped.

Climate change vulnerabilities assessment and hot-spot mapping approach

Global-, MENA and National climate change models and data have been used to understand climate change trends and projections in Jordan and Lebanon and to justify this project, focused on addressing water-related challenges in the target areas in both countries.

Target areas / municipalities have been selected by identifying which areas experience most pressure on water-related services, exacerbated by climate change impacts and the influx of DPs. Irbid and Mafraq in Jordan are the municipalities that host most DPs after Amman. In Lebanon, the Bekaa area, in which Zahle and the three surrounding target municipalities are located, hosts most DPs. See Annex 1 for more info.

As labelled by the WB, cities under widespread stress from displaced persons – which significantly impacted the overall absorption capacity, including urban systems and services such as water supply (exacerbated by climate change), sanitation, education, and health services, are called ‘type 2’ cities.

Figure 1: Typology of settlements

Figure 2: Climate change vulnerability assessment and hotspot mapping approach (UN-ESCWA approach)

During project preparation, data has been collected required to map climate change vulnerable hotspots (see approach in figure 2 below) and develop response plans (i.e. identify appropriate adaptation measures) to address specific vulnerabilities in these hotspot areas. This has been done through a combination of research and a comprehensive planning and consultation process (see section II.I), including with vulnerable groups.

Project target areas

There is enough evidence that water challenges will likely grow for Irbid, Mafraq and Zahle in the future due to climate change impacts. There is also a clear link between the influx of Syrian DPs and increasing pressure on water resources in these areas. Both challenges are coupled with adaptation challenges in both countries. Common adaptation challenges for the two countries are financial constraints to implement climate action. For example, the financial deficit in the municipality budget for Greater Mafraq has reached 107 percent due to the impact of the influx of Syrian DPs. Also, there is a lack of awareness at the community level, weak coordination between relevant authorities and a need to spend more on research and capacity building to apply low-cost innovative solutions.

Many of the DPs have now been in the host country for five or more years. As most DPs live in cities, solutions focused on their needs and negative climate change impacts must target host cities and towns. The shift from a focus on camps to cities and towns means changing the paradigm for how humanitarian and development agencies work with DPs. Instead of providing stand-alone solutions to DPs in camps or rural areas, the challenge is to establish urban – rural linkages and support host communities to adapt / scale up existing services, shelter and jobs to meet the needs of both the original residents and DPs, considering the impacts of climate change, especially increasing water challenges, on these services.

The Jordan Refugee Response Plan identifies the Northern region as highly vulnerable (including Irbid) while the East (Mafraq) is the second highest region in the percentage of DPs rated highly vulnerable or above. Syrian DPs in Jordan and Lebanon are specifically vulnerable to climate-induced water challenges. The Vulnerability Assessment Framework 2019 shows 11 percent of the Syrian DP population as having high or severe VAF WASH indicator vulnerability, while this indicator might appear very low, sub-indicators reveal much higher levels of vulnerability, namely expenditure on WASH items, 58 percent reported spending more than five per cent of expenditures on water. In Lebanon, 42 percent of households rely on bottled water. In Bekaa, Lebanon—where Zahle is located—the unemployment rate (unemployed over labour force), 61.9 percent, is the highest amongst all Lebanese Governorates and almost double the total unemployment rate nationally (31.3 percent). Moreover, the Bekaa Governorate is the second lowest when measuring the percentage of “households with members working in the past 7 days” with an average of 36.4 percent compared to the lowest 30.1 percent in Baalbek El-Hermel Governorate and as compared to 59.4 percent nationally.  There is also a cultural barrier with Syrian populations used to higher water availability and so higher consumption and so are struggling to cope with much less amounts of water.

In addition, there is a number of specific challenges across the region, including limited job access and livelihoods opportunities, exhaustion of savings, and the adoption of negative coping mechanisms, which further exacerbate the residual protection risks they face. Broader political and social pressures can also affect stability between displaced populations and host communities in both countries. There are over 10,000 Syrian displaced children recorded in the Arab region as either separated, unaccompanied or in institutional care. The loss of social networks further decreases the adaptive capacities and make DPs more vulnerable to climate change.

The 2015 population census estimates the population of Irbid governorate at 1,770,158 (Syrian DPs 134,649), Qasabit Irbid, Bani Obeid and Ramtha targeted area populations are estimated at 739,212 (Syrian DPs 165,843), 204,313 (Syrian DPs 48,574) and 238,502 (Syrian DPs 68,306) respectively. The population of Mafraq governorate was estimated at 549,948 (Syrian DPs 161,977), Qasabit Mafraq,  Al-Ghadeer Al-Abyad and Akaider targeted area populations are estimated at 124,479 (Syrian DPs 39,359), 1,661 (Syrian DPs 166) and 1,649 (Syrian DPs 165) respectively. Disaggregated data and the overview of climate change concerns for each target area are shown in tables 1 and 2.

Figure 3: Target municipalities in Lebanon

Lebanon

Zahle and surrounding area lies in central Bekaa valley and has an annual rainfall of between 200-600 mm. Figure 3 shows the administrative boundaries of Zahle and the surrounding municipalities. The target areas in Zahle have been identified based on high share of vulnerable communities. The total populations and disaggregated data and an overview of climate change issues and adaptation needs for each municipality are shown in table 1.

Figure 4 shows communities in most need of water resources, which have been combined with figure 5, which shows poverty distribution in Zahle area among vulnerable Lebanese communities (living under 4US$ per day, as per the World Bank data, 2011) and location of vulnerable Syrian displaced population living in Informal Tented Settlements (ITSs). The maps also show the land cover with agricultural and built areas, which has been used to identify vulnerable farmers and vulnerable urban populations.

Figure 4: target areas in need of water	                         Figure 5: target area poverty

Focus group consultation and key informant interviews have been held in the target municipalities (see section II.I.) with the purpose to identify specific issues and needs regarding climate change-related water issues and possible concern regarding proposed adaptation actions (see outcomes in table 1). Drought has been identified as the most problematic hazard in the city of Zahle and its surrounding municipalities during the past 10 years. In general, the surrounding municipalities suffer from extreme heat that has been increasing, especially in the years between 2016 and 2018. In 2017 and 2018, flooding has also been a major concern for the target areas. This trend coincides with the predictions of Lebanon’s Third National Communication to the UNFCCC for generally prolonged drought periods all over the country, increase in average temperature and increase in winter flooding by up to 30 percent.

Zahle:

During the past 8 years, the amount of rainfall and upstream melting snow serving the area has noticeably decreased, causing boreholes to dry out in the summer in addition to becoming increasingly contaminated. The agriculture sector is especially vulnerable, not only to climate change-related increased water scarcity, but also groundwater pollution. As most of the Syrian DPs work in this sector, their jobs are dependent on the resilience of the sector and the use of non-conventional clean water resources. For instance, Haouch El Oumara’s targeted community of host Lebanese population in Zahle has identified drought and extreme heat as the main climate change hazards in their area, especially in the years 2017 and 2018. The rainfall season shifted to the end of winter- beginning of spring, with heavy downpours. As a result, water infiltration into the underground water table has reduced and so has lowered the water table. Twenty years ago, the water table in summer was 80 m underground in Zahle and nowadays one has to dig to 150 m to reach the water table. Existing boreholes are drying out in summer and supplying less water in winter. Farmers started digging deeper boreholes to reach the water table. This water scarcity has increased the cost of crop production due to the need to pump water from deeper boreholes. As a result, some farmers have lost their livelihoods as they are failing to compete with cheaper imported products. This has also caused farmers to use the polluted water of Litani River, which in turn increased diseases in the surrounding area. According to the community, Lebanon is the third in the world in the rate of cancer, with the central Bekaa area (around Litani River) having the greatest share of cancer patients (800 cases in Bar Elias alone). These water scarcity issues have been also exacerbated by the increased temperature that increased the water need for plants as well as caused crop damages and spread of new types of insects. Consequently, farmers are using pesticides more often.

Bar Elias, Ablah, Hazerta, El-Marj, Ferzol, Qaa El-Rim, Taanayel, Taalabaya and Terbol:

Similar to Zahle, all areas in the Bekaa region have witnessed various water-related problems. It is said that factories, mainly located in Zahle, and sewage lines in the area have been dumping their waste in the Litani River without prior treatment. This has heightened reported health problems and which include the spread of diseases and elevated cancer rates in the Bekaa. Also, the residents have addressed concerns related to the presence of bad odors in and around the area. Drought and flood incidents have led to crop damage, surface water pollution and decreased water quality and groundwater depletion.

Qab Elias and Saadnayel:

The drinking water being distributed (e.g. by World Vision in Qab Elias is not enough for all the ITSs and at the same time boreholes are drying out in summer due to the increasing drought incidents. Due to the fact that 68 percent of the targeted communities in both municipalities are unemployed, most of the community cannot afford to buy drinking water and so collect water from untested water sources. Since women and children are responsible for domestic work and water supply, they are facing safety issues while walking away from ITS to collect water. Another safety concern—especially for children, elderly and disabled people—is the damage caused by the increased flooding causing loss of shelter. This is in addition to the fires in ITS due to increased heat that melts electrical wires. Skin diseases have also spread among the community due to decline in hygiene caused by water scarcity. While other diseases such as respiratory diseases and fever have increased mainly among children due to increased temperature which also caused an increase in the numbers of insects and rodents. The river stream dries in summer and so is filled with wastewater which has also caused spread in insects and rodents carrying diseases. However, government priorities don’t focus on the ItSs.

For an overview of the main climate change issues and needs in target areas in Lebanon see table 1.

Table 1: overview of main climate change issues and needs in target areas in Lebanon

| Municipality | Population | Main climate change impacts / Hazards (exposure) | Effects on communities and vulnerable groups (sensitivity) | Barriers to adapt (adaptive capacity) | Priority resilience building interventions | Issues and concerns (identified through consultations) and response needs |
| --- | --- | --- | --- | --- | --- | --- |
| Bar Elias | Total population count: 69,124 Women: 35,514 Youth: 3,802 Syrians: 39,124 | - Drought - Flooding - Extreme heat | Drought: - Water Scarcity in urban areas - Add financial burden to families due to lack of adequate drinking water - Agriculture/ crop failure with significant impact on Syrian DPs Extreme heat: - Increase in agricultural water demand - Increase of pests and other insects which damage crops and bring about diseases - Change in agricultural patterns and evident decline in livestock production - Low air quality resulting in heightened level of pollutants Flooding: - Loss of shelter and safety risks for vulnerable groups (mainly displaced persons, women, elderly and children) - Limited mobility - Spread of diseases - Leachate seepage | - Lack of adequate water supply - Lack of funding - Lack of capacity - Lack of awareness about water scarcity and water conservation strategies. - Absence of legislations to cope with climate change - Legal restrictions on supplying piped water to ITS | - Clean water, e.g. through rooftop rainwater harvesting and reuse, and a Constructed Wetland - Awareness on water scarcity and water conservation strategies - Guidelines including Climate Change Adaptation measures, landuse and water scarcity issues | - Harvested water can be polluted (need quality control and awareness) - Harvested and treated stormwater can only be used for domestic reuse and irrigation purposes - Maintenance of rainwater harvesting system (need maintenance plans) Service provision disparities - Service provision disparities - Resistance on the use of harvested/treated water due to lack of awareness - Operation and maintenance (first year guidelines followed thereafter by continued routine guidelines) |
| Hazerta, El Marj, Saadnayel,Taanayel, Taalabaya, Terbol, Ferzol | Total population count: 98,507 Women: 49,301 Youth: 5,454 Syrians: 55,827 | - Drought - Flooding - Extreme heat | Drought: - Water Scarcity in urban areas - Add financial burden to families due to lack of adequate drinking water - Agriculture/ crop failure with significant impact on Syrian DPs Extreme heat: - Increase in agricultural water demand - Increase of pests and other insects which damage crops and bring about diseases - Change in agricultural patterns and evident decline in livestock production - Low air quality resulting in heightened level of pollutants Flooding: - Loss of shelter and safety risks for vulnerable groups (mainly displaced persons, women, elderly and children) - Limited mobility - Spread of diseases - Leachate seepage | - Lack of adequate water supply - Lack of funding - Lack of capacity - Lack of awareness about water scarcity and water conservation strategies. - Absence of legislations to cope with climate change - Legal restrictions on supplying piped water to ITS | - Clean water, e.g. through rooftop rainwater harvesting and reuse - Awareness on water scarcity and water conservation strategies - Guidelines including Climate Change Adaptation measures, landuse and water scarcity issues | - Harvested water can be polluted (need quality control and awareness) - Harvested and treated stormwater can only be used for domestic reuse and irrigation purposes - Maintenance of rainwater harvesting system (need maintenance plans) - Service provision disparities - Resistance on the use of harvested/treated water due to lack of awareness - Lack of commitment and financing to apply adaptive measures to Climate Change |
| Zahle | Total population count: 184,332 Women:94,705 Youth: 10,140 Syrians: 104,332 | - Drought - Flooding - Extreme heat | Drought: - Water Scarcity in urban areas - Add financial burden to families due to lack of adequate drinking water - Agriculture/ crop failure with significant impact on Syrian DPs Extreme heat: - Increase in agricultural water demand - Increase of pests and other insects which damage crops and bring about diseases - Change in agricultural patterns and evident decline in livestock production - Low air quality resulting in heightened level of pollutants Flooding: - Loss of shelter and safety risks for vulnerable groups (mainly displaced persons, women, elderly and children) - Limited mobility - Spread of diseases o Leachate seepage | - Lack of money to buy drinking water - Lack of adequate water supply - Lack of funding - Lack of capacity - Lack of awareness about water scarcity and water conservation strategies. - Absence of legislations to cope with climate change - Legal restrictions on supplying piped water to ITS | - Clean water for agriculture, e.g. through rooftop rainwater harvesting and reuse and through treated water from upgraded WWTP (partial diversion of the treated discharge into an open canal) - Reduced agricultural water losses through water efficient drip irrigation - Awareness on water scarcity and water conservation strategies - Guidelines including Climate Change Adaptation measures, landuse and water scarcity issues | - Treated wastewater will only benefit farmers - Harvested water can be polluted (need quality control and awareness) - Harvested and treated stormwater can only be used for domestic reuse and irrigation purposes - Maintenance of rainwater harvesting system (need maintenance plans) - Service provision disparities - Resistance on the use of harvested/treated water due to lack of awareness - Unwilligness to pay tariffs for wastewater collection and treatment, and for sludge treatment and reuse |

Jordan

Irbid is located in Jordan’s wet region the total annual rainfall in this region varies between 400 and 600 mm while Mafraq on the other hand is located within the Jordan’s  dry region in the east, average rainfall annually varies between 100 and 300 mm (see figure 6). The total populations and disaggregated data and an overview of climate change issues and adaptation needs for each municipality are shown in table 2.

Figure 6: annual average rainfall in target areas

According to focus group consultation and key informant interviews conducted within the target areas in Jordan (see section II.I), the increase in temperature and the decline in rainfall which leads to drought are two of the most hazardous climate change impacts in both Mafraq and Irbid. This confirms the outcomes of Jordan’s Third National Communication to the UNFCCC that predicted a serious decline in precipitation trends and a significant increase in the mean temperature. While in some target areas, flooding has also been pointed out as a major hazard. This is also in line with the predictions of a higher intensity of flooding in Jordan due to climate change.

Figure 7: existing situation / infrastructure and severe water vulnerability in red in Irbid and Mafraq

Figure 8: poverty with Syrian DP percentage in greater Irbid and Mafraq area

Besides natural population growth, the target areas selected suffer from increased water demand mainly due to the influx of Syrian DPs. Syrian DPs live in the same urban areas as Jordanians and so are subject to the same impacts. However, Syrian DPs have higher vulnerability due to the fact that they are likely to have less net income than the average Jordanian family. In agricultural areas, the livelihood of Syrian DPs heavily depends on job opportunities at Jordanian farms and so are affected by any decline or change in agricultural activities.

Figure 7 shows the build-up area in greater Irbid and Mafraq with existing water infrastructure. In red, the area with severe water vulnerability (according to UNICEF) is shown. Figure 8 shows the share of poverty with Syrian DP percentage in greater Irbid and Mafraq. The cities fall in the category 30-40 percent poverty / DPs.

Mafraq Governorate:

Qasabit Al Mafraq (Al Mafraq Main Municipality Area, 2 Focus Groups):

The two most problematic climate change hazards identified throughout the focus group discussions were; flooding and drought. The area has been experiencing an increase in the frequency of flood occurrence and decline in precipitation levels. Which have led to a decline in water table and groundwater level, resulting in water scarcity. Water is being pumped to households once a week and houses with small tanks do not store enough water. Flooding and water scarcity have an adverse effect on residents of the area, floods damage many households causing displacement, forcing absence from workplaces and schools which affects families income. An increase in the number of insects and rodents is prevalent. Water scarcity adds a financial burden to families that resort to purchasing water, especially Syrian families who usually have less net income than Jordanian families. It also causes psychological and physical stress to stay-at-home moms who stay up late at night to make use of the water supplied once a week in laundry, cleaning and other household purposes.  Drought has caused a decline in agricultural and livestock production in the surrounding areas, affecting the livelihoods of Jordanian farmers and Syrian DPs working on farms.

Al Ghadeer Al Abiad:

Farmers identified drought and extreme weather (heat and cold) as the two most significant climate change hazards in the past 10 years. The change in the patterns of rainfall results in deteriorating cultivated crops such as wheat and barley and forcing farmers to shift from rain fed to irrigated agriculture. According to farmers, reclaimed water is becoming more expensive. Extreme weather in summer and winter has damaged crops and caused economic losses to farmers. Farmers can no longer rely on rain fed agriculture to make a living. Due to water scarcity, farmers are becoming more dependent on reclaimed water . Farmers are forced to receive reclaimed water at even at times when irrigation isn’t that high (e.g. during rainy season) reclaimed water cannot be stored for more than a few days as its quality will extremely deteriorate resulting in serious health risks. Livelihoods of Syrian DPs who work on Jordanian = farms are also negatively affected by these impacts. Less farmers are required due to the decline in livestock and agricultural production caused by drought.

Irbid Governorate:

Qasabit Irbid (Greater Irbid Municipality):

Flooding and drought are the two most hazardous climate change impacts affecting the area. Increased frequency of flooding- which occurs mainly in winter- over the past few years. drought caused by decline in rainfall and water scarcity caused a shortage in supplied drinking water. Floods impose safety risks and limits the mobility of residents, specifically; children, disabled and elderly. It may result in displacement among the population living in wadi (valley) areas in addition to damage to houses and infrastructure. Flooding increases the number of insects and rodents which increased diseases among children. Women and children mainly remain at home during flooding. Drought has severely affected households, exacerbated by Syrian DPs influx, water scarcity caused a shortage in supplied drinking water adding a financial burden to families as they need to purchase drinking water from the private market, which is not subsidised. . It also causes psychological and physical stress to stay-at-home moms who stay up late at night to make use of the water supplied once a week in laundry, cleaning and other household purposes. Drought also caused a shrinkage in the agricultural area and changes in the vegetation cover. For example, the supply of olive oil has dramatically decrease and with much higher prices.

Edon Neigbourhood, Liwa: Bani Obead:

Drought, extreme heat and flooding have been identified as the most hazardous climate change impacts in the target area.

Water scarcity caused a shortage in supplied drinking water, drought causes shrinkage in agricultural area and flooding causes safety hazards. Exacerbated by influx of Syrian DPs, water scarcity caused a shortage in supplied drinking water adding a financial burden on families that resort to purchasing  drinking water from the private market which is not subsidised. It has also affected personal hygiene especially among children. Drought also caused a shrinkage in the agricultural area. The agricultural pattern has also changed due to increased temperature with a decline in wheat and clover. Temperature which used to reach 35°C can now reach up to 45°C in summer according to the community members causing spread of mosquitos and emergence of diseases that are new to the area. Floods damage houses and infrastructure hindering mobility.

Ramtha:

Drought  and extreme weather (heat and cold) were identified as the two most significant climate change hazards in the past 10 years by local farmers.

Water shortage at household level, farmers are more dependent on reclaimed water due to water scarcity, however reclaimed water is becoming more expensive. Drought has also caused a decline in food and water available for livestock production. Financial burden on farmers, as reclaimed water is increasing in price. Forced to receive reclaimed water in times that they do not need for irrigation (e.g. during rainy season) and they cannot store it for long as its quality will deteriorate, resulting in serious health risks. Women pointed out that lack of knowledge around permaculture techniques and greywater use in addition to lack of funding to install rainwater harvesting systems. Less farm workers are needed and for less number of days. In addition, extreme weather in summer and winter has damaged crops and caused economic losses to farmers. Livelihoods of Syrian DPs who work in the farm for Jordanians are also negatively affected by these impacts.

Jerash:

Flooding and drought are the two most significant climate change hazards in Jerash. Poor water purification system, results in farmers receiving poor quality water. Reclaimed water that does not meet minimum health and safety standards pollutes the soil and groundwater. Drought and the fall in rainfall as a result of climatechange has an adverse effect on areas, especially areas like Jerash that depend highly on agricultural and livestock production. Farms are in critical conditions, livestock, olive and olive oil production has decreased in Jerash, causing loss of jobs, this results in financial burdens to farmers. The quality of reclaimed water is deteriorating and becoming more expensive, as a result farmers in Jerash suffer from poor water quality and quantity causing a decrease human and land productivity. Moreover, water ponds result in potent smells that may cause disease. Syrian DPs that work on farms are also negatively affected by these impacts.

For an overview of the main climate change issues and needs in target areas in Jordan see table 2.

Table 2: overview of main climate change issues and needs in target areas in Jordan

| Community | Population | Main climate change impacts / Hazards (exposure) | Effects on communities and vulnerable groups (sensitivity) | Barriers to adapt (adaptive capacity) | Priority resilience building interventions | Main issues and concerns (identified through consultations) and response needs (to be aligned with work Amal) |
| --- | --- | --- | --- | --- | --- | --- |
| MUNICIPALITY |  |  |  |  |  |  |
| Qasabit Mafraq (Greater Mafraq Municipality) | Total Number: 124,479 Syrian DPs: 39,359 Female: 59,542 Disabled: NA | Flooding Drought | - Flooding - Safety risk due to flooding especially for women and children - Damage to infrastructure and houses - Households Displacement - Spread of diseases among children and youth - Limit children and parents mobility - Drought - Water Scarcity in urban areas - Add financial burden to families due to lack of adequate drinking water - Agriculture/ crop failure with significant impact on Syrian DPs | - Lack of funding - Lack of capacity - Lack of awareness about water scarcity and water conservation strategies. - Absence of legislations to cope with climate change - Lack of adequate water supply for household purposes | - Greywater reuse system - Rooftop rainwater harvesting system | - How to use apartment blocks for water harvesting (to be identified during full proposal) - Some cultural and religious resistance to greywater reuse (awareness through religious leaders) - Service provision disparities - Potential conflicts over the provided services due to land ownerships - Wastewater polluting the soil. - Having microorganisms in the treated water |
| AL Ghadeer AL Abiad (Mafraq) | Total Number: 1,661 Female: 814 <14: 680 15-24: 338 25-60: 658 >60: 76 Disabled: NA Syrian DPs: 271 | - Drought - Extreme Weather (heat and cold) | - Drought - Less water available for agriculture - Changing crop patterns - Decline in livestock production - Extreme heat and cold - Crop failure | - Lack of funding and high prices of reclaimed water - Lack of capacity to use new agricultural techniques - Absence of legislations to cope with climate change | - Enhance the quality of treated wastewater from Al Mafraq WWTP - Shared water ponds between farmers to store and mix water of different qualities | - Land availability as farmers prefer to use the whole land for cultivation. - Non-equal access to provided service. Water shares are not evenly distributed among farmers (inclusive planning) |
| Irbid (Greater Irbid Municipality and nearby municipalities) | Total Number: 739,212 Jordan Population: 573,369 Syrian DPs: 165,843 Female: 355,898 Disabled: NA | - Flooding - Drought | - Flooding - Safety risks especially for displaced, elderly women and children - Displacement - Damage to infrastructure and houses - Increased diseases - Drought - Urban water scarcity - Add a financial burden on families due to lack of adequate drinking water - Agricultural decline with significant impact on Syrian DPs | - Lack of funding - Lack of awareness - Lack of space in wadis to provide buffer zone in flooding - Absence of legislations to cope with climate change | - Rooftop rainwater harvesting | - Resettlement during construction and after it as many houses are located within the buffer zone of the Wadi (project will ensure no resettlement will take place / resettlement is not needed as intervention is upstream) - How to use apartment blocks for water harvesting (to be identified during full proposal) |
| Neighbourhood: Edon, Liwa: Bani Obead (Irbid) | Total Number: 204,313 Jordan Population: 155,739 Syrian DPs: 48,574 Female: 100,351 Disabled: NA | - Drought - Extreme heat - Flooding | - Drought - Urban water scarcity - Add a financial burden on families due to lack of adequate drinking water - Personal Hygiene among children - Decline in agricultural area - Extreme heat - Increased diseases - Change of agricultural patterns - Flooding - Safety risks among displaced, elderly, women and children - Damage to houses and infrastructure - Affect mobility of women and children | - Lack of funding - Lack of awareness about water scarcity and water conservation strategies. - Outdated water supply networks causing inadequate water supply for household purposes - Absence of legislations to cope with climate change | - Rooftop rainwater harvesting - Greywater reuse in public buildings schools and mosques | - Lack of participation in planning of project/ interventions. - Safety during construction. - Service provision disparities - Potential conflicts over the provided services due to land ownerships. - Untreated groundwater leakage and water salinity. |
| Ramtha (Irbid) | Total Number: 238,502 Jordan Population: 170,196 Syrian DPs: 68,306 Female: 114,571 Disabled: NA | - Drought - Extreme Weather (heat and cold) | - Drought - Less water available for agriculture with significant impact on Syrian DPs - Urban water scarcity - Decline livestock production - Extreme heat and cold - Crop failure | - Lack of funding for farmers to adapt - Lack of financial capacity to invest in permaculture - Lack of capacity to use new agricultural techniques | - Permaculture at JUST - Rainwater harvesting at schools | - Non-equal access to provided service. Water shares are not evenly distributed among farmers (inclusive planning) - Crop failure due to poor water quality (the treated water does not meet the Jordanian standards) - Increased water expenses - Untreated groundwater leakage and water salinity |
| Jerash | Total Number: 207,97 Jordan Population: 197,704 Syrian DPs: 10,293 Female: 99,879 Disabled: NA | - Drought - Flooding | - Drought - Less water available for agriculture - Decline in livestock production | - Lack of funding and high prices of reclaimed water - Lack of capacity to use new agricultural techniques - Absence of legislations to cope with climate change | - Enhance the quality of treated wastewater from Al Maerad WWTP - Introduce modern water conserving irrigation methods to nearby farms (drip irrigation) | - Non-equal access to provided service. Water shares are not evenly distributed among farmers (inclusive planning) - The lack of distribution of water pipes to farmers - Wastewater polluting the soil. - Not cleaning the canals between the station and the flood stream. |

Project Objectives

The overall aim of this project is to better respond to climate change impacts and vulnerabilities in the context of the Syrian crisis in Jordan and Lebanon. This is done by demonstrating what concrete adaptation measures (see comp 3) respond to the needs of both DPs and host communities, and especially women and youth, while avoiding any tension over resources and employment opportunities.

The project will focus on responding to climate change-related water challenges by taking a sustainable water management approach. This means it aims to reduce the demand of unsustainable water sources such as overextracted (and ofthen polluted) groundwater, while increasing water supply options from non-conventional and more sustainable sources, incl. rainwater harvesting and the reuse of treated waste water (see comp 3).

The project will promote the replication and upscaling of the demonstrated techniques and approaches, also beyond Jordan and Lebanon (see comp 4), and to demonstrate how water can be assessed, planned and managed more efficiently at the municipal level (i.e. establish urban-rural linkages) and sustainably (by mainstreaming climate change and gender in municipal master plans) (see comp 1).

During project preparation, DPs in the target areas have been identified as the most vulnerable group due to their socio-economic situation and their dependence on often water-vulnerable sectors, especially the agriculture sector. However, to avoid supporting increased tension between DPs and host communities, the project also targets host community members. Assessment and planning processes under component 1 and capacity building activities under component 2 will target both DP and host community groups to avoid and even reduce any tension.

Table 3: project objectives and sub-objectives

| Objectives | Development approach applicable to climate change and DPs crisis context |
| --- | --- |
| Overall objective: Increasing the resilience of both displaced persons and host communities to climate change-related water challenges in Jordan and Lebanon. |  |
| Sub-objectives: |  |
| - Increasing the resilience of municipal governments: Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from DPs migration | Support addressing regional DPs crisis and climate change challenges at the municipal level: through developing a comprehensive and integrated development response approach (see comp 4) |
|  | Forward-looking / pro-active urban spatial planning and sustainable water management: planning for future urban (population) growth and climate change impacts in an integrated manner (see comp 1) |
| - Increasing the resilience of citizens (DPs and host communities): Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems | Citizen engagement: minimizing risks of social tensions through citizen engagement and enhancing opportunities for social exchange between host-city inhabitants and DPs (especially women and youth) (see comp 1 and 2) |
|  | Awareness, capacity / skill building support: providing support such as skill building and training to build people’s self-reliance, especially regarding water (targeting especially women and youth) (see comp 2) |
| - Increasing the adaptive capacity of the water sector: Expand unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context | Settlement upgrading: Area-based (i.e. urban – rural linkages) approach for increasing the resilience of water supply services (see comp 1) |
|  | Assets, services and livelihood security projects: Expanding and strengthening water infrastructure and services which are climate change resilient and sustainable (and capture best practices) (see comp 3) |
| - Improving knowledge and policies and regulations to increase urban resilience in the region: Project KM and replication, incl. development of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration) | Improvement of knowledge, policies regulations in the region: by developing a ‘regional’ approach model for managing urban risks and vulnerabilities in the context of climate change and urban (population) growth (also because of high influx of DPs), especially for type 2 cities, including gender considerations + sharing lessons |

*In line with World Bank et all (2017, policy note September 14): Refugees in the middle east. Bringing an urban lens to the forced displacement challenge.

Project Components and Financing

Table 4: project components and financing

| Project Components | Expected Outcomes | Expected Outputs | Countries |  | Amount (US$) |
| --- | --- | --- | --- | --- | --- |
| 1. Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from DPs migration | 1.1.1. Strengthened municipal institutional capacity to manage climate change and DP crisis related urban water scarcity challenges by mainstreaming these aspects into spatial strategies + developing action / investment plans and guidelines (with identified solutions) to use water most efficiently within municipal boundaries (in line with AF outcome 2) | 1.1. Territorial planning and development strategy / guidelines with CC and gender mainstreamed in Lebanon 1.2. Urban master plans at municipal level with CC and gender mainstreamed in Lebanon 1.3. Urban master plans at municipal level with CC and gender mainstreamed in Jordan Above strategies and plans including mapped current and future water demand needs and supply options considering esp. climate change, urban growth and agriculture evolution + action / investment plans (incl. identified solutions) to use water most efficiently within municipal boundaries Above also includes workshops / trainings targeting esp. women and youth (both host communities and DPs) to develop the plans | Lebanon Lebanon Jordan |  | 249,000 366,000 366,000 T: 981,000 |
| 2.Improve awareness, ownership and capacities to respond to climate change, incl, to operate, maintain and replicate resilient water harvesting, supply and irrigation systems | 2.1.1.Strengthened DPs and host community awareness and ownership of CC adaptation measures + capacities strengthened to operate, maintain and replicate proposed adaptation measures (in line with AF outcome 3 and 8) | 2.1. Community organisation, awareness and capacity building + operation, maintenance and replication/ upscaling plans for concrete adaptation output 3.1 2.2. See above for output 3.2. 2.3. See above for output 3.3. 2.4. See above for output 3.4. 2.5. See above for output 3.5. 2.6. See above for output 3.6. 2.7. See above for output 3.7. 2.8. See above for output 3.8 For more details see section II.A | Lebanon & Jordan |  | 177,400 139,200 234,000 316,300 16,000 276,700 259,000 314,600 T: 1,733,200 |
| 3.Expand unconventional water harvesting and supply options, using innovative and replicable techniques | 3.1.1. Increased adaptive capacity within the water sector through resilient and sustainable water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context and benefitting vulnerable groups (in line with AF outcome 4, 6 and 8 | 3.1. Rooftop rainwater harvesting in Lebanon 3.2. Rooftop rainwater harvesting in Jordan 3.3. Greywater treatment and reuse in Jordan 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon 3.5. Efficient treatment and reuse of wastewater in Jordan 3.6. Water-use-efficient irrigation of treated wastewater in Lebanon 3.7. Water-use Efficient irrigation of treated wastewater in Jordan 3.8. Permaculture demonstration - water use efficient system For more details see section II.A | Lebanon Jordan Jordan Lebanon Jordan Lebanon Jordan Jordan |  | 867,262 820,820 843,112 1,996,955 1,053,332 1,278,300 804,400 384,046 T: 8,048,227 |
| 4. Project KM and replication, incl. dev. of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration) | 4.1.1. Strengthened (inter)National institutional capacity to manage climate change and DP crisis related urban water scarcity challenges, including lessons learned collected and shared regionally (in line with AF outcome 3 and 8) | 4.1. Regional / international KM with focus on sharing project lessons and replication 4.2. Jordan and Lebanon KM with focus on project progress, best practices and lessons learned 4.3. Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities 4.4. Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities | Lebanon & Jordan (and other countries in the region that are part of ESCWA |  | 270,000 433,800 144,000 40,362 T: 888,162 |
| 5. Total components |  |  |  |  | 11,650,589 |
| 6. Project/Programme Execution cost 7. Total Project/Programme Cost 8. Project/Programme Cycle Management Fee charged by the Implementing Entity |  |  |  |  | 1,223,272 |
|  |  |  |  |  | 12,873,861 |
|  |  |  |  |  | 1,094,278 |
| Amount of Financing Requested |  |  |  |  | 13,968,139 |

Projected Calendar

| Milestones | Expected Dates |
| --- | --- |
| Start of Project/Programme Implementation | June 2020 |
| Project/Programme Closing | December 2024 |
| Terminal Evaluation | September 2024 |

Table 5: Project calendar

pART ii:  Project / programme JUSTIFICATION

- Project components

To achieve the overall project objective ‘Increasing the resilience of both displaced persons and host communities to climate change-related water challenges in Jordan and Lebanon’ the projects’ ‘core’ entails a set of ‘concrete’ adaptation actions, using innovative and replicable techniques that aim to reduce the demand of unsustainable water sources such as (polluted) groundwater, while increasing water supply options from non-conventional and more sustainable sources, such as rainwater harvesting and the reuse of treated waste water at municipal and community level (component 3). To ensure local ownership and capacity to ‘manage’ these ‘concrete’ adaptation actions and to avoid social tension of proposed project benefits, measures to inclusively plan, operate, maintain and replicate the actions are proposed at the community level (component 2). To better manage urban risks and vulnerabilities, especially related to the water sector, assessment and planning capacities will be strengthened at the municipal level (component 1). Based on above, a model to better manage urban risks and vulnerabilities suitable for a high DPs influx context area (in type 2 cities) will be developed, taking into account the impacts of climate change, especially on water resources. This model is relevant for the Mafraq region as well as areas with a similar context and will therefore be shared in the region (component 4). For detailed maps of target areas and conceptual drawings of concrete interventions, see annex 2. For details of all activities, see budget notes in annex 6.

The objectives of the proposal are in line with national priorities (see section II.D) and Adaptation Fund outcome areas, which resulted in the following components:

Component 1: Increasing the resilience of municipal governments: Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from DPs migration (in line with AF outcome 1 and 2).

This component will focus on strengthening municipal institutional capacity to manage climate change and DP crisis related urban water scarcity challenges by mainstreaming these aspects into spatial strategies and urban master plans + developing action / investment plans and guidelines (with identified solutions) to use water most efficiently within municipal boundaries. Thus, through this project, these strategies and plans will be used as tools to manage water, also for future needs. Municipal officers will be trained to developing these strategies and plans and to manage related urban risks and vulnerabilities.

Why is this needed: As tensions between DPs and host communities, especially around scare resources and jobs, are increasing, inclusive community-level planning processes are needed to support social exchange and to ensure equal benefits to interventions. However, in both Jordan and Lebanon, there is very limited capacity at the municipal/ community level to manage water in an efficient, comprehensive and forward-looking way. One of the reasons is the lack of coordination between different authorities (i.e. municipalities, water establishments, ministry of agriculture) and disciplines (i.e urban planners, water engineers and agriculture engineers), which all produce their separate plans, making planning often not inclusive and efficient. Besides that, in both Jordan and Lebanon, water management is the responsibility of national and governorate-level authorities. At this level, the focus is still very much on extracting water from conventional sources, especially groundwater, which is overexploited and increasingly polluted and current demand and supply focused, with limited consideration of climate change impacts and population growth and migration trends. However, municipalities are responsible for managing non-conventional water sources within their boundaries, including e.g. rain/storm-water, which opens up opportunities to plan and implement climate change adaptation options, such as rainwater harvesting, in an inclusive way.

Therefore, to respond to the issues of climate change and urban risks and vulnerabilities it is important to deal simultaneously with urbanization, water issues and agriculture in a forward-looking way. Municipalities need tools to do this, and the proposed strategies, plans and guidelines are just that.

For instance, the current Lebanon Bekaa Water Establishment water and wastewater masterplans are solely operational/sectoral plans that indicate the locations of the main supply and distribution of water and wastewater facilities. These plans lack any synergies with intersectoral issues that climate change has impact on. The  proposed strategies and plans aim to address these gaps by integrating the needs of various sectors in one area-based approach.

In Jordan, the current municipal master plan for Irbid was developed before the Syrian crisis and is outdated. In Mafraq, no master plan exists. In Lebanon, the same is the case for the municipalities surrounding Zahleh. The process of formulating strategies and plans will help the target municipalities to identify medium and long-term adaptation needs and to develop strategies to get these funded.

Component 2: Increasing the resilience of citizens (DPs and host communities): Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems (in line with AF outcome 3)

This component will focus on strengthened DPs and host communities awareness and ownership of climate change adaptation measures + capacities strengthened to operate, maintain and replicate proposed adaptation measures, including skills building.

Why is this needed: To ensure sustainability of the proposed adaptation measures under component 3, communities need to ‘own’ the interventions and it needs to be clear how the proposed measures will be operated, maintained and replicated. Because there is a lack of capacities to do this at the community level, these capacities will be strengthened, as well as the awareness of adaptation options.

Above will be done by developing operation, maintenance and replication plans for proposed adaptation actions in a participatory way, including identifying responsibilities and maintenance budgets. Women and youth organization will be strengthened and trained to lead water harvesting interventions at home / in the settlement and to use and replicate techniques.

Component 3: Increasing the adaptive capacity of the water sector: Expand unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context (in line with AF outcome 4 and 6).

This component will focus on increasing the adaptive capacity within the water sector through resilient and sustainable water supply, using innovative, climate change resilient water supply techniques, which are suitable for high DPs influx context and replicable and mostly benefit vulnerable groups, also through securing water-dependent livelihoods, especially in the agriculture sector. The purpose is to reduce the demand of unsustainable water sources such as (polluted) groundwater, while increasing water supply options from non-conventional and more sustainable sources, such as rainwater harvesting and the reuse of treated waste water.

Why is this needed This is needed because of increasing water availability challenges in both Jordan and Lebanon, exacerbated by climate change and the limited options municipal government have to respond to these challenges.

The proposed concrete adaptation measures all aim to harvest available water from non-conventional sources (rain and waste water) and to treat and irrigate it as efficient as possible. The proposed interventions include Rooftop rainwater harvesting systems and water saving devices, Greywater treatment and reuse systems  and water saving devices, Efficient treatment and reuse of waste water, incl. using wetlands, Water-use-efficient irrigation of treated wastewater systems and Permaculture demonstration -  closed loop water system.

These proposed measures were prioritised by the project steering committees (with representatives from different ministries and the target municipalities) and beneficiary communities (through consultations).

Rooftop rainwater harvesting systems will be established in municipal buildings, schools and mosques and residential buildings in the target areas in Jordan and Lebanon. Municipal buildings were selected as demonstration / awareness raising sites, while schools and mosques were selected because of high impact and awareness raising purposes, including through curriculum and religious leaders speeches inputs (see linked component 2). Residential buildings were selected to test these systems in all possible buildings with the purpose to identify how the rainwater harvesting intervention can be scaled-up to a municipal or national programme. In Jordan, various ministries requested UN-Habitat (see section II.I) to set-up a national programme for rainwater harvesting. Techniques will be piloted in Irbid and Mafraq, while a possible incentive mechanism will be developed under output 4.4.

Besides that, grey water treatment and reuse systems will be established in municipal buildings, schools and mosques in Jordan, also targeting religious leaders and children for awareness raising purposes (under linked component 2).

In both Jordan and Lebanon, the quality of waste water will be improved and water storage capacity increased to safely and efficiently irrigate agriculture land. In the target areas, release of untreated waste water and non-efficient use of treated waste water (due to lack of storage capacity and non efficient irrigation techniques) has been identified as a major problem and priority (see section II.I). Besides that, a permaculture demonstration site will be established at JUST university in Jordan, targeting students and surrounding farmers to replicate the techniques.

Component 4: Improving knowledge and policies and regulations to increase urban resilience in the region: Project KM and replication, incl. development of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration) (in line with AF outcome 7).

This component will focus on Strengthened (inter)National institutional  capacity to manage climate change and DP crisis related urban water scarcity challenges, including lessons learned collected and shared regionally.

Why is this needed: as mentioned above, there is a need for more effective, inclusive and sustainable programming focused on addressing water challenges, especially in ‘host’ (type 2) cities, exacerbated by both the influx of DPs and climate change impacts. There is an opportunity to share lessons between Lebanon and Jordan, but also in the region through the by UN-ESCWA established Arab Centre for Climate Change Policies and KM platform and to have the project outcomes and outputs feed into 3RP (i.e. Regional, Refugee and Resilience Plan) programming under the WASH sector (see annex 1).

Overview propsed project activities

Table 6: Jordan and Lebanon proposed project activities details and feasibility assessment outcomes. For detailed maps of target areas and conceptual drawings of concrete interventions, see annex 2.

| Problem description and climate change adaptation needs statement | Adaptation measure outcome (to address the problem and needs) | Detailed outputs / activities | Target areas | Suitability | Beneficiaries (Total, Women, Youth, Syrians – T, W, Y and S used below |  | Budget (USD) | Executing entity | Effectiveness in terms of adaptation / water saving and or collection |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Direct | Indirect |  |  |  |
| Component 1: Increasing the resilience of municipal governments: Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from DPs migration |  |  |  |  |  |  |  |  |  |
| Lack of municipal institutional and technical capacity to manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, including from DPs migration Lack of forward-looking planning, incl. capacity and tools at municipal level | Strengthen municipal institutional capacity to manage climate change and DP crisis related urban water scarcity challenges by mainstreaming these aspects into spatial strategies + developing action / investment plans and guidelines (with identified solutions) to use water most efficiently within municipal boundaries | - Territorial planning and development strategy / guidelines at district level with climate change and gender mainstreamed (Lebanon) | Zahle District | Target municipalities experience water challenges and have largest numbers of DPs in the country Proposed activities are aligned with national and municipal priorities, incl. municipal development plans Spatial strategies and urban master plans and action / investment plans / feasibility studies are suitable tools to plan water within municipal boundaries | Direct involvement T: 480 W: 40 % Y: 15 % | District: T: 429,824 W: 217,475 Y: 23,733 S: 243,465 | 249,000 | Consultancu firm | By planning and managing water in a forward-looking and holistically way, water will be managed much more efficiently and overall demand reduced |
|  |  | - Urban master plans at municipal level with climate change and gender mainstreamed (Lebanon) | Hazerta Bar Elias El Marj Saadnayel Taanayel Taalabaya Terbol Ferzol |  | Direct involvement T: 240 W: 40 % Y: 15 % | Municipalities: T: 167,631 W: 84,815 Y: 9,256 S: 94,951 | 366,000 | Consultancu firm |  |
|  |  | - Urban master plans at municipal level with climate change and gender mainstreamed (Jordan) | Mafraq Irbid |  | Direct involvement T: 450 W: 15 % Y: 10 % | Municipalities: T: 863,691 W: 415,440 Y: 259,107 S: 205,202 | 366,000 | Consultancu firm |  |
| Total |  |  |  |  | 930 |  | 981,000 |  |  |
| Component 2: Increasing the resilience of citizens (DPs and host communities): Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems |  |  |  |  |  |  |  |  |  |
| Lack of citizen awareness of climate change, esp. water scarcity challenges and capacities to respond to these challenges locally | Strengthened DPs and host communities awareness and ownership of climate change adaptation measures + capacities strengthened to operate, maintain and replicate proposed adaptation measures, including skills building | - Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1: Rooftop Rainwater Harvesting in Lebanon | Zahle Ablah Hazerta, Saadnayel Bar Elias El-Marj | Citizens have limited awareness of water scarcity challenges, especially climate change-related Capacities to operate, manage and replicate relevant techniques are limited, esp. related to water harvesting, efficient irrigation and permaculture Large numbers of citizens can be reached through curricula, imams, demonstration sites, also in municipal government buildings | Direct involvement T: 55,000 W: 27,689 Y: 2,950 S: 29,300 | Municipalities: T: 300,877 W: 154,582 Y: 16,548 S: 170,296 | 177,400 | UNICEF LARI/Company (in line with output 3.1.) | Increased acceptance efficient water use, supply and irrigation techniques Increased capacity to operate, maintain and replicate techniques, including monitoring |
|  |  | - Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1: Rooftop Rainwater Harvesting in Jordan | Mafraq: Qasabit Mafraq Irbid: Qasabit Irbid Bani Obeid Ramtha |  | Direct involvement T: 52,855 W: 26,420 Y: 19,385 S: 8,728 | Municipalities: T: 863,691 W: 415,440 Y: 259,107 S: 205,202 | 139,200 | JOHUD (in line with output 3.2.) |  |
|  |  | - Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.3: Grey Water Treatment and Reuse in Jordan | Mafraq: Qasabit Mafraq Irbid: Qasabit Irbid Bani Obeid Ramtha |  | Direct involvement T: 39,582 W: 21,940 Y: 15,646 S: 6,827 | Municipalities: T: 863,691 W: 415,440 Y: 259,107 S: 205,202 | 234,000 | UNICEF (in line with output 3.3.) |  |
|  |  | - Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.41: Efficient treatment and reuse of wastewater from Zahle WWTP, in Lebanon | Zahle |  | Direct involvement T: 816 W: 416 Y: 85 S: 766 | Municipalities: T: 184,332 W: 94,705 Y: 10,140 S: 104,332 | 163,200 | RTO LARI (in line with output 3.4.1) |  |
|  |  | - Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.4.2: Efficient treatment and reuse of wastewater through wetlands, in Lebanon | Bar Elias |  | Direct involvement T: 1200 W: 600 Y: 300 S: 600 | Municipalities: T: 69,124 W: 35,514 Y: 3,802 S: 39,124 | 153,100 | UNICEF BWE/Company LRA/Company (in line with output 3.4.2) |  |
|  |  | - Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation 3.5: Efficient treatment and reuse of wastewater in Jordan | Jerash(Ketteh) Mafraq (Al-Ghadeer Al-Abyad and Al-Akaider) |  | Direct involvement T: 35 W: 5 Y: 2 S: 0 | Municipalities: T: 11229 W5342 Y: 2972 S: 727 | 16,000 | WAJ / YARMOUK (in line with output 3.5.) |  |
|  |  | - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.6: Water-use-efficient irrigation of treated wastewater for fruit trees in Lebanon | Zahle |  | Direct involvement T: 1,682 W: 864 Y: 93 S: 952 | Municipalities: T: 184,332 W: 94,705 Y: 10,140 S: 104,332 | 142,100 | RTO/Company LARI/Company (in line with output 3.6.1) |  |
|  |  | - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.6: Water-use-efficient irrigation of treated wastewater for potato crops (40 ha) in Lebanon | Bar Elias |  | Direct involvement T: 622 W: 320 Y: 34 S: 352 | Municipalities: T: 69,124 W: 35,514 Y: 3,802 S: 39,124 | 134,600 | RTO/Company LARI/Company (in line output 3.6.2) |  |
|  |  | - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7: Water-use Efficient irrigation of treated wastewater from Maerad and Al Akaider WWTPs in Jordan | Jerash (Ketteh) Mafraq (Al-Akaider) |  | Direct involvement T: 450 W: 200 Y: 150 S: 150 | Municipalities: T: 9568 W: 4528 Y: 2474 S: 561 | 144,800 | JOHUD (in line with output 3.7.1) |  |
|  |  | - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7: Water-use Efficient irrigation of treated wastewater from Mafraq WWTP in Jordan | Mafraq (Al-Ghadeer Al-Abyad) |  | Direct involvement T: 300 W: 120 Y: 180 S: 100 | Municipalities: T: 1,661 W: 814 Y: 498 S: 166 | 114,200 | BADIA (in line with output 3.7.2) |  |
|  |  | - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 2.8; permaculture demonstration | Irbid (Ramtha) |  | Direct involvement / targeted T: 300 W: 150 Y: 45 S: 30 | Municipalities: Students: 23,000 W: 11,500 Farmer family: 400 W: 200 Y: 60 S: 40 | 314,600 | PRI (in line with output 3.8 |  |
| Total |  |  |  |  | T:113,860 W:>40 % Y:>15 % |  | 1,733,200 |  |  |
| Component 3: Increasing the adaptive capacity of the water sector: Expand unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context |  |  |  |  |  |  |  |  |  |
| Lack of water availability in target areas, which will worsen with climate change: Lack of using rainwater efficiently and lack of showcases to build on to set-up a municipal or national rainwater harvesting programme | Increased adaptive capacity within the water sector through resilient water harvesting options Water to be used for toilets, gardening, etc., not drinking Showcasing water harvesting options in different buildings | 3.1. Rooftop rainwater harvesting in Lebanon 20 systems (large) - 11 Educational facilities - 7 Religious buildings - 1 Health facility - 1 Municipal building (show room in building with RWH system, GWTR system and WSDs | Zahle Ablah Hazerta Saadnayel Bar Elias El-Marj | Target municipalities experience water challenges and have largest numbers of DPs in the country Aligned with national and municipal priorities, incl. municipal development plans Municipalities are mandated to manage water within municipal boundaries, which includes rainwater harvesting options Schools and mosques are targeted because of large water harvesting potential + awareness raising potential (see comp) | Direct involvement T: 55,000 W: 27,689 Y: 2,950 S: 29,300 | Municipalities: T: 300,877 W:154,582 Y: 16,548 S: 170,296 | 867,262 | UNICEF | 1,410 m3 |
|  |  | - Rooftop rainwater harvesting in Jordan 86 systems: - 49 schools (of which 18 rehabilitation) - 15 mosques - 20 residential buildings - 2 municipal buildings with RWH system | Irbid (Qasabit Irbid, Bani Obeid, Ramtha) Mafraq (Qasabit Mafraq) |  | Direct involvement T: 52,855 W: 26,420 Y: 19,385 S: 8,728 | Municipalities: T: 863,691 W: 415,440 Y: 259,107 S: 205,202 | 820,820 | JOHUD | Av school saving (Irbid):528m3 Av saving for 40 schools (Irbid): 21,120m3 Av school saving (Mafraq):101m3 Av wsaving 9 schools (Mafr): 909m3 Total: 22,029m3 |
| Lack of water availability in target areas, which will worsen with climate change: Lack of using grey water efficiently | Increased adaptive capacity within the water sector through resilient water treatment and reuse options in buildings Water to be used for toilets, gardening, etc., not drinking | - Greywater treatment and reuse in Jordan 40 systems: - 35 schools - 5 mosques | Irbid (Qasabit Irbid, Bani Obeid, Ramtha) Mafraq (Qasabit Mafraq) |  | Direct involvement Schools: T: 39582 W: 21940 S: 6827 | Municipalities: T: 863,691 W: 415,440 Y: 259,107 S: 205,202 | 843,112 | UNICEF | Potential Monthly Water Quantity Treated and Reused (m3): 4,369 m3 |
| Lack of water availability in target areas, which will worsen with climate change: Lack of re-using treated wastewater efficiently due to: - Lack of quality - Lack of storage capacity | Increased adaptive capacity within the water sector through resilient water treatment and reuse options - efficient use of treated wastewater systems through improved quality of treated wastewater + storage capacity for efficient irrigation purposes | - Efficient treatment and reuse of wastewater from Zahle WWTP, in Lebanon Diverting the plant’s treated effluent for irrigation purposes. | Zahle (Cadastres: Zahle Aradi, Zahle Haouch El-Oumara Aradi, Zahle Haouch EL-Oumara, Zahle Maallaqa Aradi) | Target municipalities experience water challenges and have largest numbers of DPs in the country Aligned with national and municipal priorities, incl. municipal development plans Farmers are facing water scarcity challenges because the WWTPs do not produce and store enough clean water; waiting list for farmers exist to get access to WWTP water (through contract) Zahle WWTP releases treated water into Litani River which does not directly benefit the area’s farmers. Farmers use polluted water from rivers for crop irrigation. Treated water from WWTP in Jordan is lost during the night because of lack storage capacity and water already used by farmers lacks quality | From WWTP T: 3,917 Women 2013 Youth 216 Syrians 2217 | Municipalities: T: 184,332 W: 94,705 Y: 10,140 S: 104,332 | 846,120 | RTO/Company | 18,000 m3 treated daily for 116 Hectares of agricultural lands |
|  |  | - Efficient treatment and reuse of wastewater through wetlands, in Lebanon 60,000 sqm Free Water Surface to clean the Ghzayel tributary river, incl. earthworks; lining; pumping, fencing; vegetation. | Bar Elias |  | From wetlands T: 2,304 W: 1,184 Y: 127 S: 1304 | Municipalities: T: 69,124 W: 35,514 Y: 3,802 S: 39,124 | 1,150,835 | UNICEF | 6,000 m3 of tributary water for 70 Hectares of croplands |
|  |  | - Efficient treatment and reuse of wastewater in Jordan Improving water quality and storage capacity for irrigation use from Maerad WWTP | Jerash (Ketteh) |  | T: 77 W: 31 Y: 20 S: 15 Farms: 25 | Municipalities: T: 7,919 W: 3,789 Y: 1,980 S: 396 | 426,357 | WAJ / YARMOUK | Water Storage: 3,000m3 |
|  |  | - Efficient treatment and reuse of wastewater in Jordan Improving water quality and storage capacity for irrigation use from Al Akaider WWTP | Mafraq |  | T: 78 W: 31 Y: 20 S: 15 Farms: 32 | Municipalities: T: 1,649 W: 739 Y: 494 S: 165 | 496,400 | WAJ / YARMOUK | Water Storage: 2,000m3 |
|  |  | - Efficient treatment and reuse of wastewater in Jordan Improving water quality for irrigation use from Mafraq WWTP | Mafraq |  | T: 120 W: 35 Y: 20 S: 25 Farms: 40 | T: 1,661 W: 814 Y: 498 S: 166 | 130,575 | WAJ / YARMOUK | Irrigated dunums: 100 |
| Lack of water availability in target areas, which will worsen with climate change: Lack of using water efficiently in agriculture practices | Increased adaptive capacity within the water sector through water efficient irrigation options – Efficient irrigation of treated wastewater to farmland with accepted irrigation technology | - Water-use-efficient irrigation of treated wastewater for fruit trees and vineyards in Lebanon from Zahle WWTP, Lebanon Replace surface irrigation for fruits trees and vineyards with drip systems (pumps, filters, sensors, automated tools) | Zahle | Target municipalities experience water challenges and have largest numbers of DPs in the country Aligned with national and municipal priorities, incl. municipal development plans; in Jordan, sprinklers are forbidden by law but still often used. Farmers are facing water scarcity challenges but often don’t use efficient water use irrigation systems | T: 4,495 W:2,293 Y: 540 S: 2,525 F: Leb: 394; Syr: 505 | Municipalities: T: 253,456 W: 130,219 Y: 13,941 S: 143,456 | 928,950 | RTO/Company | 110 Hectares of agricultural |
|  |  | - Water-use-efficient irrigation of treated wastewater for potato crops in Lebanon from Bar Elias wetland, Lebanon.Drip systems for potato plantations | Bar Elias |  |  |  | 349,350 | RTO/Company | 40 Hectares of croplands |
|  |  | - Water-use Efficient irrigation of treated wastewater from Maerad and Al Akaider WWTPs in Jordan. Modern irrigation system | Jerash (Ketteh) Mafraq (Akaider) |  | T: 155 W: 62 Y: 40 S: 30 Farms: 40 | Municipalities: T: 9568 W: 4528 Y: 2474 S: 561 | 406,400 | JOHUD | 120 donums Increase the amount of reclaimed water allocated for irrigation to 15% |
|  |  | - Water-use Efficient irrigation of treated wastewater from Mafraq WWTP, Jordan. Modern irrigation system | Mafraq |  | T: 120 W: 35 Y: 20 S: 25 Farms: 40 | T: 1,661 W: 814 Y: 498 S: 166 | 398,000 | BADIA | 100 donums Increase the amount of reclaimed water allocated for irrigation to 15% |
| Lack of water availability in target areas, which will worsen with climate change: Lack of using water and other resources Incl. waste) efficiently in agriculture production systems | Permaculture demonstration site showing efficient water use system for student and farmers; This includes organic production examples that increase the quality and the quantity of soil (creating a bio-sponge) while producing nutrition-dense food. This system reduces water needs | - permaculture demonstration – efficient water use system Bio-Fertilizer production; Crop Garden and Compost Egg laying Chickens; Bees / apiculture; Compost worms; Olive Orchard Monoculture Conversion to Food Forest | Jordan University of Science and Technology campus Irbid (Ramtha) | Target areas experience water challenges and have the largest numbers of DPs in the country; Farmers are facing water scarcity challenges but often don’t use water efficiently; The area experiences unsustainable land use / agriculture practices that resulted in degradation of ecosystems leading to reduced services and food security issues | T: 300 W: 150 Y: 45 S: 30 Students: 200 | Students: 23,000 W: 11,500 Farmer family: 400 W: 200 Y: 60 S: 40 Community: 2,000 W: 1,000 Y: 300 S: 200 | 384,046 | Permaculture Research Institute in cooperation with Jordan University of Science and Technology (JUST) | Water is saved by increasing the quality and the quantity of soil, creating a bio-sponge. |
| Total |  |  |  |  | T: 119,421 (much overlap with comp 2) W:>40 % Y:>15 % |  | 8,048,227 |  |  |
| Component 4: Improving knowledge and policies and regulations to increase urban resilience in the region: Project KM and replication, incl. development of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration) |  |  |  |  |  |  |  |  |  |
| Lack of (inter)national institutional and technical capacity to manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, including from DPs migration | Strengthened (inter)National institutional capacity to manage urban climate change and DP crisis related water scarcity challenges, including lessons learned collected and shared regionally; Through these activities knowledge between Jordan and Lebanon and the larger MENA / Arab region will be shared + some global exposure | - Regional / international KM with focus on sharing project lessons and replication | MENA + Arab region and global | The MENA region is the most water scarce region in the world combined with the highest share of DP urban population Climate change action considering DPs crisis impacts, esp. in urban areas, is very limited | T: 200 W:>40 % Y: >15 % | Total MENA region | 270,000 | UN ESCWA | By planning and managing water in a forward-looking and holistically way, water will be managed much more efficiently and overall demand reduced |
|  |  | - Jordan and Lebanon KM with focus on project progress, best practices and lessons learned | Jordan & Lebanon |  | T: 200 W:>40 % Y: >15 % | All target ministerial and municipal staff | 433,800 |  |  |
|  |  | - Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities | Target municipalities |  | T: 200 W:>40 % Y: >15 % | All target municipal staff | 144,000 | Consultancy firm |  |
|  |  | - Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities | Jordan and possibly Lebanon |  | T: 200 W:>40 % Y: >15 % | All target municipal staff | 40,000 | Consultancy firm |  |
| Total |  |  |  |  | T: 600 W:>40 % Y:>15 % |  | 888,162 |  |  |
| Grand total |  |  |  |  | T: 120,951 W:>40 % Y:>15 % |  | 11,650,589 |  |  |

- Promotion of innovative solutions

Component 1: The proposed Territorial planning and development strategy and Urban master plans at municipal level aim to enable district and municipal governments to manage climate change and DP crisis related urban water scarcity challenges within their borders through a participatory approach. This approach will allow for more coordinated and forward-looking investment in infrastructure and services, which is currently lacking in the target areas and at the municipal level. The approach is not only unique for the target countries and target municipalities, but also for the region, as the assessment and planning approach responds to both climate change and DP crisis issues and aim to reduce tension over scarce resources. Therefore the replication of this model will be promoted (through outputs 4.1, 4.2 and 4.3).

Component 2: The proposed measures aim to ensure sustainability (maintenance and replication) of the proposed concrete adaptation measures under component 3. Although this is not innovative, using community-level adaptation related planning and decision-making (also under component 1) as a tool to enhance social cohesion (i.e. avoid tension over scarce resources) is unique and very relevant and timely in the case of Lebanon and Jordan, where increased tension between DPs and host communities has been reported. Especially women and youth groups will be encouraged to participate in the exchange and planning process.

Component 3: The project proposes to use innovative internationally proven technologies to increase water availability from non-conventional sources and using it efficiently, while in that way reducing water demand from conventional sources such as (often polluted) groundwater. The purpose is the showcase intervention / techniques that are suitable for urban areas, considering urban-rural linkages, and that can also be used elsewhere in the Jordan and Lebanon and in the region. Although some rainwater harvesting initiatives exist in Jordan and Lebanon, showcasing these in various types of buildings, including costs and benefits and replication options, will be a step to upscale such ‘lose’ initiatives towards municipal and even national rainwater harvesting programmes (see output 4.4), which has been pointed out as a priority in Jordan. Wastewater treatment and its use in agriculture is practiced in Jordan, but the water quality of often not good enough and storage capacity is lacking. In Lebanon, treating wastewater to a quality that it can be used in agriculture is not common practice and to showcase best practices, including standards, in both Jordan and Lebanon can be examples for both countries (which exchange to learn from both approaches (under output 4.2) and the larger region (under output 4.1.). The same accounts for the proposed wetland in Lebanon, which cleans river water, and was prioritised by the Lebanese government to be fully tested. While drip-irrigation exists in both Jordan and Lebanon, sprinklers are still often used. Therefore a transfer to more water-use efficient irrigation technology is needed. The innovative permaculture concept has shown to be promising in Jordan through the national AF project and will be promoted through student (to be involved with surrounding farmers and communities) and in the region (output 4.1) and in Lebanon (through output 4.2).

Component 4, The assessment and planning approach under component 1 is not only unique for the target countries and target municipalities, but also for the region, as it responds to both climate change and DP crisis issues and aim to reduce tension over scarce resources. Therefore the model will be further developed under output 4.3, including best practices (and standards) of proposed concrete adaptation measures and replication of this model will be promoted through outputs 4.1, 4.2 and 4.3. Under output 4.4. mechanisms to upscale rainwater harvesting initiatives towards municipal and even national rainwater harvesting programmes will be identified, which would be a great step towards a national water saving impact.

- Economic, social and environmental benefits

The proposed project aims to maximize benefits to the most vulnerable groups, including DPs, poor Lebanese and Jordanians, women and youth, and to avoid any negative environmental and social impacts.

Table 7: Project Economic, Social and Environmental benefits

| Type of benefit | Baseline |  | With/after project |
| --- | --- | --- | --- |
| Economic | Climate change is already leading to economic and livelihood losses, especially caused by less rain, droughts and water evaporation. Water dependent livelihoods, especially in the agriculture sector, are especially threatened; A large share of DPs, poor Lebanese and women are dependent on the agriculture sector for their income | - The governments, at different levels, but especially at the municipal level, will be able to better assess, plan and manage scarce water resources, which are also of economic importance - Through rainwater harvesting and grey water treatment and ruse interventions, water losses will be reduced / water saved, which will also save costs. - Through the treatment and reuse of wastewater interventions, water losses will be reduced / water saved, which will also save costs, both for the Water Authorities of Jordan (esp Yarmouk, which has very limited resources), but also for the farmers, as water will be provided against reasonable costs. Without this intervention, farmland may be lost, which is also a treat to food security. - The agriculture sector in target areas will be more climate change / drought resilient, leading to improved livelihood security, benefitting especially DPs, poor Lebanese and Jordanians, women and youth, with more secure / higher income. - The permaculture intervention is to show student and farmers that through this approach water and resources can be used efficiently, making it a replicable business case. It will also increased crop diversity and productivity; |  |
| Social | Climate change is already leading to negative social impacts, especially caused by less rain, droughts and water evaporation, leading to rural –urban migration, and social tension and incoherent development. | - The governments, at different levels, but especially at the municipal level will be able to better assess, plan and manage scarce water resources, also with the purpose to enhance social cohesion (i.e. avoid / reduce tension) over scarce water resources. - Inclusive assessment, planning and decision-making processes over scare water resources, also involving DPs, poor Lebanese and Jordanians, women and youth, will enhance social cohesion (i.e. avoid / reduce tension) over scare water resources. - Climate change resilient techniques skills building activities, including to operate, sustain and replicate these (especially targeting women and youth) + resilient water supply and irrigation systems, will benefit the most vulnerable, including DPs, poor Lebanese and Jordanians, women and youth. - Water resources and water dependent livelihoods (i.e. agriculture) will be protected from pollution and through waste water treatment. This will reduce health issues, of whom the most vulnerable / poor groups suffer the most. Currently, water-related health issues are very high in the Bekkaa area compared to other areas. - Harvesting systems and grey water reuse in public buildings, especially schools, will raise awareness for sustainable water use and climate change for students and through religious leaders - ‘Peacebuilding’ through involving youth and thus reducing possible tension between host and DP communities that is most likely to occur among youth. |  |
| Environmental | Climate change is already leading to negative environmental impacts, especially land / soil degradation and desertification and overexploitation of resources. Moreover, due to the crisis, untreated wastewater is increasingly polluting water resources | - The government, at different levels, will be able to better assess, plan and manage scarce water resources - Water resources and water dependent livelihoods (i.e. agriculture) will be protected from pollution and through waste water treatment. This will reduce health issues, of whom the most vulnerable / poor groups suffer the most. Currently, water-related health issues are very high in the Bekkaa area compared to other areas; Waste water treatment and reuse facilities to irrigate agriculture land and efficient water use options and permaculture will reduce groundwater and agriculture pollution while enhancing sustainable access to water, thus also securing agriculture livelihoods. - Rooftop rainwater harvesting increases water availability at building and residential household level, and reduces urban flash flooding probabilities and reduces illegal connection to wastewater network thus reducing manhole flooding in the streets in winter season - Introduction of unconventional water sources will help decrease pressure on the already depleting groundwater resources in some areas. - Permaculture: water needs reduced; pesticides and related soil/water pollution reduced; overall land / soil degradation reduced. |  |

The number of direct beneficiaries is estimated at 930 for component 1, 113,860 for component 2,  119,421 for component 3 and 600 for component 4 (see table 6). Apprimately one forth of the target population is Syrian. Targets for women and youth are set at 40 percnet for women and 15 percent for youth. Because there is some overlap with beneficiaries between component 2 and 3, the total number of project direct benefificaries is estimated at around 120,000. However, with a large share of the project activities focus on replication and knowledge sharing, the number is of indirect beneficiaries is expected to be very large. Moreover, indirect positive impacts of increased water availability and quality and livelihood sustainability is expected to have benefits for whole communities.

- Cost-effectiveness

Table 8: Proposed adaptation actions’ cost-effectiveness rationale

| Proposed adaptation actions / outputs | Rationale why priority actions have been selected from a cost-effectiveness perspective and alternative actions considered |
| --- | --- |
| 1.1. Territorial planning and development strategy / guidelines with CC and gender mainstreamed in Lebanon 1.2. Urban master plans at municipal level with CC and gender mainstreamed in Lebanon 1.3. Urban master plans at municipal level with CC and gender mainstreamed in Jordan | A total of over 1 million people in the project target areas will benefit indirectly from municipal level master plans, which means the plans. Municipal master plans are a cost-effective ways to assess, plan and manage water resources efficiently and comprehensively by looking at the whole system and future trends and projections (including for implementation of concrete adaptation actions such as below). These strategies will reduce water use costs because of more efficient use within the system and avoid costs associated with future climate change related water scarcity issues. However, these strategies and plans should be seen as a package to better plan for concrete adaptation actions in the future, and thus also sustain these. Alternatively, Integrated Water Resource Management is an approach to comprehensively plan and manage water within a system, but this is not a ministry priority. Currently, water is managed at higher levels (ministry) with a focus on current demand and supply. |
| 2.1. Community organisation, awareness and capacity / skill building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.1 2.2. See above for output 3.2. 2.3. See above for output 3.3. 2.4. See above for output 3.4. 2.5. See above for output 3.5. 2.6. See above for output 3.6. 2.7. See above for output 3.7. 2.8. See above for output 3.8 | Participatory planning processes are required to ensure ownership over to be implemented concrete adaptation measures. Participatory processes to operate, maintain and replicate interventions is required to sustain them. Moreover, some monitoring activities are needed to measures to effectiveness and sustainability of proposed concrete measures Alternatively, interventions are planned and executed top-down, but this may lead to lack of ownership and capacity to operate, maintain and replicate proposed concrete measures, which would result in a loss of investment |
| 3.1. Rooftop rainwater harvesting in Lebanon 3.2. Rooftop rainwater harvesting in Jordan 3.3. Greywater treatment and reuse in Jordan 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon 3.5. Efficient treatment and reuse of wastewater in Jordan 3.6. Water-use-efficient irrigation of treated wastewater in Lebanon 3.7. Water-use Efficient irrigation of treated wastewater in Jordan 3.8. Permaculture demonstration - closed loop water system in Jordan | Proposed concrete adaptation actions are cost-effective solutions in a water-scare context. Rainwater harvesting options are regarded as being cost-effective when the investment is returned within an accepted number of years or when it supports awareness raising purposed, which will be the case as many students and inhabitants visit the target schools, mosques and municipal buildings. Wastewater treatment and reuse systems are regarded as being cost-effective when availability of groundwater is limited and when the action can stop pollution of water (used for agriculture). This is the case in the target areas and therefore the proposed measures are expected to have a positive impact on the surrounding communities. The permaculture intervention can be regarded as cost-effective because it will teach students, whom are expected to share and apply their knowledge more widely, also with surrounding communities / farmers. Alternatively, conventional water supply methods are used, such as continued pumping of groundwater, but this is not sustainable / climate change resilient in areas that already suffer from water scarcity. Moreover, groundwater is often polluted. |
| 4.1. Regional / international KM with focus on sharing project lessons and replication 4.2. Jordan and Lebanon KM with focus on project progress, best practices and lessons learned 4.3. Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities 4.4. Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities | Regional project steering committee meetings (output 4.2) are organised, where possible, in conjunction with relevant regional events (output 4.1), thus avoiding double costs for travel and allowances. Relevant project lessons will be shared regionally and even globally through an existing relevant KM platform (output 4.1),and outreach mechanism, thus avoiding cost for this. Replicating the model developed under output 4.3. (through outputs 4.1 and 4.2) may result in adoption of the model elsewhere and in that way increase efficient use of water, also looking at the future, and in that way, avoiding related cost of non-adoption. Alternatively, best practices and approaches are not shared regionally, which may lead to loss of investments is countries and urban areas, which need to deal with similar situations. |

Altogether, the project will be cost-effective by:

- Avoiding future costs associated with damage and loss due to climate change impacts (especially less rain and droughts) and to ensure the interventions are sustainable;

- Efficient project operations because of ‘in-house’ technical support options and capacity building expertise and because of direct partnering with communities (thereby building their capacity as well as reducing costs) and specialist agency such as UNICEF and UN-ESCWA

- Community involvement with development / construction of concrete interventions and because of community capacity building especially for youth who would ensure the sustainability of the project.

- Having selected technical options based on cost-, feasibility and resilience/sustainability criteria

- Consistency with national or sub-national strategies

Both Jordan and Lebanon have advanced climate action agendas, since both countries ratified the UNFCCC in 1994. Both countries submitted the Third National Communications (TNC) and an INDC to the UNFCCC, while also having done Climate Change Technical Needs Assessments TNA). Jordan also has a national climate change policy (also for water). However, the institutional and individual capacities, especially at sub-national levels, for effective climate programming (e.g. through spatial strategies and planning) is still weak. A detailed overview of project consistency with all relevant national and sub-national priorities has been developed in table 9 below.

The project proposal especially aligns with the INDC, TNC and TNA and National Water  (Sector) Strategies in both countries. In Jordan, the project proposal also aligns with the National climate change policy (for water). Relevant ministries have been consulted to fully align with their most recent priorities (see section II.I). During the full proposal development phase, the established national project steering committees re-prioritised some interventions, including the proposed wetlands in Lebanon and the selected WWTP in Jordan. In both Jordan and Lebanon, municipalities are mandates to develop municipal master plans. Moreover, municipalities are required to manage water, especially non-convention sources such as stormwater and rainwater, within their municipal boundaries. Although Irbid has a master plan, it is outdates and other municipalities don’t have these plans, which can be used to manage water within their boundaries, including consideration of climate change, DPs migration trends and gender.

Table 9: Jordan project alignment with National and sub-national priorities

| Policy / Document | Year submitted / ratified | Relevant priorities |
| --- | --- | --- |
| Jordan |  |  |
| Climate Change strategies / plans |  |  |
| Jordan’s Climate Change Policy for a Resilient Water Sector (2016-2025) | 2016 | This document is an integral part of the National Water Strategy (2016 – 2025) and related policies and action plans published by Ministry of Water and Irrigation (MWI). It lists a number of water-related solutions that the project aligns with. These include: - Water storage e.g. dams & reservoirs and ponds - New water, water harvesting (in combination with supplementary irrigation for drought and climate-proofing and increasing the water use efficiency of primarily rain fed agriculture, which is practiced on 60% of Jordan’s cropland), water transfers, wastewater collection/treatment/reuse - Water quality protection and improvement, to increase water availability for unrestricted use; - Integrated water and land planning / management / zoning, water-smart land use, including urban planning - Water (and energy) demand management: via technical measures, e.g. infrastructure rehabilitation and reduction of transmission losses (according to the 3rd National Communications the main threat to rainfed cultivation in Jordan is urban expansion). - Better use of rainfall, more efficient irrigation - Improvements in water use efficiency, e.g. driven by demand-management or water reallocations, these generally also translate into energy savings18; - Training and capacity development: public awareness and behavioural change e.g. mainstreaming climate expertise into water management, facilitating the use of climate data for planning and early warning (climate services); and training of experts for writing successful proposals to international climate funds. The action plan for the Climate Change Policy can build on existing Integrated Water Resources Management (IWRM) activities. However, the implementation has been slow so far. In order to avoid such problems, the action plan needs to include incentives for effective implementation and enforcement of the Climate Change Policy. |
| Jordan’s Third National Communication on Climate Change | 2014 | A document submitted to UNFCCC by Ministry of Environment and United Nations Development Programme, it stated that the expected reduced precipitation, maximum temperature increase, drought/dry days and evaporation are the main determinants of climate change hazards. The impact of the increased evaporation and decreased rainfall will result in less recharge and therefore less replenishment of surface water and groundwater reserves. In the long term, this impact will extend to cause serious soil degradation that could lead to desertification, exacerbating future conditions and worsening the situation of the agricultural sector due to the lack of sufficient water that will affect the income of the agriculture sectors. The proposed project aligns with the document by; - Enhancing climate vulnerability analysis at the local level. - Implementing the adaptation strategies and measures suggested by the report specifically for the water sector; - Rainwater Harvesting - Wastewater treatment - Desalination - Increasing Efficiency of irrigation technologies - Greywater Reuse - Raise Public Awareness |
| Jordan’s Intended Nationally Determined Contribution (INDC) | 2015 | The project is well aligned with some of the adaptation measures for the water sector listed in the INDC: - Reducing water losses in distribution pipes; - Introducing water saving technologies such as low-flow toilets and showers, and efficient appliances; - Collection of rainwater for gardens, toilets, and other applications; - Promoting water saving by awareness campaigns. - Improving wastewater treatment plants (WWTP); - Recycling wastewater; - Increasing public awareness to water related issues; |
| The National Climate Change Policy of the Hashemite Kingdom of Jordan (2013-2020)- Sector Strategic Guidance Framework | 2013 | National Climate Change Policy, published by the Ministry of Environment of Jordan, aims to achieve a pro-active, climate risk-resilient Jordan, to remain with a low carbon but growing economy, with healthy, sustainable, resilient communities, sustainable water and agricultural resources, and thriving and productive ecosystems in the path towards sustainable development. 8 of 14 Climate Change Policy are designated for a Resilient Water Sector This Policy will provide guidance to the Government of Jordan to implement the major climate change objectives of national priority related to adaptation The project is aligned with numerous adaptation measures listed as follows: Water Sector: - Further mainstream climate change consideration in water sector strategies, policies, and planning documents on all levels; - Address the use of treated/recycled wastewater in the regulation/ directives on the demand-side such as grey water as part of codes and regulations for buildings including, high-rise and high-density buildings; Improve the domestic water distribution networks, including reducing water losses and energy efficiency in pumping; - Develop proposals for adaptation in the water sector for financing from international climate change adaptation funds Agricultural/food security and production: - Develop a comprehensive insurance system for agriculture; Permaculture. - Promote water use efficiency in agriculture. |
| Climate Change Technology Need Assessment Project of Jordan (TNA) | 2017 | The Report outlines all the adaptation technology options available for water sector in Jordan and prioritized them based on most cost-effective, sustainable and socially acceptable options. It also highlighted the main barriers to adopting each of these technologies that should be addressed. The top three adaptation technologies for water sector include rainwater harvesting; water users association; and desalination/brackish water treatment and re-use. The AF project is in line with TNA plan which has selected water and agriculture as two of Jordan’s most significant adaptation sectors. |
| NAP | (Forthcoming in 2020) |  |
| National Development strategies / plans |  |  |
| Jordan 2025- Part 1 Jordan 2025- Part 2 | 2015 | This document (Jordan 2025) represents a long-term national vision and strategy (framework) rather than a detailed government action plan. The vision acknowledged the impact of climate change in widening the gap between water supply and water demand. The project is aligned with the vision’s objective to maximize the utilization of water and the reuse of waste water. |
| Jordan Economic Growth Plan 2018-2022 | 2018 | The JEGP is comprised of economic, fiscal and sectoral strategies that outline the vision and policies pertaining to each sector published by The Economic Policy Council. The project is aligned with JEGPin terms of achieving water security through ; - Integrating the management of water resources by increasing the quantities of water available and storage capacity of all the WWTP. Also implementing rainwater harvesting interventions - Improving the quality of water and wastewater services. - Supplying water for agriculture through replacing freshwater from surface and groundwater sources with treated wastewater from wastewater treatment plants - Promote efficient use of water in irrigation and high-yield agricultural products. - Adopt and publish an updated “Action Plan” to reduce water sector losse. |
| A National Green Growth Plan for Jordan (2017-2025) | 2017 | This NGGP seeks to understand what prevents Jordan from implementing the goals established in Jordan’s current plans and strategies, and offers suggestions in the context of green growth for other aspirations that will help to futureproof Jordan’s Vision. The plan identified water as one of main six priority sectors that provide coverage of key green growth issues and opportunities for Jordan. The project is aligned with the plan in terms of: - Acknowledging that water sector presents a crucial challenge to Jordan and that climate change has exacerbated existing water security issues resulting in significant negative implications for social development. Promoting the reuse of wastewater - Reallocate humanitarian funding towards more strategic interventions to boost to boost resilience and minimise environmental impacts of refugee communities e.g. microgrid renewable energy, water harvesting - Implementing a water provision intervention which could take the form of a desalination plant, a dam or a form of water harvesting. - Educate the locals and different decision-making bodies on value and scarcity of water and on making water-efficient project decisions |
| Environmental strategies / plans |  |  |
| Strategic Plan of the Ministry of Environment in Jordan (2017-2019) | 2017 | This document addresses the programs and plans of the Ministry of Environment in Jordan during 2017-2019 to ensure the continuation of the ministry’s pioneer and pivotal role successfully, in light of the challenges that are surrounding the region, and the accelerated changes in recent years. The project is well aligned with one of the objectives of the plan which is to prevent and reduce the negative impacts on the environment caused by pollution & climate change. |
| The Aligned National Action plan to Combat Desertification in Jordan 2015- 2020 | 2015 | The project will contribute to achieving the objectives of this action plan through mainstreaming climate change in planning in the target areas and so strengthening the enabling environment to adapt to drought in these areas. . |
| The National Biodiversity Strategy and Action Plan (NBSAP) in Jordan 2015 - 2020 | 2015 | The 2015-2020 NBSAP embraces a new vision for Jordan’s biodiversity as follows: The project is specifically aligned with the objective regarding ecosystem services and climate change: through enhancing the national understanding of dryland ecosystem benefits to national resilience, economic sustainability and local livelihoods. This is mainly through increasing resilience to climate-induced drought. |
| Sectoral strategies / plans, especially related to water |  |  |
| Jordan’s National Water Strategy (2016-2025) | 2016 | This document represents the vision and reference of the water sector in Jordan, which sets the goals and objectives for the water sector and also provides an initial response to Jordan’s commitment to the Global Sustainable Development Goals, ….highlighting the need for stronger intersectoral coordination and producing a National Water Master Plan, including Management Plans for managing water resources and water demand. The proposed project is generally well aligned with the adaptation to climate change measures. In addition, the project will contribute to reducing inefficient use of water as well as increasing water supply for irrigation. |
| Water Demand Management Policy 2016 | 2016 | This policy addresses the management of water demands in all sectors, including municipal, industry, tourism, agriculture and other activities of national importance and lists a wide range of capacity building, institutional, economic and technical measures for demand management. The project is aligned with the policy in terms of: - Maximizing the utilization of the available water and minimize water losses and conserve water resources, promote effective water use efficiency, to adapt with the challenge we face of water scarcity in order to reduce the gap between supply and demand. It supports the achievement - Updating codes and technical regulations periodically to ensure the installation of Rainwater harvesting systems in new construction (residential, commercial, industrial, tourism, etc.) where the size of the storage tank that depends on average rainfall and the surface area of the building is considered within the construction code. - Continue implementation the replacement of all inefficient plumbing fixtures, appliances and equipment with the latest most efficient models. Assist low income consumers to obtain water saving devices for free or stimulatory prices - The introduction of best technologies and modern and advanced irrigation systems in terms of the efficient water use in agriculture - Expansion in establishing water harvesting systems “dams, ponds, excavations" in all regions of the Kingdom especially in the highlands and desert areas that are suited for it, this water can be used in different purposes and agriculture in particular. Continue public awareness campaigns and water education through several means of communication and media focusing on water scarcity and spreading the culture of awareness and responsibility to protect the water sources and its efficient use |
| Surface Water Utilisation Policy | 2016 | This policy, published by MWI as an integral part of National Water Strategy, aims to present in more details what is envisioned towards the maximum utilization and optimum use of surface water, its protection, its management, and propose measures needed towards successfully integrating all its components. Also it addresses the interactions between the different resources and with different qualities, especially treated wastewater, to reach the maximum amounts of supply fit for use and the optimal return per meter cube; the proposed project is aligned with the Surface Water Utilisation Policy in terms of: - Maximizing the use of surface water to the greatest extent possible by increasing the storage capacity of dams, construction of new dams, and investment in rainwater harvesting in remote areas and from rooftops. - Constructing water harvesting schemes (ponds and desert dams) in the Highlands. Increasing Jordanians’ awareness of water scarcity and the importance of conserving and protecting Jordan’s limited water resources. - The quality of treated wastewater from all municipal and industrial wastewater treatment plants shall comply with Jordanian standards, monitored regularly, and reviewed periodically. |
| Jordan’s Decentralized Wastewater Management Policy (2016-2025) | 2016 | This Policy is an integral part of the Jordan’s National Water Strategy that was published by MWI. One of its key objectives is to seek measures to adapt to the increasing pressures from climate change on public sewer and wastewater treatment facilities. The project will follow the guidelines for wastewater reuse in all the interventions related to greywater and wastewater reuse. |
| Water Substitution and Reuse Policy (2016-2025) | 2016 | The Water Substitution and Reuse Policy, an integral part of the Jordan’s National Water Strategy published by MWI, aims at substituting freshwater with treated wastewater and possibly other non-conventional water sources, avoiding negative impacts on water and soil quality, and which also refers to the principles of IWRM. The project is well aligned with the main objectives of this policy which are: - To cope with the scarcity situation by enhancing the efficiency of the management of the scarce water resources in Jordan through maximizing the benefits and returns, and proposing actions required for implementation. - To Increase the amounts of treated Wastewater (WW) and considering it as a potential water and revenue source - To ensuring sustainability and preservation of water resources. |
| Water Sector Capital Investment Plan 2016 – 2025 | 2016 | This plan, which is an integral part of the Jordan’s National Water Strategy published by MWI, defines its main aim as the sustainable development and management of water resources. The proposed project is well aligned with the two key focus areas of the plan that are essential to respond to Jordan’s increased water scarcity; [1] The development of new water resources by implementing rainwater harvesting systems and encouraging reuse of treated wastewater and greywater [2] The expansion of wastewater treatment services. |
| Water Reallocation Policy (2016-2025) | 2016 | This policy, which is an integral part of the Jordan’s National Water Strategy published by MWI, prioritizes and re-allocates water from different sources (e.g. groundwater use considering safe yields) between the different sectors and governorates according to adaptive capacity, and at the same time at reducing non-revenue water. The proposed project is well aligned with the policy in term of: - Maintaining acceptable water quantities for different areas and excellent water quality - Frequency of water supply during summer and winter by implementing rainwater harvesting system - Collecting and treating wastewater for safe agricultural use. |
| National Strategy for Agricultural Development 2016-2025(In Arabic) | 2016 | The National Strategy for Agricultural Development 2016-2025 stated that among challenges facing the agricultural sector is desertification in Jordan, which is increasing due to climate change, overgrazing and poor agricultural practices. The project is aligned with the strategy in terms of increasing the efficiency of water use in irrigation and the use of non-traditional water resources such as greywater. |
| Land use plan 2007 | 2007 | Comprehensive plan designating the land use throughout the Kingdom. This Master Plan is distinctive in that it is a directive map illustrating the natural, geographic and demographic characteristics, including the sustainability of natural resources. The plan aims to: - Preserve agricultural lands, ensure its continuity, and its development. - Control the arbitrary urban sprawl - Limitation of urban development based on natural features and actual needs - Protect the environment from pollution. |
| Water for Life Jordan's Water Strategy 2008-2022 | 2008 | This document is Jordan's vision for a water strategy published by MWI prior to the National Water Strategy, where it emphasis on the fact that Jordan must manage its water resources giving priority to municipal and industrial needs and cap agricultural use. The proposed project is well aligned with the strategy in terms of; - Increasing awareness among the Jordanian public and decision makers to seek behavioral change and lay the foundation for policy change. - Policy and Regulation change and enforcement in the municipalities. |
| The National Strategy for Health Sector in Jordan 2016- 2020 | 2015 | This strategy represents the general framework for developing and strengthening the capacity of the health system to face the challenges and raise Jordan's leading position in the provision of health care. The threats include climate change impacts on health. In the context of this project, community consultations in most of the target areas have shown that there has been an increase in diseases due to climate change. |
| Jordan Response Plan for the Syria Crisis 2018-2020 JPR 2018-2020 Annex | 2017 | The project is well aligned with sector specific objectives under Environment and WASH Sectors as per the details below: - Environment sector: SSO1: Improved mechanisms to mitigate pressure and competition for ecosystem services (land, water) resulting from refugee influx - Wash sector: SSO1: Quantity, quality and efficiency of safe drinking water delivery improved and system optimized. SSO3: Strengthened sector planning, implementation, monitoring and coordination. SSO5: Sustainable provision of safe and equitable access to water services in host community as per min standards. |
| Sub-national plans |  |  |
| Irbid 2030: Greater Irbid Area Plan | 2010 | A growth plan that is designated to n provides an overall land use plan and associated policies that direct growth within an urban–rural development concept. The overall strategy of the Plan is to integrate land use, infrastructure and transportation planning. The components of the plan cover 7 subjects and recognize Infrastructure, where the consumption of water and energy and production of waste and heat are inextricably connected to urban infrastructure systems. The proposed AF project is well aligned with the infrastructure guidelines related to water and wastewater in terms of; - Increase wastewater treatment plant capacity to accommodate the expansion of the service area. - Encourage treated greywater to be used for irrigation purposes. |
| البرنامج التنموي لمحافظة إربد 2017 -2019 (Development Program for Irbid Governorate 2017-2019_Agriculture and Water Sectors) | 2017 | The project is aligned with a number of proposed interventions by the municipality and the community including rainwater harvesting and rehabilitating water networks. - Upscaling wastewater services through rehabilitation of the existing ponds and upgrading the capacity of WWTPs - Encourage the usage of treated grey water for irrigation purposes. |
| البرنامج التنموي لمحافظة المفرق 2017 -2019 (Development Program for Mafraq Governorate 2017-2019_Agriculture and Water Sectors) | 2017 | The project is aligned with some of the proposed interventions in the agriculture sector including rehabilitation of water harvesting ponds. - Improving the efficiency of residential, manufacturing, commercial and agricultural water supply systems through rainwater harvesting and rehabilitating water networks. - Upscaling wastewater services through rehabilitation of the existing ponds and upgrading the capacity of WWTPs. - Legislation development |

Table 10: Lebanon project alignment with National and sub-national priorities

| Policy / Document | Year submitted / ratified | Relevant priorities |
| --- | --- | --- |
| Lebanon |  |  |
| Climate Change strategies / plans |  |  |
| Lebanon’s Intended Nationally Determined Contribution | 2015 | This project aligns with the water related climate change adaption priorities listed in the INDC: - Rehabilitation of existing water networks - Artificial recharge of groundwater aquifers - Improving water efficiency and decrease water loss in irrigation - Increasing wastewater collection and treatment - Increasing water re-use, especially after wastewater treatment |
| Lebanon’s third national communication to the UNFCCC | 2016 | The project is well aligned with some adaptation measures for the water sector listed in the report: - Increasing the water-use efficiency of domestic, industrial, and agricultural sectors, - Developing watershed-managed plans appropriate for expected changes in climate, investigating the feasibility of alternative sources of water supply, and improving the available information about Lebanon’s water resources and water systems The report prioritized the installation of rainwater harvesting systems in agricultural greenhouses around different locations in Lebanon |
| Lebanon’s Technology Needs Assessment project | 2012 | The Report outlines all the adaptation technology options available for the water sector in Lebanon and used a criteria-based weighting system to prioritize the most cost-effective, sustainable and socially acceptable options. It also highlighted the main barriers to adopting each of these technologies that should be addressed. The report lists a number of water related solutions that the project aligns with. These include: - Rainwater harvesting from greenhouses, hill lakes and rivers. - Efficient water use irrigation systems - Use of treated wastewater in irrigation |
| National Development strategies / plans |  |  |
| National Physical Master Plan of the Lebanese Territory (NPMPLT) | 2005 | The NPMPLT was endorsed by a decree issues by the Council of Ministers in July 2009. It is a strategic reference document that overrides all documents concerning regional and local urban development and planning. It is not only the framework for urban planning policy, but also serve as a guideline for all stakeholders participating in the national and land use development. The NPMPLT tackles water resources management through land use plans and measures consisting of the following: - Launching legislative and legal reforms that define the principles of land use - Elaboration of several local urban plans with precedence to the zones threatened by urban linear expansion and agricultural lands jeopardized by urban structures. The report defines different challenges that Lebanon is facing today and might face in the future. One of those important challenges is wastewater management. |
| Disaster Risk Reduction strategies / plans |  |  |
| UNDP –DRM Unit LEBANON Monitoring of Sendai Framework 2017 | 2017 | The report outlines national updates on strengthening disaster risk management capacities in Lebanon. Target G5 of this report highlights the importance of disaster risk information through a national flood risk map. The project is in line with this target as it also aims to control floods in target areas. |
| Environmental strategies / plans |  |  |
| Support to Reforms – Environmental Governance (StREG) Programme | 2017 | Main aims: - increasing the effective capacity at the MoE to plan and execute environmental policy - enforce environmental law - mainstream environmental issues in key line ministries |
| The Practical Guide for Municipalities to Enhance Environmental Management (2017 | 2017 | This report supports this project by presenting the problems that the municipalities face in the water sector, and the measures and actions that they can take to solve these challenges. It highlights all the laws and regulations related to water resources management as well as the roles of all stakeholders involved in that sector. |
| State and Trends of the Lebanese Environment | 2010 | This report provides an overview of the current condition of natural resources and environmental management in Lebanon. It gives an analysis of past and future developments across multiple sectors. It describes the impacts of rapid population growth, urbanization and climate change on water resources, then outlines the opportunities for improving the water sector. The project is in line with the selected responses presented in this report. Wastewater collection, treatment and reuse is one of the main opportunities presented in this report. Also, rainwater harvesting is outlines as another water resource augmentation option. |
| Sectoral strategies / plans, especially related to water |  |  |
| National Water Sector Strategy (NWSS) 2010-2020 |  | Environmental concerns: Climate change negatively impacting water resources The strategy is in line with the project since it aims at: - Collection and treatment of at least preliminary level of 80% of wastewater by 2015, and of 95% by 2020. Secondary treatment and reuse for all inland and for coastal systems where reuse is applicable by 2020. Irrigation and sanitation services through 16 initiatives involving institutional & organizational reforms and financial, commercial and environment initiatives, refining climate change knowledge on the water sector and preparing the sector for private sector participation. |
| Strategy for the Wastewater Sector (MoE) | 2010 | Presents a strategic roadmap to improving water sector infrastructure and management. |
| National Physical Master Plan of the Lebanese Territory | 2005 | It’s the only national master plan that was drafted. It is not yet approved and implemented. The plan has predicted that there will be an increase in demand for water following population growth and increase of agricultural and industrial use of water. |
| Health Strategic Plan | 2016-2020 | Second Strategic goal set out by this plan is to improve collective public health through water and environmental controls. |
| Lebanese Crisis Response Plan (LCRP) | 2017-2020 | The LCRP is designed to: 1) Ensure humanitarian assistance and protection for the most vulnerable among persons displaced from Syria and poorest Lebanese; 2) Strengthen the capacity of national and local service delivery systems to expand access to and quality of basic public services; and 3) Reinforce Lebanon’s economic, social, environmental, and institutional stability. |
| Sub-national plans |  |  |
| Water Sector Lebanon - Bekaa governorate water supply (Map) | 2017 | Map showing existing water networks, wells and reservoirs in Bekaa governorate. It also highlights projects implemented or under construction. |
| Litani river basin management support program action plan for water resources awareness and enforcement (USAID) | 2009-2014 | Proposes an action plan aimed at improving the management of the Litani river through awareness projects that target schools, farmers and municipalities. |
| Water Sector Lebanon - Bekaa and Baalback El Hermel wastewater network (Map) | 2015 | Map showing existing wastewater networks and wastewater treatment plants in Bekaa and Baalbeck El-Hermel. It also highlights the most vulnerable localities in the two governorates. |
| Water Supply and Wastewater Systems master plan for the Bekaa Water Establishment | 2015-2035 | Report presents work related to the development of the Master Plan and the adoption of recommendations for the year 2035 for proposed action plans for water and wastewater sector in Lebanon. |

- Compliance with relevant national technical standards

The project fully aligns with national technical rules, regulations and standards, including those for environmental and social risks screening and impacts assessments, building codes, land use planning, water supply / harvesting / reuse, etc. As required by national law, an environmental and social impacts assessment is being finalised for the proposed wetlands in Lebanon. Although other proposed interventions don’t require risks screening and impact assessment by national laws, accredited consultant have been hired in both countries to do this anyways to comply to AF ESP and GP requirements. Outputs include feasibility assessment report, EIAs report, National ESMP and consultation report. For more information see annex 4.

Jordan

Process to comply to national technical standards: compliance will be attained by:

- Abiding with provisions of the governing Jordanian legal document (laws, by-laws, standards, codes, etc.) through conforming to the relevant rule(s);

- In cases a permit is required from the authorizing entity to fulfil certain regulatory requirements, in which obtaining the permit entails following no standardized procedure, the project initiator will prepare an official letter addressed to the authorizing Ministry to obtain the approval. This is usually requested at preliminary phases of the projects. During the full proposal development phase, sub-projects proposals will be shared with the ministries to check if permits are needed.

- If the permit is only issued based on a standardized procedure and a risk management tool is needed, the specific procedure will be followed based on the governing Jordanian Environmental Protection Law No. (6) of 2017 and Environment Impact Assessment Regulations of 2005, by-law or Instructions (i.e. ESIA permit based on Ministry of Environment-administrated ESIA Bylaw no. 37 of the Year 2005 will be obtained including developing an ESMP for activities that are required to develop an EIA, etc.). In all cases sub-project proposals need to be submitted to the Ministry of Environment to decide on the type of EIA required based on the EIA compliance process shown in the figure. This will be done during the full proposal development phase. A first screening shows that no EIA may be required as there is no mentioning of EIA requirements for water-project, except ‘deep drilling and because no sub-project in the proposal entails substantial construction activities. For agriculture project, EIA are only required for cattle breeding farms.

Figure 9: EIA compliance process

Table 11: Compliance with relevant national technical standards

| Expected concrete output/intervention | Relevant rules, regulations and standards (to comply to AF principle 1) | Compliance procedure and authorizing offices |
| --- | --- | --- |
| Output 1.3. Urban master plans at municipal level with CC and gender mainstreamed in Jordan | - Cities, Villages and Buildings Planning Law and Amendments thereof No (79) for the year 1966 - Building, Villages and Cities Regulating by-law and amendments thereof for the year 2016 - Land Use Planning By-Law No. 6 of 2007 - Environmental Protection Law No. (6) of 2017 | See compliance procedure above Required: coordination and approval from Municipalities of Irbid and Mafraq and Ministry of Municipal Affairs-MoMA for Land use-related affairs and strategies |
| Output 2.1. Community organisation, awareness and capacity / skill building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.1 2.2. See above for output 3.2. 2.3. See above for output 3.3. 2.4. See above for output 3.4. 2.5. See above for output 3.5. 2.6. See above for output 3.6. 2.7. See above for output 3.7. 2.8. See above for output 3.8 | - Not relevant | Operation, maintenance and replication will be coordinated with responsible ministries, municipalities and other entities |
| Output 3.2. Rooftop rainwater harvesting in Jordan 3.3. Greywater treatment and reuse in Jordan 3.5. Efficient treatment and reuse of wastewater in Jordan 3.7. Water-use Efficient irrigation of treated wastewater in Jordan 3.8. Permaculture demonstration - closed loop water system in Jordan | - Environmental Protection Law No. (6) of 2017 - EIA Rules, regulations, standards (EIA By-law no. 37 of the Year 2005) (see above) - The Jordanian Standard for Reclaimed Domestic Water – JS No. 893/2006 - JS:286/2015: Water – Drinking Water, mandatory regulations - Water and sanitary wastewater building code, Jordan National Building Council - Jordanian National Building Law No. 7 of 1993 and recent Amendment Law No. 24 of 2018 - The By-Law of Buildings and Organization of Cities and Villages and its Amendments No. 2 0f 2018 - Jordan Green Building Guide - Instructions No. G/7 for the Year 2016: Instructions and Conditions to Use Treated Wastewater, Salty Water, and Brackish Water for Agricultural Use - Law No. 13 of 2015 concerning Agriculture Law.) - Bylaw No. (133) of 2016 Organic Agriculture bylaw Issued pursuant to Articles (7) and (71) of Agriculture Law no. (13) of 2015) | See compliance procedure above EIA rules, regulations, standards and procedures have been followed and EIA, ESMP and consultations reports have been produced and are being approved by the Ministry of Environment (although no EIAs were required by national law (see annex 4) See compliance procedure above Required: coordination with and approval from target municipalities and ministry of water and irrigation for 1) construction harvesting and grey water systems; 2) water quality compliance for toilets and gardening) See compliance procedure above Required: coordination with and approval from ministry of water and irrigation and ministry of environment See compliance procedure above Required: coordination with and approval from ministry of water and irrigation, ministry of agriculture and ministry of environment |
| Output 4.2. Jordan and Lebanon KM with focus on project progress, best practices and lessons learned 4.4. Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities | - Not relevant | - Not relevant |

Lebanon

The institutional framework for the water sector in Lebanon is managed by a number of ministries, water establishments, public agencies, municipalities, etc., as per below.

Table 12: Key players and responsibilities in the water and wastewater sectors

Source: State and Trends of the Lebanese Environment, 2010

Figure 10: Legal environmental requirement for any project activity in Lebanon

Table 13: Compliance with relevant notional technical standards

| Expected concrete output/intervention | Relevant rules, regulations and standards (to comply to AF principle 1) | Compliance procedure and authorizing offices |
| --- | --- | --- |
| Output 1.1. Territorial planning and development strategy / guidelines with CC and gender mainstreamed in Lebanon 1.2. Urban master plans at municipal level with CC and gender mainstreamed in Lebanon | - The Urban Planning decree-law of 1983: - Article 4 to 17: plans, regulations and relevant planning conditions and possibilities. - Article 18 to 24: operational arrangements that governments can use when undertaking a development project. - Article 25 to 44: building permits and land subdivision. - Municipal Law decree 118/77: - Article 11: masterplans and regulations should be submitted to the relevant municipalities. - Article 49: an urban plan should be approved jointly by the Directorate General of Urbanism (DGU) and the concerned municipality. - Environment Code, Law 444/2002. | See compliance procedure above Required: coordination and approval from target Municipalities and Ministry of Interior and Municipalities; Ministry of Environment; Directorate General of Urbanism (DGU); |
| Output 2.1. Community organisation, awareness and capacity / skill building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.1 2.2. See above for output 3.2. 2.3. See above for output 3.3. 2.4. See above for output 3.4. 2.5. See above for output 3.5. 2.6. See above for output 3.6. 2.7. See above for output 3.7. 2.8. See above for output 3.8 | - Not relevant | Operation, maintenance and replication will be coordinated with responsible ministries, municipalities and other entities |
| Output 3.1. Rooftop rainwater harvesting in Lebanon 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon irrigation of treated wastewater in Lebanon 3.6. Water-use-efficient irrigation of treated wastewater in Lebanon | - decree 8633 MoE, 2012, Annex 1 - Law 221/2000 (amendment 241/2000) and law 77/2018: Water Code - Water Code–Law 77 - Water and Wastewater masterplan for the Bekaa Governorate 2015 - National guidelines for rainwater harvesting systems prepared by MoEW based on potable water standards. - Law 221/2000 (amendment 241/2000) and law 77/2018: Water Code - Water Code–Law 77 - Water and Wastewater masterplan for the Bekaa Governorate 2015 - No guidelines for drip irrigation installation exist. Experimental stations at LARI have relevant experience for testing new crop varieties. No national standards for irrigation water quality. FAO standards will be adopted. | See compliance procedure above. According to Decree No. 8633,2012 of MoE, the following steps were taken: -A screening form for the project and sub-project was submitted -MoE decision was that the proposed wetlands project requires an EIA -A public consultation was held on December 18th 2019 -A scoping report was submitted to MoE on December 30th 2019 -The EIA report is the final step of the EIA process. It was submitted on January 13th following the reply of MoE on scoping report. See compliance procedure above; Design of rainwater harvesting system follows the guidelines. Consultation with MoEW. No Required: coordination with and approval from target municipalities and Ministry of Energy and Water for 1) construction harvesting and grey water systems; 2) water quality compliance for toilets and gardening) See compliance procedure above Required: coordination with and approval from Ministry of Environment; Ministry of Energy and Water; Bekaa Regional Water Establishment; Lithani River Authority; target Municipalities; Ministry of Agriculture; |
| Output 4.2. Jordan and Lebanon KM with focus on project progress, best practices and lessons learned 4.3. Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities | - Not relevant | - Not relevant |

- Duplication with other funding sources

The project will avoid geographical overlap with other projects and complement existing project and use lessons learned where possible. During the project preparation phase, all projects in the target areas and have been mapped to avoid geographical overlap. Besides that, similar project in Jordan and Lebanon and in the region have been identified with the purpose to extract lessons learned and integrate those in the project. An overview of all these projects, has been included in a table 14 below. This has been done through desk research, consultations (see Part II.I) but also by requested inputs from ministries and execution entities, which lead similar project before. With e.g. UNICEF as executing partner, a wealth of  knowledge and experience is available regarding WASH in the region. The same accounts for Johud and rainwater harvesting, the Water Authority of Jordan if it comes to wastewater treatment in Jordan. The Permaculture Research Institute is worldwide know institute if it comes to permaculture. UN-habitat will also work with universities and consultancy firms to further develop business cases and incentive mechanism for water harvesting options (output 4.4) and Permaculture (output 3.8). UN-habitat will continue to coordinate with all relevant stakeholders during project implementation to ensure synergies with other (potential) project, also through steering committee meetings.

Table 14: Duplication with other funding sources

| Relevant projects and focus | Relevant focus and interventions / activities | Lessons learned | Complimentary potential and non-duplication (see also consultation section) |
| --- | --- | --- | --- |
| Global |  |  |  |
| ‘Urban permaculture’ by UN-HABITAT's Cities and Climate Change Initiative in in Esmeraldas, Ecuador | - Promoting resilient communities in the face of highly probable future food and energy crises and the collapse of water and sanitation services due to Climate Change - The project tries to mimic Nature and its ecological cycle with the following components: urban agriculture and healthy food, rainwater harvesting, water recycling, solid waste recycling, and dry toilets. | - Greening of urban habitats and environments while harvesting water and producing food have been demonstrated; - Permaculture can be used as a climate change adaptation measures in an urban context | Complementary - Use lessons learned and further develop the concept in urban context for target area (through desk research) Non-Duplication - In Ecuador |
| MENA region |  |  |  |
| UN-Habitat – with AF funding – Enhance water and livelihood security and social cohesion through adaptation in Syria’s Barada watershed (concept to be submitted) – USD 10 million | - The protection of water resources (and prevent contamination of surface and groundwater resources / wells) - The reduction of water losses; - The increase of water use efficiency, supporting water harvesting projects and using high efficiency irrigation methods; - The promotion of use of non-conventional water resources (e.g. treated wastewater) and: - Improved agricultural production practices (e.g. drought tolerant crops). | - Project proposal under development. | Complementary - Align approach and lessons learned throughout project preparation and implementation (by ROAS) Non-Duplication - In Syria |
| IFAD with AF funding - Building Resilience of the Agriculture Sector to Climate Change in Iraq (2018-2023) – USD 10 million | - Capacity development to integrate CC adaptation and risk reduction into agriculture planning and production systems - Climate-resilient Agriculture Investments | - Has not started yet - Monitor lessons during project formulation phase | Complementary - Consider similar approach to capacity building and efficient water supply from tertiary canals up to farmland plots is secured based on climate- proof systems and technologies. ROAS to contact IFAD Non-Duplication - In Iraq |
| FAO Water Scarcity Regional Initiative (WSI) Pursuing food and water securities in MENA region | - Establishing community-farm demonstration fields to show the benefits of new irrigation technology - Implementing a plan to envision future climate change scenarios for ‘hotspots’ at the regional level | - Monitor results (which are not publically available yet) | Complementary - Potentially complement results related to new technology. ROAS to contact FAO Non-Duplication - Regional, including Jordan and Lebanon. No overlap with target areas |
| FAO Dutch-funded Sanaa Basin Project in Jemen (2014-2017) Water sustainability for farmers while empowering women | - Construction of wells through a cash-for-work formula for farmers to use for agricultural production. - All Water User Associations choose their board members through elections and 30 percent of the seats are designated for women. | - Water association and women only access to water can be used as a water management system to reduce conflict between tribes | Complementary - Consider building upon lessons from Water association and women only access to water approach and cash-for-work formula for farmers to use for agricultural production. ROAS to contact FAO Non-Duplication - In Yemen |
| Jordan |  |  |  |
| Jordan government with AF funding - Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through Implementing Innovative projects in water and agriculture in support of adaptation to climate change (2015-2018) – USD 9,2 million | - Waste water treatment plant + monitoring quality - Irrigation study - Rain/flood water harvesting dam / basin (400.000 m3) with solar panels to reduce evaporation - Permaculture – adaptation + ecosystem management in demonstration sites | - According to manager Permaculture has promising results for adaptation, reducing pollution and protecting ecosystem - Water user associations / cooperation can be used to reach farmers and administer water | Complementary - Use permaculture concept in real farms and in urban context - Use similar approach for water harvesting basins at farms and in urban areas - Water user associations / cooperation can be used UN-Habitat is already in touch with manager and specialists (see also II.I) Non-Duplication - In Jordan Valley |
| UNICEF WASH programme | Supports the Ministry of Water and Irrigation and partners in the Water Sanitation and Hygiene (WASH) sector at three different levels - Leading the emergency WASH sector coordination - Ensuring access to safe water and sanitation facilities and services in refugee camps and in host communities, and - strengthening the Government’s capacity to prioritize, plan, implement and monitor. | - In host communities, leakage along the water network results in huge losses (up to 60 per cent in some areas) and inefficient operation modalities. | Complementary - UNICEF has been consulted to better understand their approach and local needs - Compliment UNICEF work (emergency / humanitarian) by supporting sustainable and climate change resilient interventions - UNICEF will be executing partner Non-Duplication - Through coordination with UNICEF, overlap is avoided; UNICEF mainly focused on piped water |
| UNICEF - Water Conservation in schools Grey Water Reuse and storm water drainage system | In 2018, a proposal was made to UNICEF to pilot grey water reuse system in four schools to introduce water conservation and reuse in Zaatari refugee camp. The main activities of the project: - Reuse the grey water produced by the school for irrigation for no edible groups and flushing purposes - Reduce the public health risk and impact on local ground water aquifers from the discharge of untreated grey water. - Provide alternative solution for reducing the cost of desludging and network operation in Zaatari camp. - Minimize the operation and maintenance costs. - Raise the awareness among the students on the proper use of water reuse | - Water sampling and testing to ensure system efficiency. | Complementary - UNICEF has been consulted to better understand their approach. - UNICEF will be executing partner Non-Duplication - In Zaatari Camp |
| USAID Hydroponic Green farming Initiative (2015-2017) | The USAID Hydroponic Green Farming Initiative aims to introduce a model that integrates hydroponic farming and renewable energy generation for large commercial farms and small rural households. The greater focus will be on; - Promoting hydroponic technology in established farmer networks and targeted communities. - Demonstrating the feasibility of hydroponics. - Bridging the gap between traditional agricultural knowledge and hydroponic systems through educational material and training exercises. - Ensuring prospective farmers have the technical knowledge and funding to access hydroponic technology. - Focusing on vulnerable demographics – such as women and youth – when designing outreach and dissemination activities. | - Hydroponic can be scaled up as a climate change adaptation measures in Jordan - Improve water efficiency in agriculture through hydroponic systems that use significantly less water than traditional farming practices. | Complementary - Potentially complement results related to new technology and water efficiency - Use hydroponic concept in farms Will be further consulted Non-Duplication - In Jordan Valley and highlands. No overlap with target areas |
| USAID - Community Water Harvesting Systems (in Mafraq and Karak) | The project highlights: - The application of simple, low cost, and scientifically based water harvesting systems in 4 sites in Mafraq and 2 in Karak. - The utilization of harvested water for agricultural production. | - Make sure of the availability of active community organizations with resources available for the project such as land and farms | Complementary: - Use the mentioned Guideline for selecting and sizing water harvesting system Non-Duplication - In Mafraq and Karak, however no overlapping with the selected targeted schools in Mafraq. |
| USAID Mercy Corps - Community-Based Initiatives for Water Demand Management I (CBIWDM I) and II (CBIWDM II) | The goal of the initiative is to reduce the social and economic impacts of water resource limitations, as well as responding to the destabilizing effects in Jordan on the water and sanitation sectors caused by the influx of Syrian refugees. The main activities/interventions, to enable rural Jordanian communities to reduce water demand through improved resource management, are as follow: - CBO Capacity Building Program - Construct rainwater harvesting reservoirs with water catchment systems responds to the immediate need of water and provided a convenient resource - Awareness Campaigns at Schools that complement the construction work of rainwater harvesting cisterns implemented at the schools. One of these campaigns is “For all of us” Campaign (إلنا كلنا) - The initiative provide network support to the Yarmouk Water Company through the provision of emergency equipment, infrastructure works for improved water supply, and outreach and customer service support to YWC. - Promote equal access to resources through the empowerment of different water users requires that there is at least one woman on the management committees for each CBO | - Conducting leak detection and repairs for municipal water systems to increase water delivery/availability. | Non-Duplication - In all 12 governorates, however ,no overlapping with the selected targeted area. |
| JOHUD - The Arteries of The Nation: Repairing Jordan’s Water Networks (WRAP) Project | The project was initially developed in 2015 to preserve Jordan’s slim water resources, and to provide adequate water resources to the populations. It focused on; - Revitalise the springs that provided the local farms with water for crop irrigation in collaboration with Madaba Water Authority - Improve quality and quantity of the drinking water - helping to improve the health and wellbeing of around 20,000 local residents - Repair canals and providing more reliable sources of irrigation water - Reduce local household electricity bills, because they no longer using electric pumps to fill the rooftop water tanks. | - Water Authority managers were able to determine and measure the real needs and demands in the community. | Complementary - Help the targeted areas to retain its agricultural character - JOHUD will be one of the executing bodies - Potential similar results regarding the rehabilitation and upgrading the WWTPs. Non-Duplication - Ma’een District, in Madaba Governorate |
| The Hashemite Fund for Development of Jodan Badia - Treated Waste Water Reuse Project – Wadi Mousa | The first community-based project was established in collaboration with the USAID. The local community was provided with technical support to use treated and reclaimed wastewater for irrigating their fodder crops. - Improve the livelihoods of local community members in the target area. - Reduce the competition on and demand for fresh water resources. - Conserve natural resources and better manage the environment through the reuse of reclaimed water. - Develop drip irrigation systems for an area of 100 hectares. |  | Complementary - source of income for the local community members - Badia Fund will be one of the executing bodies Non-Duplication - Wadi Mousa, Jordan |
| GIZ – improvement of community water efficiency through cooperation with religious authorities | - Religion-based teaching materials are developed for schools and universities and then included in religious education to raise awareness of the issue of water scarcity. - Equipping selected mosques in northern and central Jordan with rainwater collection and grey water recycling systems. | - It is important to raise awareness of religious leaders and education experts on the issue of water scarcity at mosques and schools to serve as serve as water ambassadors. | Complementary - Potentially complement efforts related to water efficiency and harvesting in Mosques and Schools. UN-Habitat is already in touch (see II.I) Non-Duplication - Northern governorates. Through coordination with GIZ, Ministry of water and irrigation, Ministry of Awqaf, overlap is avoided. |
| FAO Project- Reduce Vulnerability in Jordan in the Context of Water Scarcity and Increasing Food/Energy Demand | - The project pilots a three-pronged, community-based approach, combining water harvesting, conjunctive use of groundwater, and solar power for lifting irrigation water. - Downstream water harvesting in Al-Ghadeer Al-Abyad watershed site - Rehabilitation of Al Ghadeer Dam - Installing PV system to pump water from the dam to nearby agricultural lands. - Assessment of the water harvesting sector in Jordan which will serve as an important input into the development of a sub-sector strategy for water harvesting. | - Focus on the creation of a comprehensive policy framework for water harvesting to promote the more efficient use of water resources as well as to better integrate agricultural production policies with the water harvesting efforts. | Complementary - Potentially complement efforts related to upstream water harvesting. UN-Habitat is already in touch (see II.I) and intervnetions will be well coordinated Non-Duplication - Al Mafraq Governorate, around Al Mafraq WWTP. Through coordination with FAO, overlap is avoided. |
| Permaculture Gardens for schools project Al Jawaseri School Garden project | Al Jawaseri is a permaculture school garden in a hyper arid landscape in the Dead Sea Valley of Jordan. A Collaboration between the Permaculture Research Institute of Australia and Kids Are Sweet. The project enables children in a small village with severe water shortages to learn how to build soil, maximise water retention, and create garden abundance. They focused on; - Design a hyper-arid garden - Local women empowerment, where the implementation of the project was directed by local women residents - Establishment of self-replicating educational demonstration sites across the globe | - Use sunken beds lined with builders plastic to retain all the water from drip irrigation. - Very successful project to promote permaculture everywhere. | Complementary - Potentially upscaling this project into some vocational schools in the targeted areas Non-Duplication - In Dead Sea Valley, Jordan |
| Lebanon |  |  |  |
| UNHCR Water, sanitation and hygiene programme | - UNHCR’s strategy on water, sanitation and hygiene (WASH) is aimed at helping both refugees and the Lebanese communities hosting them. It targets the needs of refugees in informal settlements, as well as refugees living in Lebanese communities, through the implementation of water and waste water projects that strengthen and/or rehabilitate existing infrastructure. - Rehabilitation of storm water channels to the construction of reservoirs, and even the drilling and equipping of boreholes. - Nine water supply systems in the Bekaa and North Lebanon are being rehabilitated | - Crucial to support both DPs and host communities. | Complementary - UNHCR has been consulted to better understand their approach and local needs - Use lessons learned for supporting both DPs and host communities, while adding the climate change component UN-Habitat is already in touch (see II.I) Non-Duplication - Through coordination with UNHCR, overlap is avoided |
| UNICEF WASH programme 2013-2016 | Three components: - Strengthen the capacities and information systems of authorities in Lebanon; - Improve access to WASH services for Syrian refugees in ISs (WASH in Emergencies); - Improve WASH infrastructure to ensure better service delivery to host communities (WASH in urban areas/stabilization interventions). | - Interventions should support national water plan / targets - Different targeting strategies required (difference between urban and camp-based refugees) - Requires flexibility | Complementary - UNICEF has been consulted to better understand their approach and local needs - Compliment UNICEF work (emergency / humanitarian) by supporting sustainable and climate change resilient interventions - UNICEF will be executing partner Non-Duplication - Through coordination with UNICEF, overlap is avoided; mostly piped water |
| #### UNDP Support to Host Communities in North Lebanon in the WASH Sector (2014-2017) – USD 8,8 million | - Identification, implementation of water supply / storage works and commissioning and handover of works to North Lebanon Water Establishment | - Lengthy process for licensing for works | Complementary - Complement UNDPs work in target area while also supporting host communities UN-Habitat is already in touch (see II.I) Non-Duplication - North of Lebanon |
| #### Lebanon Recovery Fund (MOE & UNDP) | - Systems for rainwater harvesting from the top of greenhouses has been installed in three sites Choueifat, Kfarmashoun and Damour in Mount Lebanon. - Collecting rainwater from the top of the greenhouses, storing it in big tanks to be used for irrigation during the dry months. | - Farmers are saving all the money they used to spend on purchasing water for irrigation and on pumping. - The groundwater quality will be protected from pollution and salinization, since pumping rate and depth will both decrease. - Water quantity will be preserved as natural recharge - CO2 emissions from energy consumed for pumping water will decrease. | Complementary - Benefit from UNDP’s guidelines destined for all Lebanese farmers to replicate these pilot rainwater harvesting initiatives. UN-Habitat is already in touch (see II.I) Non-Duplication - Mount Lebanon |
| IFAD with AF funding Climate Smart Agriculture: Enhancing Adaptive Capacity of the Rural Communities in Lebanon (2013-2017) – USD 8 million | - Water Management: Rainwater harvested from greenhouse roof tops - Water Management: Water efficient irrigation systems deployed - Adaptation Techniques Roll-out: Capacity building on adaptation techniques for vulnerable field crops enhanced and Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed | - Get guidelines | Complementary - Consider similar approach to water harvesting and irrigation systems Will be further consulted Non-Duplication - Target is Rural communities |
| World Bank - Greater Beirut Water Supply Project (2010 – 2020) – USD 370 million | - Bulk Water Supply Infrastructure - Supply Reservoirs, Distribution Network and Metering - Project Management, Utility Strengthening and National Studies - Land Acquisition and Resettlement Compensation |  | Complementary - Increase the provision of potable water to the residents in the project area within the Greater Beirut region - Strengthen the capacity of the Beirut Mount Lebanon Water Establishment in utility operations UN-Habitat is already in touch (see II.I) Non-Duplication - Greater Beirut Area |
| World Bank – Water Supply Augmentation Project (2014 – 2024) – USD 617 million | - Construction and construction supervision of the Bisri Dam and the associated access road. - Construction and construction supervision of the conveyor pipelines to the existing Joun reservoir and the associated access road - Two (2) hydropower plants - Expansion of the Ouardaniyeh water treatment plant (WTP) - Technical assistance to the Ministry of Energy and Water (MOEW), Beirut Mount Lebanon Water Establishment (BMLWE) and Council for Development and Reconstruction (CDR) on the operation and maintenance of dams; on management of water resources; in developing and implementing awareness raising campaigns on the economic benefits of switching to the public water network and eventual volumetric metering water supply | - People will access to clean and improved water supply service without spending additional expenses on alternative water sources. | Complementary - Increase the volume of water available to the Greater Beirut and Mount Lebanon area - Capacity building to the Ministry of Energy and Water (MOEW) UN-Habitat is already in touch (see II.I) Non-Duplication - Greater Beirut and Mount Lebanon Area |
| World Vision (applied projects based on Bekaa water and wastewater masterplans) | - Taalabaya Water Network Replacement and Expansion project - Rehabilitation of Waste Water Treatment Plant in Ablah - Project for Waste Water Treatment for Bar Elias and Dakweh in Bekaa Area | - Limit water trucking and informal water services - Enhance water supply for vulnerable communities. | Complementary - Support to Enhance Basic Infrastructure and Economic Recovery in Lebanon - The use of treated wastewater for irrigation. - Benefit from network expansion. UN-Habitat is already in touch (see II.I) Non-Duplication - Follows the masterplan which is coordinated by the Bekaa Water Establishment. |
| CDR, national government with grant from Kuwait - Rehabilitation of water systems in West Bekaa and villages in East Zahle district - US$ 32.9 million (CDR report) | - Drilling of two wells and equipping of the seven wells, building pumping stations in Shamseen, installation of pumping lines from these two stations to two central reservoirs on Mount Anjar and Mount Terbol; - Construction of the two mentioned reservoirs in addition to a reservoir in Majdel Anjar and another in Sultan Yacoub al-Tahta and - Construction of two local reservoirs in Jeb Jenin and Kamed el Laouz, installation of transmission line from these central reservoirs to local reservoirs in West Bekaa and East of Zahle villages, construction of transmission lines from the central reservoir in Baaloul to Jeb Jenin and Kamed el Laouz reservoirs and the distribution networks in both towns | No started yet | Complementary - CDR has been consulted to better understand their approach and local needs - Compliment CDR work (conventional water supply) by supporting sustainable and climate change resilient interventions UN-Habitat is already in touch (see II.I) Non-Duplication - Through coordination with CDR, overlap is avoided |
| CDR, national government - Rehabilitation and improvement of potable water systems in Zahle and surroundings (CDR report) | Three tier project: - Part 1: potable water networks in Haoush el Omara and Ksara (under USAID, US$ 5 million) - Part 2: potable water networks in the city of Zahle which are fed from the potable water treatment plant; the cost of (Ministry of Energy and Water US$ 5 million) - Part 3: potable water systems in East Zahle, Dhour Zahle, Touaite, Mouaalaka, Karak, Madina Sinaiiya, Qaa El Reem and Hezerta (US$ 16 million and is funded by the Kuwait Fund for Arab Economic Development, the budget of the Ministry of Energy and Water, the Lebanese Government and managed by the CDR.) | - No started yet | Complementary - CDR has been consulted to better understand their approach and local needs - Compliment CDR work (conventional water supply) by supporting sustainable and climate change resilient interventions UN-Habitat is already in touch (see II.I) Non-Duplication - Through coordination with CDR, overlap is avoided |
| The International Bank for Reconstruction and Development (IBRD): Lake Qaraoun Pollution Prevention Project (2016-2023) | - Objective: reduction of sewage discharge into the Litani River and to enhance pollution management around Qaraoun Lake. - Project components: - Improvement of municipal sewage collection (IBRD -US$50.5 million, GoL-US$5 milion) - Promotion of Good Agricultural Practices (including Integrated Pest Management) (IBRD-US$1.5 million) Solid Waste, Water Quality Monitoring, Capacity Building, and Project Management (IBRD-US$3 million) |  | Complementary - This project takes care of waste management around the Litani river, thus waste management approach in proposed project is limited Non-Duplication - Focused on waste management |
| AgriCAL- Climate Smart Agriculture: Enhancing Adaptative Capacity of the Rural Communities in Lebanon (2012-2017) | Goal of the project: increase community resilience and adaptive capacity to climate change in Lebanon Objective: implement climate change adaptation measures in the agriculture sector in three highly vulnerable focus areas: The four outcomes of the project are: - Increased water availability and efficient use through water harvesting and irrigation technologies - Increased adaptation to climate change for crop production - Increased resilience of shepherds and small ruminants to climate change through sustainable rangeland management - Climate index insurance initiated, policy influenced, and lessons learned and shared through a knowledge management system | - Risk-coping agriculture techniques - Initiating a pilot climate insurance index | Complementary - Assist communities in adapting by improving water harvesting and irrigation technologies - Introducing adapted crop varieties to future climate condition - Spreading awareness of expertise and skills Will be further consulted Non-Duplication - Increase community resilience and adaptive capacity to climate change |
| UPLoAD, APIEU and Bekaa Water Establishment - Integrated approach for dealing with the water/urbanization problématique through the case of the city of Zahle and the Bedawni river watershed. | The idea is that in Lebanon there is little articulation - institutionally and scientifically - between urbanization management concerns (mainly defined in terms of urban development and land use management and led by local authorities) and water management concerns (mainly defined in terms of engineering adequacy of water resources and water demands and led by regional water establishments). This is problematic as, on one hand, urbanization and urban development have impacts on water flows, consumption and pollution. On the other hand, water resources are historically appropriated as local resources and integrated into local development initiatives (in agriculture, tourism and industry) and there is clear resistance to give its management to a sectorial supra-local authority (regional water establishment) especially as this authority does not concern itself with local development issues. In this context, their approach works on: - Building a platform of stakeholders (including water sector actors (Bekaa Water Establishment, Ministry of Energy and Water, Litani River Authority), Zahle municipality, representatives of the industrial, agricultural and commercial sectors, etc.) where these issues are discussed and possibly information shared. - Developing a number of synthesis studies that help understand the context. - Working with the urban planning consultant mandated by the municipality of Zahle to draw its new Masterplan (including urban development orientations and land use zoning) to allow him to integrate the results of the studies (in 2)) in his Masterplan and sensitize him to water-sensitive urban planning and design approaches (including "ville perméable" and "sponge city" approaches) - Through a participatory workshop, identify with stakeholders' possible projects/initiatives that would enhance urban water management in the city of Zahle - Based on the workshop results and available funds develop a pilot project or prepare feasibility studies that could serve other projects | - Ongoing (year two of project); - Very limited budget funded; - Difficult coordination with water stakeholders in the Bekaa region; - Enlargement of water management scale to encompass different surrounding regions, since the watershed is common for other regions; - Working through municipalities to enhance efficient climate resilient interventions within the municipal boundaries. | Complementary - Water management - WASH service delivery - Agriculture and urbanization trends in Central Bekaa Non-Duplication - Masterplan for Zahle |
| ReWater MENA managed by the International Water Management Institute and funded by SIDA http://rewater-mena.iwmi.org/ | Regional project researching and promoting a safe reuse of treated wastewater in Lebanon, Egypt and Jordan. In Lebanon, it has three main components: - A study assessing the Wastewater reuse potential at national level to inform government and decision makers on where and how wastewater can be reused and the associated constraints (technical, social, financial, institutional) - Two specific studies around two respective WWTPs where reuse models will be designed in a participatory approach involving stakeholders at all levels. The outputs will be two models (technical, economic and management plans) ready to be physically implemented by the Government and donors. The Rewater MENA won’t be implementing infrastructure. - Support to the Lebanese Government in developing legal standards for wastewater reuse, based on the FAO Lebanese guidelines (2010). This is currently being done within a committee recently formed by LIBNOR which consists of different relevant ministries and other stakeholders (the meetings started in September 2019). | Designing a wastewater reuse system is a complex endeavor as it entails a diversity of technical, environmental, economic, social and institutional factors. It should be carefully designed with the different stakeholders, especially plant operators and users. It should be guaranteed that The WWTP will continue operating, that water is of sufficient quality, that water is needed and wanted by farmers, that the system is economically feasible and socially accepted. Different scenarios of geographic allocation should be considered and assessed with farmers themselves. If not, there is a risk that infrastructure won’t be used. It also has to be politically accepted by the water administration. For example, the Litani River Authority did not want to use treated water in their irrigation systems. | Complementary - Adopting wastewater reuse guidelines especially in the target area - Benefiting from existing coordination platforms Non-Duplication Applying wastewater reuse projects for both irrigation and crop improvement |
| ELARD and UNDP – Provision of Services for the Development of Local Level Master Plans and Detailed Urban Plans in the Qaraoun Catchment. Draft Master Plan Report (April 3, 2019). | Based on the National Physical Master Plan for the Lebanese Territory recommendations, as well as on the detailed diagnostic of the study area that was prepared during the first phase of the project, this Master Plan for the Districts of Zahle, West Bekaa and Rachaya addresses challenges to be addressed at several levels including landscape, heritage and environmental, urban development structure, as well as economic development challenges. | - No industrial activities in core zone - New Urbanization not allowed - Heavy industries to be relocated far from residential and agricultural areas - The masterplan which is in line with the National Physical Master Plan for the Lebanese Territory (NPMPLT) classifies the study area into four zones: A (Agricultural), U (Urban), N1 (Peaks: high mountain above 1900m), and N3 (Valleys, quality forests and continuous ecological areas) | Complementary Continuation of the mapping exercise especially in landscapes and heritage, natural hazards, urban infrastructure and economic development challenges Non-Duplication Thorough studies on soil, land use, hydrogeology water sheds and climate related effects on various sectors |

- Learning and knowledge management

One of the main objectives of the project is to promote KM / learning between Jordan and Lebanon, but also beyond, also with the purpose to replicate and upscale demonstrated adaptation approaches and techniques. This is mostly done through a dedicated project KM / learning component 4.

As component 4 will be mostly executed by UN-ESCWA, learning will be promoted through their Arab Centre for Climate Change Policies and existing KM platform.

At the regional / international level, learning / knowledge will be managed and promoted through the creation of a community of practice on climate change in urban areas (with implications of the Syrian crisis) (with documentation of good practices and lessons; replication package; project baseline and results video; etc.). Sharing of lessons will also be done through regional / international seminars organised by UN-ESCWA (e.g. Arab water weeks, Arab Ministerial Water Councils, Regional Preparatory Meeting on Climate Change) and international events (e.g. (AMFHUD, WUF, COP side events (2x); AFSD; HLPF 2022 reviewing SDG 11 and 6 and HLPD 2023).

At the national level (in and between Jordan and Lebanon), learning / knowledge will also be managed and promoted through UN-ESCWA. This will be done through regional SC meetings (where possible organised at the same time as UN-ESCWA organised regional / international seminars) and a platform/working space for communication and sharing lessons regarding the project (research; project best practices and lessons learned). Field visits to project sites will also be organised.

At the district / municipal level, learning / knowledge will be managed and promoted by a consultancy firm. UN-habitat in coordination with universities and execution entities. Geo-referenced databases and an online platform will be used to share project data produced + territorial observatories (by universities) in the target areas. The consutancy firm will also develop the ‘regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities.

At the community level, project beneficiaries will be involved through a participatory assessment,  planning approach (comp 1) and capacity and skills building (comp 2) to operate, maintain and replicate the proposed concrete adaptation techniques being developed under comp 3. Moreover, capacities of government officials, mostly at the municipal level, but also at the national level, will be strengthened to operate, maintain techniques and replicate these, as well as approaches.

Knowledge sharing tools to be used include websites, including existing platforms, social media streams (e.g. Facebook), presentations and a project video, but also produced strategies, plans and guidelines.

Table 15: Learning and knowledge management

| Expected Concrete Outputs | Learning objectives (lo) & indicators (i) | Knowledge products |
| --- | --- | --- |
| Outputs 1.1. Territorial planning and development strategy / guidelines with CC and gender mainstreamed in Lebanon 1.2. Urban master plans at municipal level with CC and gender mainstreamed in Lebanon 1.3. Urban master plans at municipal level with CC and gender mainstreamed in Jordan | (lo): To use strategies and plans to better plan water (taking into consideration both climate change and DPs migration (i): Number of plans; number of trainings | - Territorial planning and development strategy / guidelines, incl. toolkit on mainstreaming climate change and DPs considerations in land use planning to address water issues in type 2 cities - Urban master plans and investment plans (+ feasibility assessments) - Training reports |
| Output 2.1. Community organisation, awareness and capacity / skill building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.1 2.2. See above for output 3.2. 2.3. See above for output 3.3. 2.4. See above for output 3.4. 2.5. See above for output 3.5. 2.6. See above for output 3.6. 2.7. See above for output 3.7. 2.8. See above for output 3.8 | (lo): Build community and vulnerable groups capacities and skills to operate and maintain resilient water systems; identify best way to reduce (potential) tension between groups (i): Number of plans; number of trainings | - Operation, maintenance and replication plans - Training toolkits for building capacities at the community level - Training reports |
| Output 3.1. Rooftop rainwater harvesting in Lebanon 3.2. Rooftop rainwater harvesting in Jordan 3.3. Greywater treatment and reuse in Jordan 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon 3.5. Efficient treatment and reuse of wastewater in Jordan 3.6. Water-use-efficient irrigation of treated wastewater in Lebanon 3.7. Water-use Efficient irrigation of treated wastewater in Jordan 3.8. Permaculture demonstration - closed loop water system in Jordan | (lo): showcase best practice information on replicable innovative techniques / interventions in context of high influx of DPs and climate change impacts (i): Number of techniques / interventions showcased | - Techniques / interventions documented |
| Output 4.1. Regional / international KM with focus on sharing project lessons and replication 4.2. Jordan and Lebanon KM with focus on project progress, best practices and lessons learned 4.3. Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities 4.4. Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities | (lo): Share lessons on how to address climate change impacts in type 2 cities context (i): Number of knowledge products and events on which lessons will be shared | - Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities - Community of practices - KM platforms - Project video |

- Consultative process

For the project preparation phase, consultations have been conducted with key stakeholders and beneficiary communities, including representatives from the government, UN agencies, NGO’s and vulnerable groups. An overview of consultations conducted, including objective, outcomes and how inputs have been incorporated in the proposal is available in annex 3. Details such as completed consultation questionnaires and attendance sheets are available on request. Four type of consultations shaped this proposal. Consultations to:

- Align with National and sub-national priorities: throughout the project preparation phase, UN-Habitat worked with the AF focal points, ministries mandated to work on aspect touched by the project (i.e. water, agriculture, spatial planning, etc.) and target municipalities. The proposed project activities have been prioritised / selected with these government representatives, as well as the target areas. Both Jordan and Lebanon governments prioritsed water harvesting and wastewater treatment and reuse adaptaion measures (see annex 3)

- To avoid duplication with other projects (government, UN agencies, NGOs, etc.) and use lessons learned (see annex 3)

- Identify specific needs and possible concerns of vulnerable groups. In line with AF ESP and GP policies, consultations with beneficiary communities and specific groups (especially women, youth, Syrians) of each sub-project took place to identify specific needs and possible concerns regarding the proposed project activities (see annex 3, 4 and 5).

- Identify potential environmental and social risks and impacts. Related to above and in line with AF ESP and GP policies, consultations took place to identify potential risks and impacts of proposed project activities. This also includes public hearings in line with national requirements for conducting EIA ((see annex 3, 4 and 5).

Table 16: List of stakeholders consulted. For more details, including outcomes, see annex 3

| Stakeholder | Leb | Jor |  | Principle choice for consultation |  |  |  | Method |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | To align with government priorities | To avoid duplication with other projects | To comply with standards, rules and regulations | Identify specific needs and possible concerns vulnerable groups | Identify potential environmental and social risks and impacts. |  |
| Ministry of environment | x | x | x | x | x |  | x | - Private meeting - Steering committee |
| Ministry of energy and water | x |  | x | x | x |  |  | - Private meeting - Steering committee |
| Council for development and reconstruction | x |  | x | x |  |  |  | - Private meeting - Steering committee |
| Bekaa Water Establishment | x |  | x | x | x |  |  | - Private meeting - Steering committee - Execution partner |
| Litani River Authority | x |  | x | x | x |  |  | - Private meeting - Steering committee - Execution partner |
| Lebanese Agriculture Research Institute | x |  | x | x |  | x |  | - Private meeting - Execution partner |
| Municipality of Zahle | x |  | x | x | x | x |  | - Private meeting - Steering committee |
| Municipality of Bar Elias | x |  | x | x | x | x |  | - Private meeting - Steering committee |
| Other target Municipalities | x | x | x | x |  |  |  | - Private meeting |
| Ministry of Planning and International Coordination |  | x | x | x |  |  |  | - Private meeting - Steering committee |
| Ministry of water and irrigation |  | x | x | x | x |  |  | - Private meeting - Steering committee |
| Ministry of Local Administration |  | x | x | x |  |  |  | - Private meeting - Steering committee |
| The Ministry of Awqaf Islamic Affairs and Holy Places |  | x | x | x | x |  |  | - Private meeting - Steering committee |
| Ministry of Education |  | x | x | x | x |  |  | - Private meeting - Steering committee |
| WAJ / Yarmouk Water Company |  | x | x | x | x |  |  | - Private meeting - Steering committee |
| Municipality of Irbid |  | x | x | x | x | x |  | - Private meeting - Steering committee |
| Municipality of Mafraq |  | x | x | x | x | x |  | - Private meeting - Steering committee |
| UploaD | x |  |  | x |  | x |  | - Calls - Execution partner |
| UN-ESCWA | x |  | x | x |  | x |  | - Private meeting - Execution partner |
| UNICEF | x | x |  | x |  | x | x | - Private meeting - Execution partner |
| Johud |  | x |  |  |  | x | x | - Private meeting - Execution partner |
| Badia Fund |  | x |  |  |  | x | x | - Private meeting - Execution partner |
| Permaculture Research Institute |  | x |  | x |  | x | x | - Private meeting - Execution partner |
| UN Women | x | x |  | x |  | x | x | - Private meeting |
| UNHCR | x | x |  | x |  | x | x | - Private meeting |
| UNDP | x | x |  | x |  |  |  | - Private meeting |
| FAO |  | x |  | x |  |  |  | - Private meeting |
| ILO | x | x |  | x |  | x | x | - Private meeting |
| OHCHR | x |  |  | x |  | x | x | - Private meeting |
| IUCN | x | x |  | x |  | x | x | - Private meeting |
| GIZ | x |  |  | x |  |  |  | - Private meeting |
| Norwegian Refugee Council | x |  |  |  |  |  | x | - Private meeting - Community consultations |
| Solidarites International | x |  |  |  |  |  | x | - Private meeting |
| WB | x |  |  |  |  |  |  | - Private meeting |
| Vulnerable groups, including women, youth, Syrians and farmers | x | x |  |  |  | x | x | - Focus groups consultations - Public hearings |

During the pre-concept note development phase, consultations were conducted with the AF focal points and relevant ministries in both countries to ensure project alignment with national priorities (i.e. national strategies and plans). Since then, UN-Habitat staff in both countries continued close coordination with government representatives at the national and municipal level, also through formed steering committees.

During the concept note development phase, consultation were conducted with project beneficiary groups, including vulnerable groups, including through (12) focus group discussions. The consultations aimed to identify the most hazardous climate change impacts on target communities and groups, their barriers to adapt to such impacts, their specific needs and their potential concerns regarding proposed project activities. Vulnerable groups consulted include: Syrian DPs, women, youth, children and disabled people by ensuring their representation in most of the discussions. Whenever possible and acceptable, focus groups with women only followed the main discussions. Some of the community consultations were organised in collaboration with municipalities of Mafraq, Irbid and Zahle and others were organised with support of NGOs and CBOs (i.e. World Vision, Norwegian Refugee Council) working in the target areas.

Workshops with government representatives, academia, etc. were also conducted to identify the main climate change issues, needs and other projects (to avoid duplication) in target municipalities and to further select project activities. Also, “one to one” meetings targeting relevant government institutions, UN agencies, other international organisations and NGOs were conducted.

The outcomes of consultations shaped the selection of proposed interventions at that stage. Some of the proposed interventions were excluded due to cost inefficient (in low density areas), non-feasibility due to e.g environmental risks (e.g groundwater use) and non-preference of beneficiary groups. In some discussions, new interventions were suggested by the communities (e.g. efficient irrigation techniques). Also, measures will be taken to respond to some concerns raised, especially those of Syrian DPs and women

During the full proposal development phase, accredited consultants to conduct feasibility assessments and environmental and social risks screening and impact assessment were hired in both countries. These consultants followed national requirements to do these assessments (including public hearings), as well as AF requirements (consultations with all beneficiary groups to identify potential risks and impacts, including possible concerns). Complete national feasibility assessment, ESIA-ESMP and consultation reports are available on request.

Figure 11: Lebanon workshop to identify main climate change issues, needs and other projects in target municipalities and to futher select project activities. Attendance sheets can be shared on request.

Figure 12: Jordan workshop to identify main climate change issues, needs and other projects in target municipalities and to futher select project activities. Attendance sheets can be shared on request.

Figure 13: Example of community consultations and women focus groups and representatives in Lebanon

Figure 14: Example of community consultations and women focus groups and representatives in Jordan

- Justification of funding request

There is little exploration of how urban systems respond to a rapid influx of new and often long-term residents by conflict combined with climate change impacts. Therefore, it is manifest and critical to build resilient communities and institutions that are equipped to respond to shocks and stresses arising from climate change in combination with displacement. This project explores and collects evidence of approaches and best practice techniques that effectively respond to these challenges faced in urban areas in Jordan and Lebanon.

The project will support implementation of national priorities as well as responding to local needs, especially of the most vulnerable, and will provide added value to national plans and approaches through implementation of innovative technical interventions. The proposed project components also fully align with AF outcome areas. This alignment has resulted in the design of a comprehensive approach to address climate change related water challenges in a type 2 host cities context.

There is a need for concrete adaptation actions in the water sector in the targeted urban areas in Jordan and Lebanon focusing on the most vulnerable groups. Since most Syrians in Lebanon and Jordan work in the water-dependent agriculture sector and have limited access to water, increasing water scarcity, acerbated by climate change, is a big challenge. The actions are crucial for the urban areas to cope with current and future climate change impacts exacerbated by the influx of Syrian DPs. The Third National Communications to the UNFCCC of Jordan and Lebanon stated clearly that financial constraints are among the barriers to adaptation and that there is a clear need for funding and capacity building to support national and municipal climate action. As mentioned earlier, the target urban areas were selected because of a combination of existing and projected climate change-related water challenges, high pressure on water resources due to high influx of DPs and lacking resources and capacities to address these climate change-related water issues and specific needs of DPs, which includes access to affordable water.

From a regional perspective, the project can be justified by responding to some funding gaps under the regional Syrian crisis response programming (i.e. 3RP), where budget gaps exist, especially under the WASH and the social cohesion and livelihoods components, which is most relevant in ‘host’ cities (see also annex 1). Besides that, considering the significance of the combined challenges posed by the climate change and the Syrian crisis, regional knowledge exchange and learning is needed, between Jordan and Lebanon, but also in the wider region, which will be done through component 4.

The project aims to maximizing the funding amount for the concrete adaptation component (component 3; USD 8 million, which is 69 percent of the sum of the four project components); funding allocation to component 2 is required to operate, maintain and replicate the proposed concrete interventions under component 3. Funding for component 1 is needed to more efficiently assess, plan and manage water at the municipal level, including to identify additional solutions to adapt to climate change.

The table below provides a justification for funding requested, focusing on the full cost of adaptation reasoning, by showing the impact of AF funding compared to no funding (baseline) related to expected project outcomes.

Table 17 Overview of impact of AF funding compared to no funding (baseline) related to expected project outcomes

| Project outcomes | Baseline (without AF) | Additional (with AF) | Comment and alternative adaptation scenario’s |
| --- | --- | --- | --- |
| 1.1. Strengthened municipal institutional capacity to manage climate change and DP crisis related urban water scarcity challenges by mainstreaming these aspects into spatial strategies + developing action / investment plans and guidelines (with identified solutions) to use water most efficiently within municipal boundaries (in line with AF outcome 2) | In Jordan and Lebanon, water is managed at the national and district scale, by looking also most solely at current demand and supply needs, with limited consideration of climate change and population movement trends. Most of the response in target areas is still humanitarian; therefore, a sustainable water assessment, planning and management approach is lacking; | The activities related to this outcome will allow municipal governments to assess, plan and manage climate change and DPs movement related risks and vulnerabilities, especially related to water, in a participatory, integrated, sustainable and climate change resilient way; Displacement and climate change are increasingly important factor driving urban growth trends. Taking into account the scale, scope and impacts of displacement and climate change in the target areas, strategies and master plans will help municipal government to respond to the challenge effectively | Municipal governments lack the capacity and financial resources to execute activities related to this outcome without support Without sustainable and climate change resilient approaches, target areas will become more water scarce, resulting in negative effects for poverty reduction targets and livelihood security and possible tension over scare resources. Alternatively, water is managed through IWRM approaches, but this is not in line with national priorities / practices |
| 2.1.1.Strengthened DPs and host communities awareness and ownership of CC adaptation measures + capacities strengthened to operate, maintain and replicate proposed adaptation measures, including skills building (in line with AF outcome 3 and 8) | Target communities have very limited options (capacity – skills and technically - and financial resources) to protect their people and assets against climate change impacts, especially lack of water. Rising social tensions between host communities and DPs, pose risks and threats to development gains | The activities related to this outcome (combined with outcome 1) will enable communities and vulnerable groups to operate and sustain systems and to assess, plan and manage these together. It will also increase livelihood / income security; Inclusive approaches that promote social cohesion need to be an integral part of displacement responses, especially around scare resources | Communities and vulnerable groups lack the capacities to operate and sustain systems and to assess, plan and manage these together. Without sustainable and climate change resilient water management approaches at community level, target areas will become more water scarce, resulting in negative effects for poverty reduction targets and livelihood security and possible tension over scare resources. Alternatively, livelihoods could be diversified more, but as water is an urgent issue, this has been prioritized. |
| 3.1.1. Increased adaptive capacity within the water sector through resilient and sustainable water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context and benefitting vulnerable groups (in line with AF outcome 4 and 6 and 8) | Municipal governments invest very little in sustainable and climate change resilient urban water services, considering most cities in Jordan and Lebanon are already suffering from inadequate service provision and overextraction and pollution of groundwater. Displacement and climate change exacerbate the situation by adding extra pressure on services, often becoming a source of tension with discontent and competition around services. | The activities related to this outcome will increase the sustainability and climate change resilience of water-related services and livelihoods dependent on water in and around the target municipalities. Taking into consideration the DP and climate change context, techniques selected can be replicated in similar context areas. | Top-down proposed interventions have the risk of not being community driven and appropriate and will also not respond to the situation. The interventions selected respond to larger water system challenges, especially overextraction of groundwater and water pollution, which pose health risks and livelihood security challenges. Alternative adaptation scenarios are ad hoc humanitarian responses, which would respond to urgent needs, but not in a sustainable and climate change resilient way. |
| 4.1.1. Strengthened (inter)National institutional capacity to manage climate change and DP crisis related urban water scarcity challenges, including lessons learned collected and shared regionally (in line with AF outcome 3 and 8) | National governments in the Mashriq region have limited capacity and knowledge about available models, tools, techniques + limited financial resources to respond to the combined challenges of climate change and displacement , especially in urban areas. | The activities related to this outcome will allow governments in the region, including at the municipal level, to replicate the approach / model and best practice adaptation interventions to respond to a combination of high DP influx (i.e. type 2 cities) and climate change challenges | Without activities related to this outcome, there is a risk that interventions won’t be replicated and sustained and demand for adopting similar approaches is not generated; and high-level and international support and engagement for the proposed approach is not mobilized. |

- Sustainability

The adaptation benefits achieved through the project will be sustained after its end, and replication and scaling-up options promoted through other (potential) funds after its end, especially through component 4. Sustainability and maintenance arrangements for concrete adaptation interventions (comp 3) are layed-out in table 17 below, as well as those for strategies and plans developed under comp 1 and capacities build under comp 1 and 2. Knowledge produced will be shared through comp 4.

At the regional level, project learning and replication and upscaling of outcomes will be promoted through comp 4, which includes knowledge and learning exchange between Jordan and Lebanon and the larger region. At the national level, the project will be sustained through the strong linkages of the proposed project activities with national and sub-national priorities (ensuring national buy-in). At the local level, the full engagement of communities and vulnerable groups in project activities, including assessments, planning and decision-making processes, should achieve building of communities’ awareness and capacities and furthermore ownership and leadership in the area of water management – see component 1 and 2. Specific emphasis is given to community capacity strengthening to operate, maintain and replicate the systems (including the development of operation, maintenance and replication plans). Also, through the participatory approach, the project activities aim to contribute to avoid potential future tension over scare resources. With all four components, the project aims to support sustainable development in target areas in Jordan and Lebanon and the wider region, compared to a currently humanitarian / emergency driven approach.

Institutional sustainability: the project paves the way for the Jordan and Lebanon national and municipal governments, but also other governments in the region, to replicate and up-scale the project through the development of best practices assessment, planning and management approaches (comp 1) and best practices concrete adaptation measures, that will be shared regionally under comp 4. Trainings of government staff, especially at the municipal level, will be conducted to strengthen relevant government capacities to deliver and sustain project activities.

Social sustainability: by organizing and fully engaging community members and vulnerable groups in project activities, including assessments and planning processes during project preparation and implementation, the project aims to achieve long-lasting awareness and capacities of community members.

Economic sustainability: investing in increasing the resilience of vulnerable assets is a sustainable economic approach. It will avoid future costs related to drought / water scarcity and flood impacts, especially on the vulnerable agriculture sector.

Environmental Sustainability: the proposed project interventions support environmental sustainability by reducing the use overextracted groundwater resources and reduce pollution of water, including of streams and irrigation channels.

Financial sustainability: the proposed interventions are fully aligned with national and sub-national priorities and programmes and therefore, the government actively supports the project and interventions, including anchoring it to existing programmes and monitoring frameworks.

Technical sustainability: techniques used are innovative in the target areas but through operation and maintenance plans and the need to adopt such techniques, also identified in national priorities, sustainability will ensured.

Table 17: Project activities’ sustainability and maintenance arrangements, including replication and upscaling

| Detailed outputs / activities | Maintenance measures | Responsible | Replication + Upscaling measures | Responsible |
| --- | --- | --- | --- | --- |
| Component 1: Increasing the resilience of municipal governments: Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from DPs migration |  |  |  |  |
| - Territorial planning and development strategy / guidelines at district level with climate change and gender mainstreamed (Lebanon) | - Below municipal staff will be involved and trained, as well as appointed staff form higher level planning authorities to develop the strategies and guidelines and to embed these in national government processes | Planning: Un-H Un-H with a consultancy firm Implementation/after project: target district; Ministry of Interior and Municipalities (MoIM), Ministry of Public Works (MoPW), Ministry of Energy and Water (MoEW), Ministry of Environment (MoE), Ministry of Agriculture (MoA). | Replication at other districts, informing area-based planning to the Directorate General of Urban Planning (under the MoPW) | Line Ministries |
| - Urban master plans at municipal level with climate change and gender mainstreamed (Lebanon) | - As municipalities are mandated to develop master plans and to manage water within municipal boundaries, dedicated staff will be appointed and trained to deliver and sustain project activities | Planning: Un-H with a consultancy firm Implementation/after project: target district; Ministry of Interior and Municipalities, Ministry of Public Works, Ministry of Energy and Water, Ministry of Environment. | Replication at other Municipal levels of the district. Informing Municipal strategic planning to the MoIM | Line Ministries |
| - Urban master plans at municipal level with climate change and gender mainstreamed (Jordan) | - As municipalities are mandated to develop master plans and to manage water within municipal boundaries, dedicated staff will be appointed and trained to deliver and sustain project activities | Planning: Un-H with Consultancy Firm Implementation: target municipalities; Ministry of Local Administration; | Replication across all remaining municipalities | Line Ministries |
| Component 3: Increasing the adaptive capacity of the water sector: Expand unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context |  |  |  |  |
| - Rooftop rainwater harvesting in Lebanon | Under comp 2. Output 1 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: UNICEF/ Lebanese Agriculture Research institute (LARI under MoA) After project end: Buildings owners and Municipalities | Through the Municipal zoning and building permits | Municipalities |
| - Rooftop rainwater harvesting in Jordan in | Under comp 2. Output 2 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: JOHUD After project end: Ministry of Education and Ministry of Awqaf Residential Building owners | Applying similar interventions to other schools and mosques | Directorate of Education: Building Department Ministry of Awqaf: Maintenance Department |
| - Greywater treatment and reuse in buildings in Jordan in | Under comp 2. Output 3 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: UNICEF After project end: Ministry of Education and Ministry of Awqaf | Applying similar interventions to other schools and mosques | Directorate of Education: Building Department Ministry of Awqaf: Maintenance Department |
| - Efficient treatment in and reuse from wastewater from Zahle WWTP, Lebanon | Under comp 2. Output 4 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: The Regional Technical Office (RTO), Litany River Authorities (LRA), Bekaa Water Establishment (BWE) After project end: BWE, Zahle Municipality | Through applying similar interventions to other WWTP | BWE, MoEW |
| - Efficient treatment in and reuse of wastewater from Bar Elias wetlands, Lebanon | Under comp 2. Output 4 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: LRA, UNICEF After project end: LRA | Through applying wetlands on Litany river course | LRA |
| - Efficient treatment in and reuse of wastewater from Mafraq WWTP, Jordan | Under comp 2. Output 5 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: WAJ/YWC After project end: YWC | Ensure reclaimed water remains of high quality and up to Jordanian Standards: Law No. (22) of 1997 | YWC |
| - Efficient treatment in and reuse of wastewater from Maerad WWTP, Jordan | Under comp 2. Output 5 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: WAJ/YWC After project end: YWC | Ensure reclaimed water remains of high quality and up to Jordanian Standards: Law No. (22) of 1997 | YWC |
| - Efficient treatment in and reuse of wastewater in Akaidr WWTP, Jordan | Under comp 2. Output 5 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: WAJ/YWC After project end: YWC | Ensure reclaimed water remains of high quality and up to Jordanian Standards: Law No. (22) of 1997 | YWC |
| - Water-use-efficient irrigation of treated wastewater from Zahle WWTP, Lebanon | Under comp 2. Output 6 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: RTO, Zahle Municipality After project end: Farmers and Municipality | Through irrigation masterplans | LARI, MoA,Zahle Municipality Farmers Cooperatives |
| - Water-use-efficient irrigation of treated wastewater from Bar Elias wetlands, Lebanon | Under comp 2. Output 6 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: RTO, Bar Elias Municipality After project end: Farmers and Municipality | Through irrigation masterplans | LARI, MoA, Bar Elias Municipality, Farmers Cooperatives |
| - Water-use-efficient irrigation of treated wastewater from Mafraq WWTP, Jordan | Under comp 2. Output 7 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: BADIA Fund After project end: Farmers | Through irrigation masterplans | Water association members |
| - Water-use-efficient irrigation of treated wastewater from Maerad WWTP, Jordan | Under comp 2. Output 7 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: JOHUD After project end: Farmers | Through irrigation masterplans | Water association members |
| - Water-use-efficient irrigation of treated wastewater from Akaidr WWTP, Jordan | Under comp 2. Output 7 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: JOHUD After project end: Farmers | Through irrigation masterplans | Water association members |
| - Permaculture demonstration – efficient use of water | Under comp 2. Output 8 - Operation, maintenance and replication plans - Awareness raising campaigns and capacity development trainings | During implementation: PRI in cooperation with JUST After project end: PRI in cooperation with JUST | Landscape rehabilitation plan(s) by students and PRI team for surrounding areas, including technical replication guidebook (under comp 2); Permaculture site at JUST will function as a 2nd PRI regional demonstration site | PRI in cooperation with JUST |
| Component 4: Improving knowledge and policies and regulations to increase urban resilience in the region: Project KM and replication, incl. development of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration) |  |  |  |  |
| - Regional / international KM with focus on sharing project lessons and replication | Knowledge will be embedded and shared through the UN-ESCWA Arab center for climate change policies knowledge hub, which is sustained by UN-ESCWA already. The project will feed into refugee response plans in the region | UN-ESCWA + Un-Habitat | This component is specificially designed to share all project lessons (above), also with the purpose to replicate and upscale these. Therse this component can be regarded as part of the replication and upscaling mechanism for the the project activities. This will be done through the UN-ESCWA Arab center for climate change policies knowledge hub, which is sustained by UN-ESCWA already. | UN-Hbaitat in cooperation with UN-Escwa and other key stakeholders |
| - Jordan and Lebanon KM with focus on project progress, best practices and lessons learned | National knowledge sharing will also be sustained through UN-ESCWA | UN-ESCWA + Un-Habitat Ministries of Environment |  |  |
| - Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities | Knowledge will be embedded and shared through the UN-ESCWA Arab center for climate change policies knowledge hub, which is sustained by UN-ESCWA already. The project will feed into refugee response plans in the region | UN-Habitat in cooperation with a consultancy firm and municipalities and universities |  |  |
| - Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities |  | UN-Habitat in cooperation with ministries |  |  |

- Environmental and social impacts and risks

The proposed project seeks to fully align with the Adaptation Fund’s Environmental and Social Policy (ESP), and its 15 safeguard areas, Gender Policy (GP), Further to Part II.F above on compliance with national technical standards, outlined below is a summary of the findings of the initial screening process to identify and evaluate potential environmental and social risks and impacts of proposed project actions, and based on that, of the entire project. With this information, the entire project has been categorized. As shown in section II.I and annex 3 and 4, consultations have been conducted to identify potential environmental and social risks and impacts and to identify specific groups needs and possible concerns. A draft gender baseline, containing disaggregated data and approach, containing specific approaches for women and youth, has been developed – see annex 5.

Normative, planning and capacity development activities (i.e. non-concrete interventions) under components 1, 2 and 4 consist of strategies and plans development, capacity development and knowledge exchange. The project will ensure beneficiary groups will be equally represented and equal benefit from the project activities – see annex 4.

Activities under components 3 are ‘concrete’ adaptation actions. Because of the scope of the proposed actions, which are numerous, small scale and very localized, and will be operated and maintained by water authorities, municipal staff and communities, where possible, who have a stake in avoiding environmental and social risks and impacts, potential direct impacts are limited. Indirect impacts and transboundary impacts are highly unlikely given that water quality improvement activities will only result in improved water quality, not a degradation. Target streams are not transboundary. Given this, cumulative impacts are also unlikely. Because of this, the entire project is regarded as a medium risk (Category B) project. Annex 3 provides an overview of risks screening and impact assessment outcomes conducted in both Lebanon and Jordan. In both countries, risks screening sheets have been completed for each proposed project activity. Besides that, accredited consultants prepared country-specific ESIAs, ESMPs and consultations reports in compliance with the AF ESP and GP and national requirements for conducting ESIAs. The outcomes have been consolidated in the proposal. The only proposed project activity that required an ESIA by law is the constructed wetlands in Bar Elias, Lebanon. A scoping report has been prepared, submitted and approved by the Lebanese government.

The country specific ESIAs, ESMPs and consultations reports are available through above website. The completed risks screening sheets for each project activity are available on request. The country-specific ESIA, ESMP and consultation reports are accessible here:

https://unhabitat.org/af-lebanon-jordan

The project is designed to generate positive economic, social and environmental impacts, using inputs from especially women and youth and DPs and host communities in target communities and by incorporating best practices from other projects. Consultation to comply to the AF ESP and GP have been completed – see Part II.I, Annex 2 and above publications The adaptation actions proposed have been selected together with ministries (through already established project steering committees), mayors, and community and vulnerable group representatives, making sure they are culturally and specific area-appropriate

Summary of outcomes:

Principle 1: Relevant laws and standards have been identified, including how the project and sub-project / outputs comply. Principles, 2,3 and 5, detailed stakeholder mapping has been conducted, vulnerable groups consulted and an inclusive assessment, planning and management approach for project implementation proposed. Principle 4 and 6: the human rights and core labour rights not ratified have been identified and relevant agencies consulted to identify related potential risks and mitigation measures. Principle 7: no indigenous groups were identified in the target areas. Principle 8: all involuntary resettlement will be avoided; all interventions will be on public land or in building of which owners and managers agreed with the proposed interventions. Principle 9 and 10: no protected natural habitat would be harmed, as confirmed by IUCN. 11 and 12: project activities may result in small increase of energy use. This will be companesated through installation of PV. Principle 13. Although project activities aim to improve water quality, there may be a risk that the quality does not comply to standards. Risks mitigation measures are in place to recude the risk. Principle 14, no heritage sites were identified in the target areas (as per UNESCO website). Principle 15: lands and soils will not be affected negatively as all proposed interventions have a sustainable land use planning approach and won’t touch vulnerable soils. For more info see Part II.F, Part II.I and annex 3, 4 and 5.

Table 18: Overview of the environmental and social impacts and risks. For more details see section annex 4.

| Checklist of environmental and social principles | Principle triggered during risks screening | Justification. (For potential impacts and risks see annex 4 and country-specific assessments conducted) |
| --- | --- | --- |
| Compliance with the Law | No | All relevant rules, regulations and standards have been identified for all proposed project activities, including procedures / steps to comply to these. |
| Access and Equity | No | All project beneficiaries (i.e. population; groups) have been mapped for each project activity / output. Community consultations and focus groups discussions have been conducted per beneficiary group to identify possible rivals, disputants and concerns related to equal access of project benefits |
| Marginalized and Vulnerable Groups | No | All project beneficiaries (i.e. population; groups), including marginalised and vulnerable groups have been mapped for each project activity / output. Desk research, expert consultations and community consultations and focus group discussions have been used to identify possible risks / adverse impacts of project activities on marginalized and vulnerable beneficiary groups (i.e. specific needs, limitations, constraints and requirements of groups). |
| Human Rights | No | Possible project human rights issues have been identified by assessing whether Jordan and Lebanon are cited in any Human Rights Council Special Procedures, and to confirm and understand possible issues through consultations with ‘experts.’ Communities have also been consulted about possible human rights issues with the purpose of design activities appropriately |
| Gender Equity and Women’s Empowerment | No | All project beneficiaries (i.e. population; groups), including women and youth have been mapped for each project activity / output. Desk research, expert consultations and community consultations and focus group discussions have been used to identify possible risks / adverse impacts of project activities on women and youth. A ‘gender’ annex has been developed |
| Core Labour Rights | No | Possible Core labour rights compliance issues have been assessed by analysing if Jordan and Lebanon ratified relevant conventions and by understand possible issues through consultations with ILO |
| Indigenous Peoples | No | No indigenous people are present in the project / programme target areas. |
| Involuntary Resettlement | No | No physical or economic displacement will take place due to the project/programme. This has been determined by mapping project target sites land ownership (private, public) and land use, also informally, and through consulting communities / users on the possible risk of resettlement and to get agreement on proposed interventions (i.e. no interventions will take place without the consent of inhabitants in the targeted areas). Land owners, private or public, have agreed with using their land for project activities. As for the wetlands, the target land is public land (belonging to the Litani River Authority) and no land use, even informally takes place in the area. |
| Protection of Natural Habitats | No | It has been checked if any critical natural habitats exist in the target location, including their location, characteristics and critical value (i.e. legal protection status, common knowledge or traditional knowledge), as well as possible negative impacts on these due to project activities. This has been done by checking IUCN Red list and by consulting IUCN (regional office) |
| Conservation of Biological Diversity | No | It has been checked if any important biodiversity exist in the target location, including their protection status and other recognised inventories as well as possible negative impacts on these due to project activities. According to the IUCN red list and UNESCO Man and the Biosphere Programme reserve, no sensitive biospheres are located in the target areas. This was confirmed through consultations with IUCN (regional office). |
| Climate Change | No | Although very limited, energy use could be increased because of pumping of water from WWTP to farm lands. To compensate for this, PV will be installed at the plants |
| Pollution Prevention and Resource Efficiency | YES | An analysis of possible risks of inefficiencies in energy and material resource use and waste and pollution risks of each activity has been conducted. Irrigation of waste water from the Zahle WWTP for instance has been designed to serve farmers through a gravity system. There may be a small risks of contamination of soil, surface water and groundwater because of project activities at WWTP. Therefore some risks mitigation measures are put in place. |
| Public Health | YES | To avoid potential negative health impacts for project activities and other activities safety signs and equipment will be provided in line with core labour rights (155 and 187). Although the project intends to improve the quality already used for irrigation, water quality monitoring is required. The same accounts for the rainwater harvesting and greywater treatment and reuse interventions. Therefore some risks mitigation measures are put in place to make sure there will be no health risks because of water use. |
| Physical and Cultural Heritage | No | It has been checked if physical or cultural heritage sites are present or near project sites, as well as possible risks of impacts on these due to project activities. UNESCO listed Heritage sites in target area: Anjar has been identified as a heritage site in Lebanon (in the district of Zahle). However, this is not in the target areas |
| Lands and Soil Conservation | NO | The project ensures no negative impacts lands and soil conservation will result from project activities. All proposed project activities aim to enhance sustainable land and soil use, especially for agriculture use. No major excavations will take place, except for the initial phase of constructing the wetlands in Bar Elias, but this is to enhance vegetation. A study of the targeted area was done, showing that the target area has low organic matter content, which is one indicator of soil fragility. The proposed intervention will reduce the loss or degradation of the soil, reducing any related risk. |

# pART iiI:  Implementation arrangements

  - Arrangements for project management

The following arrangements for project management (oversight, coordination and execution) have been agreed upon with AF DAs, the project steering committees and Execution Partners in Jordan and Lebanon.

Figure 15: Project Organigram

Table 19: Key project organigram stakeholders and roles and responsibilities

| Stakeholder | Role and responsibility |
| --- | --- |
| UN-Habitat | Project oversight / supervision and coordination - Compliance with AF and UN-H policies and reporting / M&E requirements, incl. safeguarding system - Contracting and coordination execution partners - Coordination with Project Steering Committees to execute project components / activities |
| Project Steering Committees | Providing technical inputs to ensure smooth implementation of the project from start to completion, including providing advice on how to deliver project outputs and the achievement of project outcomes in a timely matter in line with national and sub-national strategies and technical standards: - Required coordination with relevant ministries and authorities - Approve annual work plans and review key project periodical reports; - Review any deviations and consider amendments to work plans and contractual arrangements. |
| Project Execution Entities | Execute specific project components / activities |

The organigram above (figure 18) shows how the project will be supervised, coordinated and executed at the regional, national and local level. As UN-Habitat is the Multilateral Implementing Entity (MIE) of the project, UN-Habitat will be responsible for the overall implementation of the project, including contracting of execution partners and coordination with stakeholders that have a ‘stake’ or say in the project, mostly through Project Steering Committees.

Regional level: at the regional level, project implementation will be supported through a Regional Project Supervision Unit (RPSU). This ‘Unit’ will be responsible for project supervision / oversight, including coordination with and between National Project Coordination Units (NPCUs), the Regional-level Project Steering Committee (PSC) and the Project Execution Entities (PEE). The Regional Project Supervision Unit will be responsible for ensuring project compliance with the AF and UN-H policies and reporting requirements, for contracting the Project Executing Entities and it will chair the Regional-level Project Steering Committee. This Regional-level Project Steering Committee will be responsible for ‘steering the ‘whole’ project from start to completion and for ensuring that the regional component (i.e. component 4) of the project is realized.

National level: at the national level, project implementation will be supported through National Project Coordination Units (NPCUs). These ‘Units’ will be responsible for daily project coordination in Jordan and Lebanon, including coordination on execution of the project activities with the Project Execution Entities. The ‘Units’ will also be a member of the National-level Project Steering Committees (PSCs) in Jordan and Lebanon. These National-level Project Steering Committees will be responsible for ‘steering the country specific project activities from start to completion.

Local level: at the local level, project implementation will be supported through the National Project Coordination Units (NPCUs). The National-level Project Steering Committees (PSCs) will also have (government) representatives from the sub-national level, including from the target municipalities..

Table 20: Stakeholders in the project steering committee

| Project Steering Committees (PSC) |  |  |  |
| --- | --- | --- | --- |
| Stakeholders | Regional | National |  |
|  |  | Lebanon | Jordan |
| UN-Habitat | Chair | Member | Member |
| UN-ESCWA | Co-chair | Member | Member |
| Lebanon MoE | Member | Chair |  |
| Lebanon MoEW | Member | Co-chair |  |
| Lebanon CDR |  | Member |  |
| Lebanon Bekaa Water Establishment |  | Member |  |
| Lebanon Litani River Authority |  | Member |  |
| Lebanon Agrarian LARI Research Institute |  | Member |  |
| Lebanon Municipality of Zahle | Member | Member |  |
| Lebanon Municipality of Bar Elias | Member | Member |  |
| Lebanon Execution Entities | On request | On request |  |
| Jordan MoE | Member |  | Chair |
| Jordan MOPIC | Member |  | Member |
| Jordan MWI |  |  | Co-chair |
| Jordan MoLA |  |  | Member |
| Jordan MAIAHP |  |  | Member |
| Jordan MoE |  |  | Member |
| Jordan Municipality of Irbid (GIM) | Member |  | Member |
| Jordan Municipality of Mafraq (GMM) | Member |  | Member |
| Jordan Execution Entities | On request |  | On request |
| Total | 9 + invitees | 10 + invitees | 10 + invitees |

In both Lebanon and Jordan, The National-level Project Steering Committees have been established, and chairs, co-chairs and members have already been identified and agreed upon. These Committees have already been functioning to support the development of this project proposal, including approving proposed Project Execution Entities, activities, budgets, etc.

Key stakeholders and roles and responsibilities

Table 21: overview main stakeholders and roles and responsibilities

Regional level

| Stakeholder | Role and responsibility |  |
| --- | --- | --- |
|  | Current | Project |
| UN-ESCWA | Regional coordination between governments in Arab region, including on climate change and urban agenda | - Co-chair PSC at regional level - Execution component 4 - Coordination execution component 4 at national level |

National and local level - Lebanon

| Government |  |  |  |
| --- | --- | --- | --- |
| Stakeholder |  | Role and responsibility |  |
| Main | Sub + Commissions | Government | Project |
| Ministry of Environment (MoE) | - AF DA - Office of the Minister - Climate Change Department - Urban Environment department | Manage the environment through policies, plans and legislation, including conserving water resources | - Member PSC at regional level - Chair of the PSC at national level - Policy advice and coordination and focal point on national Environmental and Social Policies and standards compliance - Scaling up adaptive measures to mitigate pollution to water bodies through the environmentally friendly and sound interventions. |
| Ministry of Energy and Water (MoEW) | - Office of the Minister - Water Resource department | Manage water resources and energy through policies, plans and legislation | - Member PSC at national level - Advise on execution component 3 on Wastewater reuse and diversion, also on Wetlands O&M. - Scaling up wastewater reuse and climate adaptive measures related to water scarcity. |
| Council for Development and Reconstruction (CDR) | - Water resources department | Engages in all phases of project implementation from planning, feasibility analysis, detailed design, bidding, expropriation, execution, and operation and maintenance of most public facilities on the behalf of the Government | - Member PSC at national level - Policy advice and coordination, including to comply to project national standards for public facilities - Operation and Maintenance of large projects until handed over to Water Establishments. |
| Bekaa Water Establishment (BWE) | - Office of Director General - Water resources department | Applies strategies and master plans for the Bekaa area, done in collaboration with the MoEW; Operation and Maintenance of water and wastewater facilities and main networks. Provision of Water services. In charge of monitoring water resources and the measurement of flows, estimation of water needs, allocation of water resources in all of the Bekaa regions. | - Member PSC at national level - Advise on execution component 3 on especially on the management of water and wastewater facilities (operates under the MoEW) |
| Litani River Authority (LRA) | - Office of Director General | Applies strategies and master plans for the Litani watershed, done in collaboration with the MoEW; Ensure water monitoring in all Lebanese rivers; Implement the Litani irrigation, drying, drinking water and electricity projects; Examine, manage and exploit the irrigation water in Central and Northern Bekaa | - Member PSC at national level - Advise on execution component 3 on managing the Wetlands and Litany river watershed (Operates under the MoEW) - Scaling up and promoting for low-cost and low maintenance measures to mitigate climate change impacts. |
| Lebanese Agriculture Research Institute (LARI) | - Director | Working under the supervision of the Minister of Agriculture; conducts research and experiments to solve problems facing the agricultural sector in this area; Has at its disposal eight experimental stations in an area of 280 hectares of agricultural land; Keeps close ties to the farmers and tries to develop research activities aiming at solving their problems. | - Member PSC at national level - Advise on execution component 3 on all irrigation projects, farmers and crops (operates under the MoA) - Scaling up and training more farmers to adopt climate change adaptive measures in agriculture. |
| Municipality of Zahle | - Public works committee of both municipalities - Municipal council members | Manage all public work projects, including water, electricity, and garbage collection according to law 118/1977; Public works and infrastructure implementation spent for municipal budget. Operation and maintenance Municipalities are responsible for managing unconventional water sources and supply within their boundaries, such as rainwater harvesting; Municipalities are also responsible for developing and managing municipal master plans in coordination with DGU | - Member PSC at regional level - Member PSC at national level - Policy advice and coordination, including to align with local plans - Advise on execution component 1 and 3 |
| Municipality of Barr Elias |  |  | - Member PSC at regional level - Member PSC at national level - Policy advice and coordination, including to align with local plans - Advise on execution component 1 and 3 and especially adopting construction measures to harvest rainwater in new constructions. |
| Municipalities of Hazerta, Bar Elias, El Marj, Saadnayel, Taanayel, Taalabaya, Terbol, Ferzol |  |  | - Member PSC at national level - Policy advice and coordination, including to align with local plans - Advise on execution component 1 and especially tackling climate change adaptive measures in territorial planning. |
| Non-government |  |  |  |
| UNICEF |  | Coordination of the inter-agency humanitarian response of the education and water sector and the child protection sub-sector in support of the Government; main government partner on WASH | - Execute outputs: 3.1 |

National and local level - Jordan

| Government |  |  |  |
| --- | --- | --- | --- |
| Stakeholder |  | Role and responsibility (policy / M&E, implementation, etc) |  |
| Main | Sub + Commissions | Government | Project |
| Ministry of Environment (MoE) | - AF DA - Directorate of the Climate Change | Manage the environment through policies, plans and legislation, including conserving water resources | - Member PSC at regional level - Chair of the PSC at national level - Policy advise and coordination and focal point on national Environmental and Social Policies and standards compliance |
| Ministry of Planning and International Coordination (MOPIC) | International Cooperation Directorate Local Development Programmes and Productivity Enhancement | Responsible for improving development policies and promoting active participation in the process, including coordinating and managing the necessary funding for development projects; responsible for preparing and updating Joint Response Plan (JRP) for Syrian crisis | - Member PSC at regional level - Member PSC at national level - Policy advise and coordination, especially on JRP and platform |
| Ministry of Water and Irrigation (MWI) | Climate Change Unit, Wastewater and sanitation Affairs (Design and Feasibility Study Directorate and Supervision and Technical Support Directorate), and Water Demand Management Directorate) | Manage water and irrigation through policies, plans and legislation. Awareness and Media Unit established a showcase room of water saving devices in the ministry | - Member PSC at national level - Policy advise and coordination, including to comply to national water strategies, plans and policies - Advise on execution component 3 on rooftop water harvesting (JVA) and the showcase rooms in municipal government buildings |
| Ministry of Local Administration (MoLA) | Zoning Directorate, Legal Unit, Higher Planning Council | Technical, financial and administrative advisor for all the local councils in the Kingdom | - Member PSC at national level - Policy advise and coordination, including on execution component 4: adopting a national programme for water harvesting from rooftops at municipal levels in the project selected governorates, incl. providing incentives/ exemption to encourage the installation of rainwater harvesting and scale it up at national level |
| The Ministry of Awqaf Islamic Affairs and Holy Places (MAIAHP) | Construction and maintenance department, Directorates of Awqaf at Irbid and Mafraq Governorates | Responsible for the Hajj & Umrah, Mosques –their reconstruction, rehabilitation, their needs and workers (Imam, etc)-; | - Member PSC at national level - Policy advise and coordination on activities in Mosques - Facilitate(d) coordination with Directorates of Awqaf in Irbid, Ramtha and Mafraq to select Mosques where activities related to greywater reuse, rooftop rainwater harvesting and the installation of water saving devices will be implemented. - Contribute to the public awareness campaigns and training in Mosques (through Imam) - Directorates - Supervise the O&M of the installed systems in mosques |
| Ministry of Education (MoE) | Directorate of Education in Iribd and Mafraq | Responsible for the Jordanian educational system | - Member PSC at national level - Facilitate(d) coordination with Schools Building Directorates in Irbid and Mafraq to select schools where activities related to rooftop rainwater harvesting and the installation of water saving devices will be implemented. - Provide capacity building and trainings to M. Of Education’s building directorates’ engineers - Directorate - Contribute to the public awareness campaigns and training on the operation and maintenance of the installed systems at schools. |
| WAJ / Yarmouk Water Authority Jordan and Company |  | Management of water in the north sector in accordance with the provisions of the Jordanian companies Law No. (22) of 1997, which is wholly owned by the Jordan Water Authority. | - Execute interventions related to enhancement of the treated wastewater quality and the management of its reuse by farmers in Mafraq, Maerad and Al Akaider around the WWTPs. - Continue to monitor the performance and operation of installed infrastructures and used treated effluent quality. - Facilitate coordination with farmers - Manage the reuse of reclaimed water by farmers, local NGOs and WUAs. - Support the public awareness campaigns related to installation of WSDs |
| Municipality of Irbid (GIM) |  | Manage all public work projects, including water, electricity, and garbage collection. Municipalities are responsible for managing unconventional water sources and supply within their boundaries, such as rainwater harvesting; Municipalities are also responsible for developing and managing municipal master plans | - Member PSC at regional level - Member PSC at national level - Policy advise and coordination, including to align with local plans - Advise on execution component 1 and 3, esp. water harvesting, incl. enforce the installation of rooftop rainwater harvesting system and tanks and issue relevant permits - Facilitate coordination with other local authorities and stakeholders |
| Municipality of Mafraq (GMM) |  |  | - Member PSC at regional level - Member PSC at national level - Policy advise and coordination, including to align with local plans - Advise on execution component 1 and 3, esp. water harvesting, incl. enforce the installation of rooftop rainwater harvesting system and tanks and issue relevant permits - Facilitate coordination with other local authorities and stakeholders |
| Non-government |  |  |  |
| The Jordanian Hashemite Fund for Human Development (JOHUD) |  | Johud is a local Non-Governmental Organization which has 51 Community Development Centers (CDCs) throughout the kingdom targeting the less fortunate groups, and remote and poor communities. Their work focuses on promoting water conservation awareness and providing livelihood opportunity in agriculture, water, energy and environment. | - Executing interventions related to rainwater harvesting from rooftops of mosques, schools, selected households and municipal buildings in addition to manage the treated wastewater reuse intervention in the farmlands around Mirad, Al Akaider and Ramtha WWTPs and establish new and efficient irrigation technology. - Capacity building and training on the installation of the irrigation system. |
| UNICEF |  | UNICEF is WASH sector lead in Jordan and their work focuses also on education and child protection in support of the Government. They have implemented WASH related activities in the Syrian refugee camps in Jordan. | - Executing component 3, the intervention related to grey water treatment and reuse in schools and mosques. |
| The Hashemite Fund for the Development of Jordan Badia |  | The fund is mandated to establish the concept of sustainable development in the Jordan Badia by implementing environmental, social and economic projects, while maintaining and respecting the existing culture and habits. The implemented a number of projects related to treated wastewater reuse, fodder cultivation enhancement and livestock production | - Execute and manage the treated wastewater reuse intervention in the farmlands around the treated wastewater reuse intervention around Mafraq WWTP and establish new and efficient irrigation technology. - Capacity building of farmers and public awareness on water management and efficient irrigation systems. |
| Permaculture Research Institute |  | B | - Execute the permaculture intervention at the Jordan University of Science and Technology (JUST). - Provide capacity building and training to (JUST). |

Legal and financial arrangements

UN-Habitat and the ministries of Environment (with the AF DAs) in Lebanon and Jordan will sign a joint Memorandum of Understanding to which this Project Document will be attached, to ensure that all partners are fully committed to the project.

UN-habitat will contract Project Execution Entities in Lebanon and Jordan through Memorandum of Understanding (MoU) or Agreements of Cooperation (AoC), which are legally binding financial tools, and UN to UN agreement to contract UNICEF and UN-ESCWA. The contract will be negotiated by the Regional Project Supervision Unit and cleared by UN-Habitat ROAS / HQ. For the UN to UN agreements, overheads will be passed through from the 7 percent PSC from the project cycle management fees, so there will be no double charge

The Regional Project Supervision Unit will develop an operational manual that clearly outlines the roles and responsibilities of the key project stakeholders and contain all the necessary tools, forms and templates required to administer the project. The operation manual will be shared with the National Project Coordination Units for inputs. While UN-Habitat takes responsibility of audits in line with AF requirements (each year), all contractors will be required to have ‘external’ audits of their budgets. The contractors will also be required to support the independent final evaluation.

Roles and responsibilities for environmental and social risks management / AF ESP and GP compliance

The Regional Project Supervision Unit will be responsibility for environmental and social risks management, including implementation of the Project ESMP. An AF and UN-H policies and reporting compliance expert will be part of the RPSU. This expert will also supervise Project Execution Entities on the implementation of the Project ESMP. Guidelines showing how to comply to the AF ESP and GP will be shared with all execution entities and they will be guided on process, including monitoring. A Safeguarding system compliance expert will also be part of the RPSU. Monitoring staff part of the RPSU will require having expertise in social risk management and be familiar with the AF safeguarding system. The RPSU will be backstopped by UN-Habitat HQ, with experts on climate change, human rights, environmental and social risks managements and gender policies.

In both Lebanon and Jordan government stakeholders responsible for compliance to national environmental and social policies and standards will be part of the Regional- and National-level Steering Committees, as well as government gender focal points.

All project-related ToR’s and contracts will include clauses stating contractors will need to comply to the AF ESP, especially principle 1 (law), 4 (human rights), 5 (gender) and 6 and 13 (labour and safety) and the AF GP.

Adaptive management: when changes in project activities or additional activities are required, these will need to go through a new risks screening and impact assessment process in compliance with AF, UN-habitat and national policies and standards. When this is required, this will be led by the RPSU and the Regional-level Project Steering Committee would need to approve the changes. For instance, when allocated budget allow targeted additional buildings for installing RWH systems, this would be possible following above process.

Launch of the project

At the launch of the project, UN-Habitat’s, together with UN-ESCWA will organize an inception workshop inviting members of the Regional-level Project Steering Committees, Excecution Partners and other key stakeholders. The project approach and the proposed outputs and outcomes of the project will be presented and discussed with the purpose to solicit feedback and inputs in a participatory manner. Comments and feedback will be incorporated in project frameworks and workplans. The Inception Workshop aims to:

- Enhance participants’ understanding of the project objectives and activities and take ownership of the project

- Discuss and confirm the organizational structure of the project, including roles and responsibilities

- Confirm / agree upon project monitoring framework and workplan

- Confirm / agree upon project risks management framework

- Discuss and agree upon project knowledge management framework and plan

- Confirm / agree upon the project Environmental and social Risks Management Plan

- Agree on the annual work plan for year one.

The inception workship will be organised within three months after signing the project agreement between the Adaptation Fund and UN-Habitat.

- Measures for financial and project risk management

Under guidance of the regional project manager, supported by the National Project coordinators, Monitoring Officers will monitor the status of financial and project management risks, including those measures required to avoid, minimise or mitigate these risks, throughout the project (please see also Section Part III.D).

The table below gives an overview of overall potential project management and financial risks, an assessment of the significance of the pertaining risks in terms of likelihood and impact and outlines measures that have been embedded in the project design in order to manage and/or mitigate these risks.

Table 22: overview of financial and management risks and measures to mitigate these

| Potential risks | Likelihood (1-5) | Impact (1-5) | Mitigation measures | Indicator to verify |
| --- | --- | --- | --- | --- |
| Institutional |  |  |  |  |
| 1 Delay of project start-up because critical staff is not in place and / or lengthy contracting process, incl. negotiations with execution entities | 3 Med | 3 Med | 1.1 UN-Habitat appointed critical staff at UN-H ROAS to start the process required to start the project, incl. putting project staff in place and preparing the inception workshop immediately after signed project agreement between UN-Habitat and the AF; 1.2 All execution entities have been identified and proposed project activities and budgets have already been agreed upon. 1.3. UN-habitat commits to organise the inception workshop within three months of the signed project agreement between UN-Habitat the AF | The inception workshop was organised within three months of the signed project agreement between UN-Habitat; Execution entities to execute activities in the 1st project year are contracted within six months after the inception workshop |
| 2 Loss of government support (at ministerial and municipal level) for the project and activities because of elections and related functions of the project steering committee, which may result in lack of prioritization of AF project activities or different pace of execution of activities in Jordan and Lebanon | 1 Low | 3 Med | 2.1 National Project Steering Committees (PSCs) have already been formed during the project preparation phase and these have approved proposed project activities and budgets, etc. This shows a participatory and inclusive project design process took place with ownership of the project as a result. If due to elections, new members of the PSCs will need to be selected, this will be requested by UN-Habitat and AF DA as soon as possible and records of decisions made during earlier PSC will be shared. 2.2 Delays in one country don’t have to result in delays in the other country because of functioning national PSCs 2.3 UN-Habitat will establish agreements with the MoE (with non-changing AF DA) (through MoUs) to ensure above | Confirming steering committee members and roles and responsibilities during inception workshop + report Government focal point to coordinate SC appointed at inception workshop MoU signed within 6 months six months after the inception workshop |
| 3 A lack of coordination between and within national government Ministries and Departments and municipalities | 1 Low | 3 Med | 3.1 Regional and National PSCs are to ensure coordination. Representatives from the target municipalities are members of both regional and national PSC. 3.2 Roles and responsibilities related to project implementation of PSC members, also for operation, maintenance and sustainability of activities, have already been identified and focal points within the ministries and municipalities will be appointed through an official letter. 3.3 Should UN-Habitat observe coordination problems, the agency will try to resolve issues directly with government focal point and / or concerned parties | See above |
| 4 Capacity constraints of executing entities, local institutions, communities and the private sector may limit the effective implementation of interventions | 1 Low | 3 Med | 4.1 The project has a strong capacity building and training component (component 2), designed to operate, maintain, sustain and replicate project activities, esp. at the community level 4.2 UN-Habitat will have dedicated project staff with expertise in spatial / urban planning, climate change, community organization and technical design, M&E and safeguards to ensure quality control from UN-Habitat side. | Capacity building indicators to be established Critical staff as mentioned being part of project staff |
| 5 Communities may not adopt activities during or after the AF project, including infrastructure maintenance | 2 Low | 4 High | 5.1 A strong participatory approach at the community level is used and will be used (component 2) during project implementation to ensure ownership and support of communities to the realised interventions in the targeted project areas. UN-Habitat works with UNICEF and NGOs partners already well established in the target area, to build on relations already established. 5.2 Capacity building and training of communities will be undertaken to improve their awareness and understanding of the benefits of the activities, including infrastructure operation and maintenance (component 2). | See above |
| Financial management and Requisite Institutional Capacity |  |  |  |  |
| 6 Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity or needed capacity | 2 Low | 2 Low | 6.1 Financial management arrangements have been defined during project preparation, including identification of all executing entities, which already agreed on the activities and budgets (see also 1.2. above); 6.2 UN-Habitat’s control framework, under the financial rules and regulations of the UN secretariat, will ensure documentation of clearly defined roles and responsibilities for management, internal auditors, the governing body, other personnel and demonstrates proof of payment / disbursement; In line with AF and UN-Habitat policies, audits will take place annually and / or for each contract of USD 500k. 6.3 Activity specific procurement will be managed by the executing entities as agreed through standard Agreements of Cooperation (with relevant conditions, incl. evidence of recognised procurement policies and procedures and specific terms and conditions for timely disbursement of funds for project activities while at the same time ensure provisions on good financial management, hence minimizing the risk of fund mismanagement or corruption). The RPMU has a certifying role (for key procurements / expenditures). | Timely audit reports (inception and yearly + following UN-H regulations) Timely evidence of recognised procurement policies and procedures provided by Execution Entities |
| 7 Inflation and instability of the national currency leading to budget issues and increased prices for infrastructure delivery | 3 Med | 1 Low | 7.1 All budgets will be in US$ 7.2 Include clauses in all contract, incl. with private sector, that they can’t increase the costs during the project duration. | All budgets in US$ Clauses in all contract, incl. with private sector, that they can’t increase the costs during the project duration. |
| Physical |  |  |  |  |
| 8 Political instability in the target localities inhibits movement and access to target areas | 1 Low | 4 High | 8.1 The selected project sites are labelled as being safe. However, UN-habitat will only let field work proceed if agreed with the UN security unit. 8.2 Execution entities will require having permanent field staff at project sites, recuing the need to travel 7.3 If target areas are not accessible, UN-Habitat and the proposed execution entities will identify alternative intervention locations and request approval from the SC and AF | Permanent field staff at project locations |
| Environmental |  |  |  |  |
| 9 Poor weather conditions (especially in winter) affect implementation of activities | 2 Low | 1 Low | 9.1 UN-habitat and the proposed execution entities have developed their work plan according to expected weather conditions and the majority of activities should be able to be carried out despite severe weather conditions as they are inside closed areas. If unexpected weather patterns occur, the proposed activities and work plan will be reviewed to make practical adaptations. | Work plans avoiding critical concrete works being planned in winter |

- Measures for environmental and social risks management

Part II.L of this proposal shows the outcome of the environmental and social risks screening and impacts assessment that has been conducted for this project to comply to the AF ESP and GP. Part II.I describes the consultation process conducted to support the development of this proposal, including for this project to comply to the AF ESP and GP. In annex 2 it shows what consultations have been conducted to identify potential environmental and social risks and impacts, including with key stakeholders such as UN agencies and beneficiary groups (i.e. potentially vulnerable groups, including women and youth). Part III.A describes the allocated roles and responsibilities for environmental and social risk management, including for the implement of the project ESMP. A designated budget for environmental and social risks management, including the implementation of the ESMP, has been included in part III.G. In Annex 3, all the details of the risks screening, impact assessment, ESMP, incl. the risks monitoring system and budget, are provided.

Based on the screening against the 15 AF principles, the project has been categorised as a “B” category project in terms of the environmental and social risks it poses.

According to the Jordan’s EIA Regulations, particularly the EIA By-Law No. 37 of the Year (2005), the project has been categorized as “Category III” project, which imply that the proposed interventions in Jordan have no considerable risks or adverse impacts, thus not requiring full EIAs. This is due to the fact that all of the construction activities and installations of proposed sub-projects are not substantial and will be constructed or installed in already built and operating facilities, such as fully-functioning WWTPs, which at the time of original construction have been subjected to MoEnv’s incumbent EIA regulations and supervision. However, although no impact assessments were required by national law, a full ESIA and ESMP report has been developed for the proposed project activities / outputs in Jordan, accompanied by a consultations report.

According to Lebanese decree 8633 MoE, 2012, Annex 1, the proposed project activities / outputs don’t required full EIAs, except the proposed constructed wetlands in Bar Elias, as this activity was  categorised as ‘category II’ sub-project, which imply that an initial screening was required, followed by an EIA. Similarly to Jordan, all of the construction activities and installations are not substantial and will be constructed or installed in already built and operating facilities, except the proposed wetlands, which will be constructed on public land selected by the government for this purpose. To comply to the AF requirements, risks screening and impact assessments have also been conducted for all proposed project activities.

Country specific ESIA-ESMP and consultation reports can be found here: https://unhabitat.org/af-lebanon-jordan

Table 23: ESP and GP compliance requirements and how the proposal complies to these requirements

| ESP and GP compliance requirements | Project compliance to the AF ESP and GP | Reference / evidence |
| --- | --- | --- |
| Have all potential environmental and social risks been identified for all project/programme activities prior to funding approval? | All potential environmental and social risks (incl. for gender and considering their significance) have been identified) for all project/programme activities at the project preparation phase. In both Jordan and Lebanon, accredited consultants prepared country-specific ESIAs, ESMPs and consultations reports in compliance with the AF ESP and GP and national requirements for conducting ESIAs; Outcomes have been consolidated in the proposal | Part II.I Part II.L Annex 3 (ESP annex) Annex 4 GP annex) |
| Has the environmental and social assessment been completed before the project/programme proposal submission to the Adaptation Fund, and its findings included in the proposal document? | In compliance with the AF ESP and GP and national requirements for conducting ESIAs, above reports have been reviewed and approved by the Jordan and Lebanon ministries of environment. Outcomes have been consolidated in the proposal. | https://unhabitat.org/af-lebanon-jordan |
| Has an ESMP been developed and does this include safeguard measures to be implemented during a project/programme? | A project ESMP has been developed, including safeguarding measures. The following has been included in the ESMP: - Allocated roles and responsibilities environmental and social risk management / implement of the ESMP - Opportunities for adaptive management - Arrangements to supervise executing entities for implementation of ESMP - Budget provision to manage environmental and social risks / implement of the ESMP - Measures to avoid, minimize, or mitigate potential risks - Risks monitoring system / indicators - Grievance mechanism | Part III.A (roles and responsibilities for env. and social risk management) Annex 3 (ESP annex) |
| Will a grievance mechanism be put in place and how will it be made widely known to identified and potentially affected parties | A project grievance mechanism will be put in place, as described in the ESMP. It will be made widely known to identified and potentially affected parties through community mobilisers, posters and online content | Annex 3 (ESP annex) |

- Arrangements for monitoring, reporting and evaluation

M & E Framework and plan

Monitoring and Evaluation (M & E) arrangements for this project will be in compliance with the AF M&E guidelines and ESP and GP and with UN-Habitat M & E policies and guidelines. This means, as a minimum, the following will be monitored and evaluated: project Milestones, Financial data, Procurement data, Risks assessment, ESP Compliance, GP Compliance, Project indicators, Lessons learned, project Results. The M & E of progress in achieving project results will be based on targets and indicators (also for gender) established in the Project Results Framework (see Part III.E).

The annual project performance reports (PPRs) will include a section on the status of implementation of any environmental and social management plan, including those measures required to avoid, minimize, or mitigate environmental and social risks. The reports shall also include, if necessary, a description of any corrective actions that are deemed necessary. The terminal evaluation report will include an evaluation of the project’s performance with respect to environmental and social risks.

UN-Habitat will ensure timely and high-quality M & E by keeping oversight of the process by providing guidance to the Project Execution Entities and national government partners through full briefing of M & E requirements. Where possible, the M & E process will be participatory, involving key stakeholders at national, municipal and communities. Project activities will be monitored by the RPSU and NPCUs with dedicated monitoring staff, which will require having expertise of M & E compliance to the AF ESP and GP. The M & E framework and plan will also need to be endorsed by the Regional-level Project Steering Committee. Audits of the project’s financial management will follow AF regulations and rules and applicable audit policies. The M&E plan will be implemented as proposed in the table below.

Table 24: M & E plan

| Type of M&E Activities | Responsible Parties | Time Frame | Reporting |
| --- | --- | --- | --- |
| Inception Workshop and Report | UN-Habitat ROAS & Regional project coordinator Coordinated with: UN-ESCWA Regional-level Steering Committee | Workshop: within first three months of signing between AF and UN-habitat Report: within one month after inception workshop | Inception Report, including 1st year workplan, monitoring framework and plan; project risks management framework and plan; environmental and social risks management framework and plan; knowledge management strategy |
| Periodic status/ progress reports | UN-Habitat ROAS & Regional project coordinator Coordinated with: NPCUs and Project EE and IOIS | Annually | Annual Report, mid-term, final |
| Compliance with ESP and GP |  | Annual, as well as upon receipt of complaints, grievances or queries | Annual Report, mid-term, final |
| Audits |  | As per AF (annually) | Audit Reports |
| Terminal project performance report |  | No later than one months after project completion | Terminal project performance report |
| Final Evaluation | UN-Habitat ROAS & Regional project coordinator Coordinated with: External consultants and NPCUs, Project EE | No later than three months after project completion | Final Evaluation Report |
| Community consultations / workshops / trainings, etc. | Project EE Coordinated with: NPCUs | Within one week after each event | Documentation |
| Visits to field sites | UN-ESCWA Coordinated with: UN-Habitat ROAS & Regional project coordinator Regional-level Steering Committee | At least every year | Field visit Report |
| Video with ‘before’ and ‘after’ the project | UN-Habitat ROAS & Regional project coordinator Coordinated with: UN-ESCWA Regional-level Steering Committee | Video one: before start of concrete interventions Video two: after completion concrete interventions | Video compilation of project results |

For the M & E budget and a breakdown of how MIE fees will be utilized in the supervision of the M & E function, please see the detailed budget (Part III.G). For related data, targets and indicators, please see the project proposal results framework (Part III.E).

M&E Activities

- Inception workshop and Project Steering Committee meetings

During the first Regional-level Project Steering Committee meeting, which will be organized in conjunction with the project Inception Workshop. The Committees will monitor / review project progress and provide technical guidance. During the first Regional-level Project Steering Committee meeting, the following will be reviewed: the project organizational structure, includes roles and responsibilities, the project monitoring framework and workplan, the project risks management framework, the project knowledge management framework and plan, the project Environmental and social Risks Management Plan and annual work plan for year one. The Regional-level Project Steering Committee will meet every year and the National Project Steering Committees will meet every six months, and ad-hoc meetings will be held as needed.

- Periodic project monitoring and terminal project performance reporting

Annual project performance monitoring will be conducted using the AF PPRs template. This will include monitoring of project: Milestones; Financial data; Procurement data; Risks assessment; ESP Compliance; GP Compliance; Project indicators; Lessons learned; Project Results

- ESMP implementation monitoring

The implementation of the project Environment and Social Management Plan (ESMP) as described in Annex x will be monitored. The ESMP includes monitoring indicators and responsibilities for identified potential risks, impacts and mitigation measures. A dedicated budget for monitoring the compliance to the AF ESP and GP has been included in Part III.G

- Financial Audits

A professional, certified and independent organization will review the financial management of the project and adherence to required standards and regulations.

- Final Evaluation

No later than three months after project completion, a final evaluation will be conducted following AF and UN-Habitat policies and guidelines. It will be conducted by an independent team of international and national experts in consultation with executing entities and national stakeholders as a participatory process.

- Community Level Participatory Monitoring

Part of the detailed project monitoring framework and plan will be identified through activities to involve Project Execution Entities and beneficiaries at the community level in monitoring activities. This would include community-level monitoring of Gender and Youth responsiveness and impact of the project.

- Periodic Project Site Visits

Members of the Regional-level Project Steering Committee and representatives of UN-Habitat will visit project sited and hold meetings with the local stakeholders to monitor the implementation of project activities.

- Video with ‘before’ and ‘after’ the project

Also, as part of the knowledge management strategy and plan, a video recording project results will be produced using ‘birds’ eye’ views and recording of project activities and beneficiaries

Reporting

- Inception Workshop and Report

Within one month after the inception workshop, an Inception Report will be submitted to the AF and project steering committees’ members. Reports will include: (i) agreement on organizational structure of the project, including roles and responsibilities; (ii) monitoring framework and workplan; (iii) project risks management framework; (iv) knowledge management framework and plan; (v) Environmental and social Risks Management Plan; (vi) year one work plan.

- Annual project performance reports, including final report

The Annual project performance reports, which will be submitted to the AF, will include:

- Milestones

- Financial data

- Procurement data

- Risks assessment

- ESP Compliance

- GP Compliance

- Project indicators

- Lessons learned

- Project Results

- Community Level Meeting /Workshop / Training Reports and site visit

Reports on all community-level meetings, workshops, and training will be prepared by Project Execution Entities within one week of the event. Photo documented site visit reports, also to monitor women participation, will also be prepared by Project Execution Entities.

- Final Evaluation Report

Independent consultant will prepare the Final Evaluation report in line with AF and UN-habitat evaluation policies and guidelines and norms and standards for evaluation in the UN system.

- Project proposal results framework

Table 25: Project results framework with indicators, their baseline, targets, risks & assumptions and verification means. *Beneficiaries T = Total; F = Female; Y = Youth.

| Expected Result | Indicators | Baseline data | Targets | Risks & assumptions |  | Data collection method | Frequency |  | Responsibility |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project component 1: Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from DPs migration |  |  |  |  |  |  |  |  |  |
| Outcome 1.1.1. Strengthened municipal institutional capacity to manage climate change and DP crisis related urban water scarcity challenges by mainstreaming these aspects into spatial strategies + developing action / investment plans and guidelines (with identified solutions) to use water most efficiently within municipal boundaries *In line with AF outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | No and type of targeted institutions with strategies / guidelines and urban master plans with climate change and gender mainstreamed. - Number of strategies / guidelines (district-national level) - Number of urban master plans in Lebanon - Number of urban master plans in Jordan | 0 0 1 (outdated) | 3 8 2 | Calculate number of strategies / guidelines and urban master plans Assess if climate change and gender are mainstreamed in strategies and plans and ensure criteria to do so are clear |  | Collect the guidelines / strategies and plans and data from government staff involved in assessment, planning and management of the plans | Baseline, mid-term and end |  | UN-H in cooperation with EE and government entities |
| Output 1.1. Territorial planning and development strategy / guidelines with CC and gender mainstreamed in Lebanon *In line with AF output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events | No. of staff and population directly involved in assessment and planning processes through workshops/trainings - Number of staff / people - Women participating - Youth participating | 0 0 0 | T: 480 W: >40 % Y: >15 % | Calculate number of staff from target institutions participating workshops/trainings |  | Workshop/training reports Participation lists and photos | Baseline, mid-term and end |  | UN-H in cooperation with EE and government |
| Output 1.2. Urban master plans at municipal level with CC and gender mainstreamed in Lebanon *In line with AF output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events | No. of staff and population directly involved in assessment and planning processes through workshops/trainings - Number of staff / people - Women participating - Youth participating | 0 0 0 | T: 240 W: >40 % Y: >15 % |  |  |  |  |  |  |
| Output 1.3. Urban master plans at municipal level with CC and gender mainstreamed in Lebanon *In line with AF output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events | No. of staff and population directly involved in assessment and planning processes through workshops/trainings - Number of staff / people - Women participating - Youth participating | 0 0 0 | T: 450 W: >40 % Y: >15 % |  |  |  |  |  |  |
| Component 2: Increasing the resilience of citizens (DPs and host communities): Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems |  |  |  |  |  |  |  |  |  |
| Outcome 2.1.1. Strengthened DPs and host community awareness and ownership of climate change adaptation measures + capacities strengthened to operate, maintain and replicate proposed adaptation measures, including skills building *In line with AF outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level *In line with AF outcome 8: support the development and diffusion of innovative adaptation practices, tools and technologies | Percentage of targeted direct population aware of adaptation measures being implemented - Women participating - Youth participating Technologies replication and upscaling plans | 0 0 0 0 0 | Mid-term: 30 % End: 50 % W: >40 % Y: >15 % 8 for each output) | Engagement of target direct population in awareness raising activities and O & M plans development Count the number of replication and upscaling plans | Surveys: use scale from 1 to 5 to summarize findings of analysis Replication and upscaling plans |  |  | Baseline, mid-term and end | UN-H in cooperation with EE and government |
| Output 2.1. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.1: Rooftop rainwater harvesting in Lebanon *In line with AF Output 3.2: strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning (also applies to below outputs) | No. of O & M plans and staff and population directly involved with development of these plans - Total staff / population: - Women participating - Youth participating | 0 0 0 0 | 20 system O & M plans; T: 80 (4/system) W: >40 % Y: >15 % | Ensure criteria of O & M plans are clear | O & M plans Workshop/training participation lists and photos |  |  | Baseline, mid-term and end | UN-H in cooperation with EE and government |
| Output 2.2. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.2: Rooftop rainwater harvesting in Jordan | No. of O & M plans and staff and population directly involved with development of these plans - Total staff / population: - Women participating - Youth participating | 0 0 0 0 | 86 system O & M plans; T: 344 (4/system) W: >40 % Y: >15 % |  |  |  |  |  |  |
| Output 2.3. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.3: Greywater treatment and reuse in Jordan | No. of O & M plans and staff and population directly involved with development of these plans - Total staff / population: - Women participating - Youth participating | 0 0 0 0 | 40 system O & M plans T: 120 (4/system) W: >40 % Y: >15 % |  |  |  |  |  |  |
| Output 2.4. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.4: Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon | No. of O & M plans and staff and population directly involved with development of these plans - Total staff / population: - Women participating - Youth participating | 0 0 0 0 | 2 systems (Zahle and Wetlands O & M plans T: 200 (100/syst) W: >40 % Y: >15 % |  |  |  |  |  |  |
| Output 2.5. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.5: Efficient treatment and reuse of wastewater in Jordan | No. of O & M plans and staff directly involved with development of these plans - Total staff: - Women participating - Youth participating | 0 0 0 0 | 3 systems (WWTPs) O & M plans; T: 15 (5/system) W: >40 % Y: >15 % |  |  |  |  |  |  |
| Output 2.6 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.6 Water-use-efficient irrigation of treated wastewater in Lebanon | No. of O & M plans and staff and population directly involved with development of these plans - Total staff: - Women participating - Youth participating | 0 0 0 0 | O & M plans for 150 ha farmland T: 150 (1/ha) W: >40 % Y: >15 % |  |  |  |  |  |  |
| Output 2.7. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7: Water-use-efficient irrigation of treated wastewater in Lebanon | No. of O & M plans and staff and population directly involved with development of these plans - Total staff: - Women participating - Youth participating | 0 0 0 0 | O & M plans for 220 dunum farmland T: 44 (2/dunum W: >40 % Y: >15 % |  |  |  |  |  |  |
| Output 2.8. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.8: permaculture demonstration | No. of students completed permaculture curriculum - Total students - Women | 0 0 | T: 200 W: >50 % | Calculate number of students which completed the curriculum | Certificates and / or plans developed by students |  |  | Baseline, mid-term and end | UN-H in cooperation with EE and government |
| Component 3: Increasing the adaptive capacity of the water sector: Expand unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context |  |  |  |  |  |  |  |  |  |
| Outcome 3 *In Line with AF outcome 4: Increased adaptive capacity within relevant development and natural resource sectors and *In Line with AF outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas *In line with AF outcome 8: support the development and diffusion of innovative adaptation practices, tools and technologies | See outputs Ha of farmland with more sustained climate-resilient livelihoods – see outputs Innovative techniques / interventions – see outputs | See outputs |  |  |  |  |  |  |  |
| Output 3.1. Rooftop rainwater harvesting in Lebanon *In line with AF output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Number of RWH systems installed | 0 | 86 (of which 18 rehabilitated) | System must be functional, effective and satisfactory of users | Photos of systems Assess effectiveness (water harvested) and satisfactory through measurements and surveys |  |  | Baseline, mid-term and end | UN-H in cooperation with EE and government |
| Output 3.2. Rooftop rainwater harvesting in Jordan *In line with AF output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Number of RWH systems installed | 0 | 20 |  |  |  |  |  |  |
| Output 3.3. Greywater treatment and reuse in Jordan *In line with AF Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Number of GWTR systems installed | 0 | 40 |  |  |  |  |  |  |
| Output 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon *In line with AF output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Irrigation channels (1x1 meters with 0.25m thick walls) constructed (in meters) 18000 m3 water flow through channel from Zahle WWTP Construction of 60,000 sqm of Free Water Surface (FWS) Wetlands 6000 m3 of tributary water quality water | 0 Baseline quality 0 Baseline quality | 3000 meters Compliant to standard 18000 m3 60000 m2 Compliant to standard 6000 m3 | Channel must be able to support 18000 m3 and comply to standards Check / assess earthworks, berms, plants, piping, pump and structures and quantity and quality of water | Quantity and quality water and channel Map / coordinates and photos Identify any visual construction weaknesses Map / coordinates and photos Quantity and quality treated |  |  |  |  |
| Output 3.5. Efficient treatment and reuse of wastewater in Jordan *In line with AF output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Water storage constructed / installed Water quality | 0 Baseline quality | 1x3000 m3 1x2000 m3 Compliant to standard | Storage must be irrigatable and quality compliant to standards | Quantity and quality water and storage tanks - map / coordinates and photos |  |  |  |  |
| Output 3.6. Water-use-efficient irrigation of treated wastewater in Lebanon *In line with AF output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability *In Line with AF output 6 No and type of adaptation assets created or strengthened in support of individual or community livelihood strategies *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Treated and channeled water from Zahle WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods Treated and channeled water from Bar Elias Wetlands irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods | 0 0 | 110 ha 40 ha | Calculate ha of farmlands being irrigated by treated wastewater Calculate number of ponds | Map / coordinates and photos |  |  |  |  |
| Output 3.7 Water-use-efficient irrigation of treated wastewater in Jordan *In line with AF output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability *In Line with AF output 6 No and type of adaptation assets created or strengthened in support of individual or community livelihood strategies *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Conveyor irrigation pipeline 6’ size installed (in meters) Treated and stored channeled water from Maered WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods Treated and stored channeled water from Al Kaider WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods Treated and channeled water from Mafraq WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods Treated and channeled water from small ponds and thus sustaining climate-resilience of agriculture livelihoods | 0 0 0 0 0 | 4000 60 dunum 60 dunum 100 dunum 15 ponds |  |  |  |  |  |  |
| 3.8. Permaculture demonstration *In line with AF output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Permaculture demonstration site established, including: - Biofertilizer site - Crop garden and compost egg laying chickens (30 chickens) - Beehives - Compost sub-od worm farms - Olive trees (Orchard Monoculture Conversion to Food Forest) | 0 0 0 0 0 | 1 30 chickens 3 5 180 | Calculate numbers Assess effectiveness of reducing water use | Map / coordinates and photos Assess reduction water use (soil moist) |  |  |  |  |
| Component 4: Improving knowledge and policies and regulations to increase urban resilience in the region: Project KM and replication, incl. development of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration) |  |  |  |  |  |  |  |  |  |
| Outcome 4.1.1. Strengthened (inter)National institutional capacity to manage climate change and DP crisis related urban water scarcity challenges, including lessons learned collected and shared regionally *In line with AF outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level *In line with AF outcome 8: support the development and diffusion of innovative adaptation practices, tools and technologies | See below outputs |  |  |  |  |  |  |  |  |
| Output 4.1. Regional / international KM with focus on sharing project lessons and replication *In line with AF Output 3.2: strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Number of international meetings organised to exchange project knowledge / lessons learned Project video developed and shared with relevant stakeholders | 0 0 | 8 1 | Regional steering committee meeting and other international events organised to exchange knowledge To project interventions | Identify number of meetings and purpose Photos and agenda Video online Photos and attendance sheets |  |  | Baseline, mid-term and end | UN-Habitat |
| Output 4.2. Jordan and Lebanon KM with focus on project progress, best practices and lessons learned *In line with AF Output 3.2: strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Number of international meetings organised to exchange project knowledge / lessons learned with focus on innovative approaches and techniques and replication options Project field visits by regional steering committee members and / or other key project stakeholders | 0 0 | 8 7 |  |  |  |  |  |  |
| Output 4.3. Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities *In line with AF Output 3.2: strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Regional’ urban risks and vulnerabilities assessment, planning and management approach model developed and shared | 0 | 1 | Including planning approach, best practices, etc. | Online and presented |  |  | 4th year | UN-H in cooperation with EE and government |
| Output 4.4. Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities *In line with AF Output 3.2: strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning *In line with AF output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities developed/published and shared | 0 | 1 | With a focus on Jordan |  |  |  |  |  |

Table 26 Indicative Core Indicator Targets

| Impact-level results | Core indicator | Disaggregated data and targets | Comment |
| --- | --- | --- | --- |
| Increased adaptive capacity of communities to respond to the impacts of climate change | Number of beneficiaries Component 1 | Total: 930 Women:>40 % Youth: >15 % | Direct beneficiary numbers in overview table 6 include all project activities, while those in the results framworks focus on specific activities such as O & M. Indirect beneficiaries, see also project overview table 6 |
|  | Number of beneficiaries Component 2 | Total:113,860 Women:78,724 (69%) Youth: 38870 (34 %) Syrian: 47805 (41 %) |  |
|  | Number of beneficiaries Component 3 | Total: 119,421 Women: 81,883 (69%) Youth: 38989 (33 %) Syrian: 51038 (42 %) |  |
|  | Number of beneficiaries Component 4 | T: 600 W:>40 % Y: >15 % |  |
|  | Assets produced, developed, improved, or strengthened - RWH systems - GWRT systems - 3km irrigation channel - Zahle WWTP treated water irrigated through channel - Wetlands constructed - Water storage constructed / installed - Modern / water efficient irrigations systems - Permaculture demonstration site | 106 40 1 1 (18000 m3 of water) 1 (60,000 m3 with 6000 m3 water flow 2 (1x2000 m and 1x3000 m3) 5 (one covering 110 ha; one covering 40 ha; 2 covering 60 dunum; 1 covering 100 dunum) 1 | All ‘concrete’ adaptation activities are designed to increase climate change-related water scarcity resiliece |
|  | Increased income, or avoided decrease in income | See ha of farmland being more water stress resilient, thus sustaining resilient agriculture livelihoods | The ‘concrete’ adaptation activities related to the WWTPs and irrigation interventions are designed to support increased resilience of the agriculture livelihoods |

Methodology to apply: https://www.adaptation-fund.org/wp-content/uploads/2016/04/AF-Core-Indicator-Methodologies.pdf

- Project alignment with the Adaptation Fund results framework

Table 27: Project alignment with the Adaptation Fund results framework

| Project Outcome | Project Outcome Indicator | Fund Outcome | Fund Outcome Indicator | Grant Amount (USD) |
| --- | --- | --- | --- | --- |
| Outcome 1.1.1. Strengthened municipal institutional capacity to manage climate change and DP crisis related urban water scarcity challenges by mainstreaming these aspects into spatial strategies + developing action / investment plans and guidelines (with identified solutions) to use water most efficiently within municipal boundaries | No and type of targeted institutions with strategies / guidelines and urban master plans with climate change and gender mainstreamed. - Number of strategies / guidelines (district-national level) - Number of urban master plans in Lebanon - Number of urban master plans in Jordan | Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | 2.1. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | 931,000 |
| Outcome 2.1.1. Strengthened DPs and host community awareness and ownership of CC adaptation measures + capacities strengthened to operate, maintain and replicate proposed adaptation measures | Percentage of targeted direct population aware of adaptation measures being implemented - Women participating - Youth participating | Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level | 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses | 1,733,200 |
|  | Technologies replication and upscaling plans | Outcome 8: support the development and diffusion of innovative adaptation practices, tools and technologies | 8. Innovations adaptation practices are rolled-out, scaled up, encouraged and / or accelerated at regional, national and / or subnational level |  |
| Outcome 3.1.1. Increased adaptive capacity within the water sector through resilient and sustainable water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context and benefitting vulnerable groups | See outputs | Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors | 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress | 8,048,227 |
|  | See outputs | Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | 6.1 Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods |  |
| Outcome 4.1.1. Strengthened (inter)National institutional capacity to manage climate change and DP crisis related urban water scarcity challenges, including lessons learned collected and shared regionally | See outputs | Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level | 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses | 888,162 |
|  | Technologies replication and upscaling plans | Outcome 8: support the development and diffusion of innovative adaptation practices, tools and technologies | 8. Innovations adaptation practices are rolled-out, scaled up, encouraged and / or accelerated at regional, national and / or subnational level |  |
| Project Output | Project Output Indicator | Fund Output | Fund Output Indicator | Grant Amount (USD) |
| Output 1.1. Territorial planning and development strategy / guidelines with CC and gender mainstreamed in Lebanon | No. of staff and population directly involved in assessment and planning processes through workshops/trainings - Number of staff / people - Women participating - Youth participating | Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events | 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events | 249,000 |
| Output 1.2. Urban master plans at municipal level with CC and gender mainstreamed in Lebanon |  |  |  | 366,000 |
| Output 1.3. Urban master plans at municipal level with CC and gender mainstreamed in Jordan |  |  |  | 366,000 |
| Output 2.1, 2.2. 2.3. 2.4. 2.5. 2.6. 2.7. 2.8 Strengthened DPs and host community awareness and ownership of climate change adaptation measures + capacities strengthened to operate, maintain and replicate proposed adaptation measures | No. of O & M plans and staff and population directly involved with development of these plans - Total staff / population: - Women participating - Youth participating | Output 3.2 Strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | 3.2.2 No of tools and guidelines developed and shared with relevant stakeholders | 350,000 Approx - see details in budget notes) |
|  | No. of students completed permaculture curriculum - Total students - Women |  |  | 170,000 |
| Output 3.1. Rooftop rainwater harvesting in Lebanon | Number of RWH systems installed | Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | 4.1.2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change 6.1. No and type of adaptation assets created or strengthened in support of individual or community livelihood strategies 8.1 No of innovative adaptation practices, tools and technologies accelerated, scaled-up and / or replicated | 8,048,227 |
| Output 3.2. Rooftop rainwater harvesting in Jordan | Number of RWH systems installed |  |  |  |
| Output 3.3. Greywater treatment and reuse in Jordan | Number of GWTR systems installed |  |  |  |
| Output 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon | Irrigation channels (1x1 meters with 0.25m thick walls) constructed (in meters) 18000 m3 water flow through channel from Zahle WWTP Construction of 60,000 sqm of Free Water Surface (FWS) Wetlands 6000 m3 of tributary water quality water |  |  |  |
| Output 3.5. Efficient treatment and reuse of wastewater in Jordan | Water storage constructed / installed Water quality |  |  |  |
| Output 3.6. Water-use-efficient irrigation of treated wastewater in Lebanon | Treated and channeled water from Zahle WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods; Treated and channeled water from Bar Elias Wetlands irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods |  |  |  |
| Output 3.7 Water-use-efficient irrigation of treated wastewater in Jordan | Conveyor irrigation pipeline 6’ size installed (in meters) Treated and stored channeled water from Maered WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods; Treated and stored channeled water from Al Kaider WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods; Treated and channeled water from Mafraq WWTP irrigating farmland (ha) and thus sustaining climate-resilience of agriculture livelihoods Treated and channeled water from small ponds and thus sustaining climate-resilience of agriculture livelihoods |  |  |  |
| Output 3.8. Permaculture demonstration | Permaculture demonstration site established, including: - Biofertilizer site - Crop garden and compost egg laying chickens (30 chickens) - Beehives - Compost sub-od worm farms Olive trees (Orchard Monoculture Conversion to Food Forest) |  |  |  |
| Output 4.1. Regional / international KM with focus on sharing project lessons and replication | Number of international meetings organised to exchange project knowledge / lessons learned; Project video developed and shared with relevant stakeholders | Output 3.2 Strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning Output 8: Viable innovations are rolled-out scaled up, encouraged and / or accelerated | 3.2.2 No of tools and guidelines developed and shared with relevant stakeholders 8.1 No of innovative adaptation practices, tools and technologies accelerated, scaled-up and / or replicated | 888,162 |
| Output 4.2. Jordan and Lebanon KM with focus on project progress, best practices and lessons learned | Number of international meetings organised to exchange project knowledge / lessons learned with focus on innovative approaches and techniques and replication options; Project field visits by regional steering committee members and / or other key project stakeholders |  |  |  |
| Output 4.3. Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities | Regional’ urban risks and vulnerabilities assessment, planning and management approach model developed and shared |  |  |  |
| Output 4.4. Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities | Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities developed/published and shared |  |  |  |

- Detailed budget

Table 28 Detailed Budget. For all budget notes, see annex 6

| Project Components | Expected Concrete Outputs | Expected Concrete Outcomes | TOTAL | Year | Year | Year | Year | % total | % comp |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 |  |  |
|  |  |  |  | 12 m | 12 m | 12 m | 12 m |  |  |
| Component 1 Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, including DPs migration trends | Output 1.1. Territorial planning and development strategy / guidelines with CC and gender mainstreamed in Lebanon | Outcome 1.1 Strenghten municipal institutional capacity to manage climate change and DP crisis related urban water scarcity challenges by mainstreaming these aspects into spatial strategies + developing action / investment plans and guidelines (with identified solutions) to use water most efficiently within municipal boundaries | 249,000 | 249,000 | - | - | - | 1.8% |  |
|  | Output 1.2. Urban master plans at municipal level with CC and gender mainstreamed in Lebanon |  | 366,000 | 173,000 | 193,000 | - | - | 2.6% |  |
|  | Output 1.3. Urban master plans at municipal level with CC and gender mainstreamed in Jordan |  | 366,000 | 173,000 | 193,000 | - | - | 2.6% |  |
|  | TOTAL |  | 981,000 | 595,000 | 386,000 | - | - | 7.0% | 8.4% |
| Component 2 Improve awareness, ownership and capacities to respond to climate change impacts, incl, to operate, maintain and replicate resilient water harvesting, supply and irrigation systems | Output 2.1. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.1 | Outcome 2.1 Strengthened DPs and host communities awareness and ownership of CC adaptation measures + capacities strengthened to operate and maintain proposed adaptation measures, including skills building | 177,400 | 28,200 | 47,500 | 50,500 | 51,200 | 1.3% |  |
|  | Output 2.2. See above for output 3.2. |  | 139,200 | 31,200 | 43,500 | 46,500 | 18,000 | 1.0% |  |
|  | Output 2.3. See above for output 3.3. |  | 234,000 | 36,000 | 82,000 | 82,000 | 34,000 | 1.7% |  |
|  | Output 2.4. See above for output 3.4. |  | 316,300 | 132,300 | 48,400 | 89,900 | 45,700 | 2.3% |  |
|  | Output 2.5. See above for output 3.5. |  | 16,000 | - | - | 6,000 | 10,000 | 0.1% |  |
|  | Output 2.6. See above for output 3.6. |  | 276,700 | 73,900 | 50,100 | 122,100 | 30,600 | 2.0% |  |
|  | Output 2.7. See above for output 3.7. |  | 259,000 | 90,400 | 83,800 | 32,400 | 52,400 | 1.9% |  |
|  | Output 2.8. See above for output 3.8. |  | 314,600 | 113,000 | 66,200 | 65,200 | 70,200 | 2.3% |  |
|  | TOTAL |  | 1,733,200 | 505,000 | 421,500 | 494,600 | 312,100 | 12.4% | 14.9% |
| Component 3 Expand climate change resilient (unconventional) water harvesting and supply options, using innovative, low-cost and replicable techniques | Output 3.1. Rooftop rainwater harvesting in Lebanon | Outcome 3.1 Increased adaptive capacity within the water sector through resilient and sustainable water harvesting, supply and irrigation options, using innovative and cost-effective techniques suitable for the context and replicable and benefitting vulnerable groups | 867,262 | 11,364 | 400,767 | 443,767 | 11,364 | 6.2% |  |
|  | Output 3.2. Rooftop rainwater harvesting in Jordan |  | 820,820 | 5,000 | 455,410 | 355,410 | 5,000 | 5.9% |  |
|  | Output 3.3. Greywater treatment and reuse in Jordan |  | 843,112 | 11,364 | 410,192 | 410,192 | 11,364 | 6.0% |  |
|  | Output 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon |  | 1,996,955 | 52,333 | 1,781,728 | 155,892 | 7,002 | 14.3% |  |
|  | Output 3.5. Efficient treatment and reuse of wastewater in Jordan |  | 1,053,332 | - | 1,053,332 | - | - | 7.5% |  |
|  | Output 3.6. Water-use-efficient irrigation of treated wastewater in Lebanon |  | 1,278,300 | 5,808 | 1,259,424 | 8,712 | 4,356 | 9.2% |  |
|  | Output 3.7. Water-use Efficient irrigation of treated wastewater in Jordan |  | 804,400 | 10,800 | 780,400 | 6,600 | 6,600 | 5.8% |  |
|  | Output 3.8. Permaculture demonstration - efficient water use system |  | 384,046 | 210,289 | 57,919 | 57,919 | 57,919 | 2.7% |  |
|  | TOTAL |  | 8,048,227 | 306,958 | 6,199,172 | 1,438,492 | 103,605 | 57.6% | 69.1% |
| Component 4 Project Knowledge management and replication and development of regional urban risks and vulnerabilities management approach model | Output 4.1. Regional / international KM with focus on sharing project lessons and replication | Outcome 4.1 Strengthened (inter)National institutional capacity to manage climate change and DP crisis related urban water scarcity challenges, including lessons learned collected and shared regionally | 270,000 | 45,000 | 35,000 | 85,000 | 105,000 | 1.9% |  |
|  | Output 4.2. Jordan and Lebanon KM with focus on project progress, best practices and lessons learned |  | 433,800 | 110,620 | 105,280 | 94,180 | 123,720 | 3.1% |  |
|  | Output 4.3. Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities |  | 144,000 | - | 68,000 | 20,000 | 56,000 | 1.0% |  |
|  | Output 4.4. Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities |  | 40,362 | - | - | 36,000 | 4,362 | 0.3% |  |
|  | TOTAL |  | 888,162 | 155,620 | 208,280 | 235,180 | 289,082 | 6.4% | 7.6% |
| Sub-total Project Components Costs |  |  | 11,650,589 | 1,562,578 | 7,214,952 | 2,168,272 | 704,787 | 83.4% |  |
| Project Execution Costs | Regional Project coordination |  | 264,000 | 66,000 | 66,000 | 66,000 | 66,000 |  |  |
|  | National Project execution |  | 805,100 | 222,900 | 208,400 | 186,900 | 186,900 |  |  |
|  | Travel Related to Execution |  | 42,172 | 10,543 | 10,543 | 10,543 | 10,543 |  |  |
|  | Operations |  | 82,000 | 16,000 | 16,000 | 16,000 | 34,000 |  |  |
|  | Terminal evaluation |  | 30,000 | - | - | - | 30,000 |  |  |
| Sub-total Project Execution Costs |  | 9.50% | 1,223,272 | 315,443 | 300,943 | 279,443 | 327,443 | 8.8% |  |
| SUB-TOTAL Component + execution fee |  |  | 12,873,861 | 1,878,021 | 7,515,895 | 2,447,715 | 1,032,230 | 92.2% |  |
| Project Cycle Management Fee | UN-H ROAS Project Support Costs: AF and UN-H policies compliance Progress / evaluation Travel | 1.50% | 193,108 | 28,170 | 112,738 | 36,716 | 15,483 |  |  |
|  | UN-H HQ Project Support Costs: Overall project supervision, incl. compliance to UN-H policies and standards (gender, human rights, climate change, etc.) | 7.00% | 901,170 | 131,461 | 526,113 | 171,340 | 72,256 |  |  |
| Sub-total Project Cycle Managament Fee |  | 8.50% | 1,094,278 | 159,632 | 638,851 | 208,056 | 87,740 | 7.8% |  |
| Amount of Financing Requested |  |  | 13,968,139 | 2,037,653 | 8,154,746 | 2,655,771 | 1,119,970 | 100.0% |  |

Table 29: M & E budget

| Type of M & E Activity | Activity | Entity | Total | 1 | 2 | 3 | 4 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Measurements of means of verification (baseline assessment and M & E plans) as part of inception | Workshop | UN-ESCWA | 20,000 | 20,000 |  |  |  |
|  | Reports preparation and EE compliance to AF ESP and GP | UN-H ROAS | 23,475 | 23,475 |  |  |  |
| Direct Project Monitoring and Quality Assurance including annual progress and financial reporting, project revisions, technical assistance and ESP and GP compliance (from execution fee M & E and safeguards) | M & E UN-H offices | UN-H National offcies | 105,000 | 26,250 | 26,250 | 26,250 | 26,250 |
| Overall project monitoring and evaluation (from cycle management fee) |  | UN-H ROAS | 32,185 | 4,695 | 18,790 | 6,119 | 2,581 |
| Audits | In line with AF requirements | OIOS | - | - | - | - | - |
| Terminal external evaluation |  | Independent | 30,000 |  |  |  | 30,000 |
| Total |  |  | 210,660 | 74,420 | 45,040 | 32,369 | 58,831 |
| From Project Execution fee |  |  | 105,000 | 26,250 | 26,250 | 26,250 | 26,250 |
| From Project Cycle Management fee |  |  | 55,660 | 28,170 | 18,790 | 6,119 | 2,581 |

- Disbursement schedule

Table 30 Disbursement schedule

|  | Year 1 | Year 2 | Year 3 | Year 4 |
| --- | --- | --- | --- | --- |
| Schedule | 1st disbursement – | 2nd disbursement – One Year after project inception | 3rd disbursement - Two years after project inception | 4th disbursement – Three years after project inception |
| Milestones | Milestones - Upon agreement signature | Milestones (by end of year): - Upon First Annual Report - Upon financial report indicating disbursement of at least 70% of funds of 1st year | Milestones (by end of year) - Upon Second Annual Report - Upon financial report indicating disbursement of at least 70% of funds of 2nd year | Milestones (by end of year) - Upon Third Annual Report - Upon financial report indicating disbursement of at least 70% of funds of 3rd year |

| Schedule date | Upon Signing | One Year after project inception | Two years after project inception | Three years after project inception |
| --- | --- | --- | --- | --- |
| A. Project Funds (US$) | 1,562,578 | 7,214,952 | 2,168,272 | 704,787 |
| B. Programme Execution (US$) | 315,443 | 300,943 | 279,443 | 327,443 |
| C. Programme Cycle Mgt (US$) | 159,632 | 638,851 | 208,056 | 87,740 |
| TOTAL (US$) | 2,037,653 | 8,154,746 | 2,655,771 | 1,119,970 |

part iV: endorsement by governmentS and certification by the Implementing Entity

- Record of endorsement on behalf of the government

| Nayef Hmeidi Al-Fayez, Minister, Ministry of Environment, Jordan | Date: August 5, 2018 |
| --- | --- |
| Tarek El Khatib, Minister, Ministry of Environment, Lebanon | Date: August 6, 2018 |

B.   Implementing Entity certification

ANNEX 1: Refugee crisis statistics and project alignment with 3RP (regional refugee and resilience plan)

Below figures show a need for funding for increasing the resilience of DPs / refugees, including for the WASH sector, which will be impacted by climate change, especially in Jordan and Lebanon. It also show the current numbers of refugees registered, those between 2013-2020 and the geographical location (which shows most are in the project target locations).

Figure 16: 3RP Regional strategic overview

DPs in Lebanon

Total Persons of Concern: 918,974

Registered

DPs in Jordan

Total Persons of Concern : 654,192

ANNEX 2: Project activities visualisation and target area maps

Figure 17: Needs and proposed concrete interventions in Zahle and surrounding municipalities

Figure 18: Schematic detail section of the Rainwater harvesting systems proposed for public buildings in the Bekaa area

Figure 19: Map showing the reuse of the Zahle Wastewater Treatment Plant (ZWWTP) effluent for irrigation through the installment of a new open concrete irrigation canal

Figure 20: Schematic detail drawing of the proposed open concrete irrigation canal of the ZWWTP

Figure 21:  Map showing the location of the Bar Elias Constructed Wetland. The agriculture land shown in target area belongs to LRA (government), but agriculture practices stopped because of water challenges

Figure 22: Schematic detail drawings of the proposed Bar Elias Constructed Wetland

Figure 23: Water-efficient irrigation: schematic detail drawing introducing drip irrigation for potato plantations instead of the existing mini-sprinklers in Bar Elias

Figure 24: Water-efficient irrigation: schematic detail drawing introducing drip irrigation for fruit trees and vineyards instead of the existing surface irrigation in Zahle

Figure 25: Proposed concrete interventions (component 3) in Jordan (Irbid, Mafraq and Jerash Governorates)

Figure 26: Proposed concrete interventions (component 3) (Irbid Zoom-in)

Figure 27: Proposed concrete interventions (component 3) (Mafraq Zoom-in)

Figure 28: Schematic detailed drawing of rainwater harvesting systems proposed for schools/mosques/municipal buildings/residential buildings in Jordan

Figure 29: Greywater treatment and reuse: schematic detail section for greywater treatment and reuse system in schools and mosques

Figure 30: Location maps for three existing WWTP in Jordan to be upgraded

Figure 31: Water-efficient irrigation: schematic detail drawing introducing drip irrigation for farms in Mafraq and Jerash instead of the existing surface irrigation

Figure 32: Permaculture demonstration site within JUST university campus in Ramtha, Irbid

Figure 33: Permaculture demonstration site

ANNEX 3: Consultation outcomes, incl. for ESP and GP compliance

Table 31: Consultations conducted specifically to comply to AF ESP and GP

| Environmental and social principles | Required to comply to AF ESP and GP | Consulted | AF ESP and GP compliance |
| --- | --- | --- | --- |
| Compliance with the Law | - Identify relevant rules, regulations and standards, including procedures to comply to these for proposed interventions - Identify national legal framework and guidelines for conducting EIAs for relevant projects | Ministry of Environment (Leb) Ministry of Energy and Water (MoEW - Leb) Litany River Authorities (LRA – Under the Lebanese MoEW Leb) Lebanese Agricutlture Research Institute (LARI – Affiliated to the Lebanese Ministry of Agriculture (MoA)) Council for Development and Reconstruction (Leb) Ministry of Environment (Jord) Ministry of Water and Irrigation (Jord) The Ministry of Awqaf Islamic Affairs and Holy Places (Jord) Ministry of Education (Jord) | Relevant laws and how to comply have been identified (see section II.F) |
| Access and Equity | - Identify needs and potential issues and concerns related to proposed project actions | Beneficiary groups, including women, youth, Syrians and farmers | Detailed stakeholder mapping has been conducted Consultations with vulnerable groups have been conducted |
| Marginalized and Vulnerable Groups |  | UNHCR; Beneficiary groups, including women, youth, Syrians and farmers | Detailed stakeholder mapping has been conducted Consultations with vulnerable groups have been conducted UNCHR has been consulted to understand specific needs and possible concerns of DPs |
| Human Rights |  | OHCHR; Beneficiary groups, including women, youth, Syrians and farmers | Detailed stakeholder mapping has been conducted Consultations with vulnerable groups have been conducted UN-Habitat checked what core human rights have been ratified; OHCHR has been consulted to identify possible project human rights risks |
| Gender Equity and Women’s Empowerment |  | UNICEF; UN Women; Beneficiary groups, including women, youth, Syrians and farmers | Detailed stakeholder mapping has been conducted Consultations with vulnerable groups have been conducted UN Women and UNICEF have been consulted to understand specific needs and possible concerns of DPs. A gender baseline and approach has been developed |
| Core Labour Rights |  | ILO; Beneficiary groups, including women, youth, Syrians and farmers | Consultations with vulnerable groups have been conducted UN-Habitat checked what core Labour rights have been ratified; ILO has been consulted to identify possible risks of non-compliance to Core Labour Rights |
| Indigenous Peoples |  | Detailed stakeholder mapping has been conducted | Some Bedouins are now official Lebanese and Jordanians |
| Involuntary Resettlement |  | Municipalities; Beneficiary groups, including women, youth, Syrians and farmers | Resettlement will be avoided in all cases. All proposed activities are on public land or at building level where management / owners have agreed with the intervention |
| Protection of Natural Habitats | - Identify any protected areas in target area | IUCN | UN-Habitat checked the IUCN Red list and consulted with IUCN regional office |
| Conservation of Biological Diversity | - Identify potential endangered species in target area | IUCN |  |
| Climate Change | - Identify potential emissions from proposed interventions | Risks screening and impact assessment studies, including public hearings / consultations with vulnerable groups | ESIA, ESP and consultation reports have been developed by accredited national consultants; these are in the process of being approved by the ministries of environment Energy use (for e.g. wastewater treatment systems) will be compensated with PV |
| Pollution Prevention and Resource Efficiency | - Identify if considered interventions will use large quantity of energy |  |  |
| Public Health | - Include specific questions in vulnerable groups survey | Beneficiary groups, including women, youth, Syrians and farmers | All interventions will support clean water supply in accordance with international standards; health risks mitigation measures are taken |
| Physical and Cultural Heritage | - Identify heritage sites - Include specific questions in vulnerable groups survey | UNESCO website | No heritage sites have been identified in close to proposed project activities areas |
| Lands and Soil Conservation | - Map any fragile and valuable lands in target area | IUCN; studies | Proposed interventions will support sustainable land/ soil use and avoid degradation |

Table 32: Detailed overview of consultations conducted.

| Stakeholder | Consultation objective | Outcome | Incorporation into project design | Evidence |
| --- | --- | --- | --- | --- |
| Ministries |  |  |  |  |
| Samar Malek Acting Head of Service Environmental Technology Ministry of Environment (MoE) Lebanon | - Align with government (ministry) priorities - Avoid duplication with other projects (ministry projects) - Confirm approach and focus is in line with priorities | - MoE supports project on water focused in water harvesting and waste water reuse - Zahle area is in high need but also complex environment - If integrated water management approach / local adaptation plans are possible that would increase water use efficiency and better understanding and matching of demand and supply - Lessons (for replication) from city level climate change adaptation options are very much needed in the region and this project could be an important contribution | - Focus on water supply of most vulnerable through water harvesting and waste water reuse - Explore feasibility and buy-in of local integrated water management approach / local adaptation plans to better match demand and supply while taking into consideration climate change projections and impacts (e.g. change in water availability from snow) | Date: multiple times since 2018 Technique: discussion and SC meetings |
| Randa Nemr Advisor to the minister Ministry of Energy and Water (MoE) Lebanon | - Align with priorities and needs of the ministry - Mapping of relevant projects and lessons learned - Understand mandates | - Main priority (National water master plan) is waste water reuse because far behind on targets - Water harvesting is possible when fit - Connection waste water reuse to agriculture would be efficient but would require a detailed irrigation study | - Focus on water supply through water harvesting and waste water reuse in target area in line with National water master plan - Identify options for connecting waste water reuse to agriculture | Date: multiple times since 2018 Technique: discussion and SC meetings |
| Youssef karam Irrigation, water, sewage & infrastructure department manager Council for development and reconstruction CDR Lebanon | - Align with priorities and needs of the ministry - Mapping of relevant projects and lessons learned - Understand mandates | - Priority of ministry of water is to construct dams to profit from water - Projects with small check dams, to harvest and irrigate water, which is possible in Zahle area, is needed - Water from Zahle waste water treatment plant can be used for agriculture irrigation; however, irrigation study is needed - Studies required for project: impact of snow melt, impact of more rain in less time | - Sub-projects with small check dams, to harvest and irrigate water in Zahle (also identified my mayor) - Water from Zahle waste water treatment plant can be used for agriculture irrigation. Irrigation study is needed - Studies within project: impact of snow melt, impact of more rain in less time | Date: multiple times since 2018 Technique: discussion and SC meetings |
| Dr Ahmad N. Abdel-Fattah General manager (AF project in Jordan) | - Identify lessons learned from AF project - Coordinate with MOPIC | - Permaculture approach is promising as adaptation measure, also in urban context - No national initiative for rooftop harvesting in Jordan while top priority in TNA – explore option for cooperation with water authority and municipality to set-up nationa programme with cost-sharing and possible tax measures to promote rooftop water harvesting - Awareness raising required, e.g. at schools | - Permaculture in urban context and in farms considered as option - Explore options to set-up national initiative for rooftop rainwater harvesting, including on schools | Date: 18-11-2018 + follow-ups Technique: discussion |
| Colin Gleichmann Head of Environment & climate portfolio Rahel Hermann Project manager GIZ (in ministry of Environment Jordan) | - Mapping of relevant projects and lessons learned - Understand priorities in forthcoming NAP which is being developed by GIZ | - Emerging issue and mentioned in forthcoming NAP are pressure of refugees on water services and floods | - Refer to NAP in proposal | Date: 18-11-2018 Technique: discussion |
| Ms. Dina Kisbi, Director of Climate Change Directorate Ms. Sarah Al Haleeq, head of Adaptation Section, And Mr. Bilal Shaqareen Ministry of Environment | - Align with priorities and needs of the ministry - Mapping of relevant projects and lessons learned Understand mandate and role | - MoE is currently working on NAP with GIZ - Water harvesting is a top priority in the TNA - There is a lack of land use management plans that take into consideration climate change - Building codes is not compatible with climate change | - Refer to NAP in proposal - Scale up rooftop rainwater harvesting - Mainstream climate change adaptation into local spatial plans. - Review building codes and incorporate rooftop rain water harvesting. | Date: 24-10-2018 Technique: discussion |
| Eng. Mohammad Al Dwairi, Acting Secretary General Assistant for Strategic Planning, and and Mr. Adel Alobeiaat and Dr. Basim Hassan, Strategic Planning Specialist. Ministry of Water& Irrigation | - Align with priorities and needs of the ministry - Mapping of relevant projects and lessons learned - Understand mandate and role | - Priority of ministry of water is to focus on rainwater harvesting. - Focus on water efficiency and invest in rainwater harvesting in remote areas and from rooftops. - The Ministry is currently working on drought assessment. | - Rooftop rainwater harvesting at household level and in farms considered as option. - Identify options to incorporate water saving devices and raise public awareness. | Date: multiple times since 2018 Technique: discussion and SC meetings |
| Ms. Dalal Eliwah Study and Design Manager- technical Affairas, Yarmouk Water Company | - Align with priorities and needs of the Yarmouk Water Company - Mapping of relevant projects and lessons learned - Understand mandate and role | - Complement the needs of YW projects current and future projects - Contribute in reduction water demand of YW beneficiaries through providing additional water supplies resources | - Increase rain water harvesting from rooftops - Increase the use of Water Saving Devices to conserve precious water resources Enhance regular use of greywater treatment and reuse in public buildings to relief increasing demands on fresh water resources. | Date: multiple times since 2018 Technique: discussion and SC meetings |
| Eng. Lamia Sharif Al-Qawasmeh, Director of Planning and Development Department, Ministry of Municipal Affairs | - Align with priorities and needs of the ministry - Mapping of relevant MSSRP projects funded by the WB and lessons learned - Understand mandate and role | - Urban flooding is an issue in municipalities - Coordinate to avoid possible duplications of actitivities, e.g. constructing box culverts in Mafraq - Follow up on Innovation Fund outcomes in order to avoid \ complement and align the activities of the two projects (i.e. MSSRP and AF-Project) | - Rehabilitation of exsiting water collection system such as existing ponds which colelcts runoff water from wadis and streets during winter time. Follow up on the relevant outcomes of the needs guide being prepared by the MSSRP. | Date: multiple times since 2018 Technique: discussion and SC meetings |
| Dr. Sami Alawiyeh Chairman/ General Manager of LRA (Lebanon) | - Align with priorities and needs of LRA combatting pollution on the litany River - Mapping of relevant projects and lessons learned, especially Joub Jannine Wetlands and its benefits to the surrounding ecosystem and agriculture - Understand mandates | - High discharge of waste water, industrial waste and other wastes into Litany River - Farmers pumping sewage water to irrigate crops around the river - High violations on the river banks - River buffer zone 200m from its banks | - Constructed Wetlands in Bar Elias on plots owned by LRA | Date: 05-12-2019 |
| Ihab Jomaa, PhD Head of the Department of Irrigation and Agrometeorology at the LARI (Lebanon) | - Align with priorities and needs of the MoA - Mapping of relevant projects, trainings for farmers, and lessons learned - Understand mandates | - Efficient irrigation techniques are often misused by farmers - Involvement in crops testing and experiments and farmers training (LARI releases new varieties of wheat and barley after testing them to climate conditions on a yearly basis to the market) - No national guidelines for wastewater reuse, using FAO 2010 instead. - Farmers do not pay for irrigation water | - Efficient irrigation techniques for potato crops - Efficient irrigation techniques for fruit trees - Capacity building for farmers cooperatives | Date: 05-12-2019 |
| UN agencies (relevant projects, target area issues and needs and ESP and GP potential risks identification) |  |  |  |  |
| Olivier Thonet Chief of WASH UNICEF Lebanon | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area - Consultations for AF ESP and GP compliance (gender approach) - Discuss possible cooperation / coordination | - UNICEF follows MoE (National water master plan) and municipal needs to increase connections of settlements to water resources, especially ground water wells - UN-H can complement UNICEF work with focus on climate change adaptation in target area | - Compliment UNICEF work in target area by focus on water harvesting and reuse and consideration of climate change | Date: multiple times since 2018 Technique: discussion and SC meetings |
| Jose A. Gesti canuto Chief of WASH UNICEF Jordan |  | - UN-H can complement UNICEF work with focus on climate change adaptation in target area - UNICEF possible executing partner |  | Date: multiple times since 2018 Technique: discussion and SC meetings |
| Renata Raad WASH Officer UNHCR | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area - Consultations for AF ESP and GP compliance (equall access, vulnerable groups and human rights approach) - Discuss possible cooperation / coordination | - Important to have a community approach to avoid social tension over water resources (equal access) - UNHCR has specific focus on women headed households, children without care and disabled - Water supply project require risk mitigation measures on waste and soil (to have access to water in environmentally friendly way) and water rights (since these are not clear - UN-H can complement UNHCR work with focus on climate change adaptation | - Design project so it avoids risks related to social tension over water resources, pollution and environmental unfriendly use (waste and soil) and water rights - Consider needs women headed households, children and disabled | Date: 06-11-2018 Technique: discussion |
| Vincent Dupin Senior technical officer Roelof Wentzel WASH offcer UNHCR |  | - UNHCR has relevant refugee vulnerability profile related to livelihood and shelter - Issue identified: municipality has challenges providing enough water in dry season - Possible innovative technique: easy to dismantle and to be shipped to other location waste water treatment plant (in container) | - Explore option of using possible innovative technique: easy to dismantle and to be shipped to other location waste water treatment plant (in container) – relevant for uncertain urbanization, e.g. with influx and departure refugees | Date: 18-11-2018 Technique: discussion |
| Vahakn Kabakian AF focal point, also working for UNDP UNDP Lebanon | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area | - Focus on water supply of most vulnerable through water harvesting and waste water reuse | - Focus on water supply of most vulnerable through water harvesting and waste water reuse | Date: 09-11-2018 Technique: discussion |
| Nedal M.Al-Ouran Head of env. CC and DRR portf UNDP Jordan |  | - GCF proposal under review – other geographic focus but UNDP and UN-H will coordinate proposal development - UNDP is piloting rainwater harvesting in public building - Suggest to identify unused or not properly used already existing water harvesting systems and make better used of these | - Include focus on identifying unused or not properly used already existing water harvesting systems (make better used of these - Conduct educational awarenss programmes on climate related-water issues - Promot non-conventional water options and focus on alternastive water sources such as grey water. - Contact and involve governance councils and boost their decentralisation role - Benefit and disseminate indigenous knowledge on water harvesting. | Date: 19-11-2018 Technique: discussion |
| Nasredin Hag Elamin Representative in Jordan Talal Al-Fayez Programme expert FAO Jordan | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area - Consultations for AF ESP and GP compliance (lands and soil conservation) | - FAO to share study on existing and potential water harvesting locations in Jordan - FAO to share best practice on water harvesting options in Mafraq | - A sub-sector strategy for water harvesting is needed to ensure the continued development of this alternative in a way that is effective and sustainable. - Developing a sub-sector strategy on water harvesting and ensure equitable approach that benefits all groups. - Diversify agricultural water supply and to improve agricultural water security. - Water harvesting could be particularly useful in Mafraq Region for supporting the cultivation of fodder crops, given the existing importance of livestock in the area. | Date: 19-11-2018 Technique: discussion |
| Sarah El jamal Programme officer Regional office for Arab States ILO Lebanon | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area - Consultations for AF ESP and GP compliance (core labour rights) | Agriculture: Lebanon and Jordan have both not ratified C129 - Labour Inspection (Agriculture) Convention, 1969 (No. 129) Construction: Lebanon and Jordan have both not ratified C167 - Safety and Health in Construction Convention, 1988 (No. 167) Migrant workers: Lebanon and Jordan have both not ratified C143 - Migrant Workers (Supplementary Provisions) Convention, 1975 (No. 143) Women: Lebanon and Jordan have both not ratified P089 - Protocol of 1990 to the Night Work (Women) Convention (Revised), 1948 | - Refer to core labour rights, technical conventions for safety and health and CBA in any contract - Ensure safety and health measures are taken during project (especially for women and DPs) and are inspected during project - Coordinate with ILO on skills needs and ILO projects | Date: 16-11-2018 Technique: discussion |
| Patrick Daru Country coordinator ILO Jordan |  | Main potential issue / risk in Jordan: - Convention 81 – labor inspection convention. Although ratified there is limited inspection capacity - Increase in child labor (because refugees often work with whole family) - Safety / harassment issues for women Figures: - Not many women in construction, but many in agriculture Improvements and projects: - Collective Bargaining Agreement (CBA) by 2019 - Shawish (mediator) protect wage of Syrian refugees - Flexible work permit for Syrian refugees (not dependent on one employer) |  | Date: 19-11-2018 Technique: discussion |
| Faten Tibi Programme Manager Women and Youth Empowerment Programme in Host communities UN Women Lebanon + Syria | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area - Consultations for AF ESP and GP compliance (gender approach) | - Many women (incl. Beduin) work in agriculture + food processing. Men work in agriculture, transport and markets - Education of women is in general more modest than men - Syrians only work in agriculture (allowed) - In women empowerment project there are no issues between Syrian and Lebanese women - Need to ensure secure / safe environment (i.e. protection) for women during work since gender-based violence can still be an issue in the region | - Consider women roles in agriculture and water handling when designing the project - Ensure women protection measures are in place for the project (when needed) | Date: 08-11-2018 Technique: discussion |
| Hazar Asfoura Programme Analyst, Women’s Economic Empowerment Resileince and Empowerment Unit. UN Women Jordan |  | - Many women are working in agricultural sector in Jordan and thus affected by water scarcity. - Due to water scarcity women who are engaged in agriculture sector are moving from one place to another following water availability - Water scarcity is one of the reasons that prevent women from getting decent working opportunities in agricultural sector. - Rural women’s existing theoretical knowledge and understanding of climate change and adaptation remain limited, impeding their ability and willingness to act and find long term adaptive solutions. When asked about the services they would like better access to, only 25% of Women reported wanting better access to water compared to 37% of men. This is manly influenced by gendered household roles. | - Raising rural women’s awareness on conservation techniques and climate change processes, proper greywater re-use and water harvesting techniques to strengthen climate-change adaptation processes. - Strengthening rural women’s leadership capacities so that they better engage in adaptive responses to climate change. - fostering rural women’s capacities to act and make significant achievements in adapting to climate change | Date: 30-12-2018 Technique: Discussion |
| Mazan Shaqoura Deputy regional representative OHCHR Lebanon | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area - Consultations for AF ESP and GP compliance (human rights) | Jordan and Lebanon have both not ratified core Human right # CMW - International Convention on the Protection of the Rights of All Migrant Workers and Members of Their Families. # Therefore, the project needs to ensure DPs (and Lebanese) have equal access to work options and are equally treated / rewarded. | - Include measures and clauses in contract to ensure on the left | Date: 16-11-2018 Technique: discussion |
| Ali Hayajneh Water and CC programme IUCN regional (Lebanon and Jordan) | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area - Consultations for AF ESP and GP compliance (natural habitats, biodiversity and soils) | - IUCN is developing water security action plans at municipal level - IUCN helped to identify potential (sub-project risks related to natural habitats, biodiversity and fragile soils in target areas - Irbid and Mafraq are located within two eco-regions, there is one national designed protected area in Irbid (Yarmouk forest reserve) and there are some important bird areas - Zahle district and surrounding municipalities are part of two eco-region. Zahle distract includes 5 Hima areas; Kafer Zabad 20km2 , Anjar 20km2, Kherbet kanfar 21.4km2, Ainzebde5.5Km2, Tarshish 10km2, these area are important for the local communities as they provide a common practice of grazing and Agriculture production. There are also some important bird, mammal and flora areas close-by | - The target areas are located in eco-regions with some vulnerable protected areas and animals. Proposed interventions are planned in urban areas and are expected to don’t negatively interrupt these because of limited disruption of water flows (of seasonal streams) and land / soil interventions. However, during the full proposal, this will be studies and assessed in detail. | Date: 19-11-2018 Technique: discussion |
| Sally Zgheib Water supply & sanitation specialist; Amal Talbi Senior Water Resources Management Specialist Shafick Hoossein Head of Environment and natural resources of Mashreq regions (Washington D.C) World Bank | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area - Discuss possible cooperation / coordination | - Ensure to avoid social tension between groups and areas, also by understanding impact on interventions upstream and downstream – use intergrated water management approach - Using treated waster water from Zahle plant is a good option to increase water use efficiency. | - Avoid social tension and negative impacts of interventions through impact assessment (full proposal) - Use intergrated water resource management approach if agreed by national government and local authorities | Date: 08-11-2018 Technique: discussion |
| Mirage for Waste Management & Environmental Services Zahle waste water treatment plant operator. Lebanon | - Understand needs and issues in target area and how waste water can be used for agriculture | - Waste water is currently being directed to Litani river but could be used for agriculture, especially in low(er) lying areas to avoid much pumping - Feasibility waste water reuse for agriculture depends on crop and level of treatment | - Design option for waster water reuse from Zahle waste water reuse plant for agriculture use and specific type of crops (fruit) | Date: multiple times since 2018 Technique: discussion and SC meetings |
| Aya Housheimi WASH Coordinator – Zahle-Lebanon Norwegian Refugee Council Lebanon | - Mapping of relevant projects and lessons learned - Understand needs and issues in target area - Consultations for AF ESP and GP compliance (human rights and ILO standards and approach for Syrian refugees) | - The refugees rely on agricultural boreholes and shallow boreholes for household water supply. Due to drought those boreholes are getting drier, and more contaminated. - Diseases, as a result of lessened personal hygiene, and household hygiene. - Safety Protection Risks: Refugees, mainly women and children, travel long outside ITS looking for other water resources, which puts them in danger. | - Rain water harvesting | Date: 07-12-2018 |
| Steering Committee Meetings Lebanon (MoE representative, MoEW representative, UNICEF, UN-Habitat and Consultant) | - Align with priorities and needs of the ministries - Mapping of relevant projects and lessons learned - Understand mandates | - Farmers not paying for the treated waste water usage - Proper O&M of the Zahle WWTP - Irrigation guidelines still not issued, currently being developed between MoEW and LIBNOR | - Physical interventions cleared | Dates: 18-09-2019 07-10-2019 |

ANNEX 3: ESP annex, incl. ESMP

Content:

  - Introduction, purpose, method, project overview / summary of project risks management approach

  - Risks screening and categorization

  - Environmental and social impact assessment (quantification)

  - Environmental and social management plan, including monitoring

  - Introduction, including summary description of the project/ programme

Introduction

Social and environmental policies are essential tools to prevent and / or mitigate undue harm of projects and project activities to people and their environment. In line with the Adaptation Fund’s ESP and UN-Habitat’s Environmental and Social Safeguard Policy (ESSP), UN-Habitat and partners are required to categorize the risk of the project as a whole and to manage potential risks and impacts.

Purpose

The purpose of this ‘ESP annex’ is to demonstrate (in an overview) how this project complies to the AF ESP. The annex shows what potential environmental and social risks and co-benefits and opportunities have been identified per project activity, the potential impacts of the risks and how these will be managed. This proposal and related country-specific ESIA-ESMP and consultation reports are being published on UN-habitat ROAS website: https://unhabitat.org/af-lebanon-jordan

Methodology

To ensure compliance with the AF ESP, all proposed project activities have been screened against the 15 AF principles (i.e. safeguards) to identify potential environmental and social risks and to assess related potential impacts. Where risks have been identified, impact assessments have been conducted and where needed, measures to avoid or mitigate risks and impact, identified (+ monitoring arrangements)

In both Jordan and Lebanon, risks screening sheets have been completed for each proposed project activity. Besides that, in both countries, accredited consultants prepared country-specific ESIAs, ESMPs and consultations reports in compliance with the AF ESP and GP and national requirements for conducting ESIAs. Details in these reports, including risks mitigation measures, will be integrated in (sub)project execution plans, including for construction, operation and maintenance. Below shows an overview / summary of these report (most important findings) and the outcomes have been consolidated in the proposal, including in the budget. The country specific ESIAs, ESMPs and consultations reports are available through above website. The completed risks screening sheets for each project activity are available on request.

Data and analysis are provided based on collected disaggregated data focused on identification of climate change related needs, limitations, constraints and requirements specific for marginalized and vulnerable groups, especially of women and youth. Activity prioritization and the identification and verification of potential risks and impacts and, where needed, identification of measures to avoid or mitigate potential risks have been done with project beneficiary groups (through community surveys, focus groups discussions and community planning and decision-making processes during project preparation.

Overview / summary of project risks management approach

Table 33 overview / summary of project risks management approach.

| ESP principle | Initial environmental or social risks present as per table in Part II.L Y/N | Impacts assessment | Safeguard measures | Monitoring indicator(s) | Baseline condition for each monitoring indicator |
| --- | --- | --- | --- | --- | --- |
| 1 - Compliance with the law | No |  |  |  |  |
| 2 - Access and equity | No |  |  |  |  |
| 3 – Marginalized and vulnerable Groups | No |  |  |  |  |
| 4 – Human rights | No |  |  |  |  |
| 5 – Gender equality and women’s empowerment | No |  |  |  |  |
| 6 – Core labour rights | No |  |  |  |  |
| 7 – Indigenous peoples | No |  |  |  |  |
| 8 – Involuntary resettlement | No |  |  |  |  |
| 9 – Protection of natural habitats | No |  |  |  |  |
| 10 – Conservation of biological diversity | No |  |  |  |  |
| 11 – Climate change | No |  |  |  |  |
| 12 – Pollution prevention and resource efficiency | Yes. Pollution. On-plant accidental spills, overflows, seepages and discharges of wastewater treatment may contaminate soil, groundwater or surface water from WWTP | Spills, overflows and seepages are at plant level and can be contained there | Carry out regular inspections and routine tests to avoid spills, overflows, seepages and discharge of low-quality water (see also water quality testing below); include detailed risks mitigation measures identified in country-specific ESIA-ESMP reports in construction, operation and maintenance plans; | Monitoring of wastewater handling and possible spills, overflows and seepages. Construction and O & M report addressing above | Check standards for water quality, treatment and construction |
| 13 – Public health | Yes. Safe water: water quality from RWH and GWTR systems may not comply to standards | Jordan: 86 RWH and 40 GWRT systems with following direct beneficiaries: 52,855 Lebanon: 20 RWH systems with following direct beneficiaries: 8,753 | Rainwater collected will be treated using sand and carbon filter, a micro filter, and chlorine. This will ensure water quality compliance. Note that tap water is not used for drinking or cooking. Water and roofs will be regularly monitored, especially at the start of the rainy season; Filter will be changed annually, as per supplier recommendation. The chlorine tank should not be empty so there will be no pumping of air that impacts water quality; Students and building staff will be made aware (through curriculum) of requirements of using water + involved in operation and maintenance; Remote monitoring systems will be installed | Water quality monitoring complying to standards; Awareness raising campaign; O & M (training) reports with attendance lists and photos; checking of filters and chlorine tank | Water quality check (compliance to tap water quality standards) Check filters and chlorine tank |
|  | Yes. Safe water: treated waste water used for irrigation may not comply to quality standards / unmonitored irrigation water may reduce quality of crops | Jordan: Extra from Maerad WWTP: storage tank with a capacity of 2,000 – 5,000 m3 Exra from Al Kaider: Storage tank with a 2,000-3,000 m3 Extra from Mafraq: 9,000 m3 Lebanon: From Zahle WWTP: 18,000 m3 From Wetlands: 6,000 m3 | Although the project intervention aims to increase the quality of water for irrigation, regular testing of water quality is required and irrigation will only begin after testing; Farmers will be made aware of requirements for use + involved in operation and maintenance; For the wetlands, visual inspection of existence of mosquito breeding sites. In case of their presence, introduction of tilapia fish that feeds on the eggs. | Water quality monitoring of the effluent from the WWTP and wetlands. The level of treatment is tertiary. This needs to be checked on a regular basis. Checking mosquitos | Water quality check (compliance with FAO guidelines for irrigation) Mosquito presence |
| 14 – Physical and cultural heritage | No |  |  |  |  |
| 15 – Lands and soil conservation | No |  |  |  |  |

  - Screening and categorization

Based on the screening against the 15 AF principles, the project has been categorised as a “B” category project in terms of the environmental and social risks it poses. See Part II.L

According to the Jordan’s EIA Regulations, particularly the EIA By-Law No. 37 of the Year (2005), the project has been categorized as “Category III” project, which imply that the proposed interventions in Jordan have no considerable risks or adverse impacts, thus not requiring full EIAs. This is due to the fact that all of the construction activities and installations of proposed sub-projects are not substantial and will be constructed or installed in already built and operating facilities, such as fully-functioning WWTPs, which at the time of original construction have been subjected to MoEnv’s incumbent EIA regulations and supervision. However, although no impact assessments were required by national law, a full ESIA and ESMP report has been developed for the proposed project activities / outputs in Jordan, accompanied by a consultations report.

According to Lebanese decree 8633 MoE, 2012, Annex 1, the proposed project activities / outputs don’t required full EIAs, except the proposed constructed wetlands in Bar Elias, as this activity was  categorised as ‘category II’ sub-project, which imply that an initial screening was required, followed by an EIA. Similarly to Jordan, all of the construction activities and installations are not substantial and will be constructed or installed in already built and operating facilities, except the proposed wetlands, which will be constructed on public land selected by the government for this purpose. To comply to the AF requirements, risks screening and impact assessments have also been conducted for all proposed project activities.

For an overview of project activities’ screening results against the 15 AF principles see below table. For details, see the next section.

Table 34: Overview of project activities’ screening results against the 15 AF risk areas / principles. For more details see country-specific ESIA reports

| Detailed outputs / activities | Risk screening result | Explanation why triggered or not |
| --- | --- | --- |
| Component 1: Increasing the resilience of municipal governments: Manage urban risks and vulnerabilities in the context of climate change, esp. water scarcity challenges, and urban (population) growth, incl. from DPs migration |  |  |
| - Territorial planning and development strategy / guidelines at district level with climate change and gender mainstreamed (Lebanon) | No risks identified | Activities involve assessment and planning processes. Potential risks considered are those related to unequal access and equity, also for vulnerable groups and gender, throughout the assessment and planning processes and identification of gender sensitive action plans. However, the execution entities involved will be required to involve beneficiary groups, including identified vulnerable groups (and women and youth) in the activities. Targets and quotas will be used. These will be verified during the project inception phase with execution entity specific baseline and targets and action plans, also to involve women and youth and other vulnerable groups. |
| - Urban master plans at municipal level with climate change and gender mainstreamed (Lebanon) |  |  |
| - Urban master plans at municipal level with climate change and gender mainstreamed (Jordan) |  |  |
| Component 2: Increasing the resilience of citizens (DPs and host communities): Improve awareness, ownership and capacities to respond to climate change, incl. to operate, maintain and replicate resilient water harvesting, supply and irrigation systems |  |  |
| - Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1: Rooftop Rainwater Harvesting in Lebanon | No risks identified | Activities involve awareness raising and capacity building activities. Potential risks considered are those related to unequal access and equity, also for vulnerable groups and gender. However, the execution entities involved will be required to involve beneficiary groups, including identified vulnerable groups (and women and youth) in the activities. Targets and if needed, quotas will be used. These will be verified during the project inception phase with execution entity specific baseline and targets and action plans, also to involve women and youth and other vulnerable groups. |
| - Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1: Rooftop Rainwater Harvesting in Jordan |  |  |
| - Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.3: Grey Water Treatment and Reuse in Jordan |  |  |
| - Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.41: Efficient treatment and reuse of wastewater from Zahle WWTP, in Lebanon |  |  |
| - Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.4.2: Efficient treatment and reuse of wastewater through wetlands, in Lebanon |  |  |
| - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.5: Efficient treatment and reuse of wastewater in Jordan |  |  |
| - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.6: Water-use-efficient irrigation of treated wastewater for fruit trees in Lebanon |  |  |
| - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.6: Water-use-efficient irrigation of treated wastewater for potato crops in Lebanon |  |  |
| - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7: Water-use Efficient irrigation of treated wastewater from Maerad and Al Kaider WWTPs in Jordan |  |  |
| - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7: Water-use Efficient irrigation of treated wastewater from Mafraq WWTP in Jordan |  |  |
| - Community organization, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 2.8; permaculture demonstration |  |  |
| Component 3: Increasing the adaptive capacity of the water sector: Expand unconventional water harvesting, supply and irrigation options, using innovative and replicable techniques suitable for the context |  |  |
| - Rooftop rainwater harvesting in Lebanon | Potential health risk (AF 13) (with some linkage to pollution prevention (AF 12) | Safe water: water quality from RWH and GWTR systems may not comply to standards |
| - Rooftop rainwater harvesting in Jordan |  |  |
| - Greywater treatment and reuse in Jordan |  |  |
| - Efficient treatment and reuse of wastewater from Zahle WWTP, in Lebanon | Potential health risk (AF 13) (with some linkage to pollution prevention (AF 12) | Safe water: water used for irrigation may not comply to quality standards / unmonitored irrigation water may reduce quality of crops Pollution: there is a small risk of contamination of soil, groundwater or surface water from on-plant accidental spills, overflows, seepages and discharges. |
| - Efficient treatment and reuse of wastewater through wetlands, in Lebanon |  |  |
| - Efficient treatment and reuse of wastewater in Jordan (Maered WWTP) |  |  |
| - Efficient treatment and reuse of wastewater in Jordan (Al Akaider WWTP) |  |  |
| - Efficient treatment and reuse of wastewater in Jordan (Mafraq WWTP) |  |  |
| - Water-use-efficient irrigation of treated wastewater for fruit trees in Lebanon from Zahle WWTP, Lebanon | No risks identified | Activities mainly involve installing water efficient irrigation systems. The source of water will come from activities under outputs above, so potential risks related to safe water are handled under above outputs. Under comp 2, target communities will be organised and involved. |
| - Water-use-efficient irrigation of treated wastewater for potato crops in Lebanon from Bar Elias wetland, Lebanon |  |  |
| - Water-use Efficient irrigation of treated wastewater from Mearad and Al kaider WWTP |  |  |
| - Water-use Efficient irrigation of treated wastewater from Mafraq WWTP, Jordad |  |  |
| - Permaculture demonstration – efficient water use system | No risks identified | Activities are very localised at JUST site. |
| Component 4: Improving knowledge and policies and regulations to increase urban resilience in the region: Project KM and replication, incl. development of regional urban risks and vulnerabilities management model in the context of climate change and urban (population) growth (incl. from DPs migration) |  |  |
| - Regional / international KM with focus on sharing project lessons and replication | No risks identified | Activities include knowledge exchange though meetings, site visits, events, etc. UN-Habitat and UN-ESCWA will ensure equal involvement / representation. |
| - Jordan and Lebanon KM with focus on project progress, best practices and lessons learned |  |  |
| - Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities | No risks identified | Activities include desk top consultancy work |
| - Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities | No risks identified | Activities include desk top consultancy work |

Details and results of the risks screening process

*For more details see country-specific ESIA reports

Principle 1: Compliance with the Law.

Screening result: no potential risk

Explanation: During project preparation, all relevant rules, regulations and standards have been identified for all proposed project activities, including procedures / steps to comply to these. These are shown in Part II.F. Where required by national law, EIAs have been completed before the start of the project. Therefore, no potential risk of non-compliance exists.

Below has been done for Jordan and Lebanon. Although no EIA was required by law in Jordan, an accredited consultant in Jordan conducting risks screening and impact assessments to comply to AF requirements. In Lebanon, the proposed constructed wetlands in Bar Elias (output 3.4.2) was regarding as a category II sub-project. According to Lebanon decree 8633 MoE, 2012, Annex 1, a screening for the project was needed (see below). Besides that an accredited consultant firm in Lebanon conducting risks screening and impact assessments to comply to AF requirements.

Table 35: Summary of the EIA Procedures in Jordan and Lebanon

| Stage | Activity |
| --- | --- |
| Initial Filing and Screening | The Project Proponent completes a Project Information Form (PIF) of the intended project and submits it to the Ministry of Environment for screening. An Inter-ministerial Central Licensing Committee reviews the PIF, and after conducting site surveys determines if the project is classified as: - Category I projects for which an EIA report is required - Category II projects for which an initial EIA is only required - Category III for which no environment analysis is required |
| Scoping | The Ministry issues legally binding guidance on the Scope of the Assessment Proponent prepares a ToR, after a mandatory public consultation. An Inter-Ministerial Technical Review Committee (TRC) reviews and approves the ToR. Accredited consulting entity commences with EIA. |

Table 36: EIAs completed as required by national law

| Output / activity | National EIA requirements and procedure | Outcome |
| --- | --- | --- |
| 3.4.1 Efficient treatment and reuse of wastewater, through constructed wetlands in Bar Elias, in Lebanon | According to Decree No. 8633,2012 of MoE, the following steps were taken: -A screening form for the project was submitted -MoE decision was that the project requires an EIA -A public consultation was held on December 18th, 2019 -A scoping report was submitted to MoE on December 30th, 2019. -The EIA report is the final step of the EIA process. It was submitted on January 13th, 2020, following the reply of MoE on scoping report. | Environmental Management and Monitoring Plan for the risks and impacts identified in EIA. |

Principle 2: Access and Equity.

Screening result: no potential risk

Explanation: All project beneficiaries (i.e. population; groups) have been mapped (see overview table 6) for each project activity / output. Community consultations and focus groups discussions have been conducted per beneficiary group to identify possible rivals, disputants and concerns related to equal access of project benefits. In that way, equal allocation and distribution of project / programme benefits will be ensured during project execution. Moreover, there will be neither discrimination nor favouritism in accessing project/programme benefits. Project benefits will be allocated and distributed equally through a participatory process and through joint decision-making using water user and agriculture associations. Component 2 has been designed to facilitate this process, including awareness raising and capacity building of communities and vulnerable groups to operate, maintain and replicate proposed activities under component 3. Under component 1, various groups will be equally involved, in assessment and planning processes (if needed through quotas).

Principle 3: Marginalized and Vulnerable Groups.

Screening result: no potential risk

Explanation: all project beneficiaries (i.e. population; groups), including marginalised and vulnerable groups have been mapped for each project activity / output (see overview table 6). Desk research, expert consultations and community consultations and focus group discussions have been used (see Part II.I and Annex 2) to identify possible risks / adverse impacts of project activities on marginalized and vulnerable beneficiary groups (i.e. specific needs, limitations, constraints and requirements of groups).  Disaggregated data at the district and municipal and activity beneficiary level has been used to identify and quantify marginalized and vulnerable groups. Also, UNHCR has been consulted to to specifically identify potential risks and needs of marginalised and vulnerable groups.

Principle 4: Human Rights.

Screening result: no potential risk

Explanation: during project preparation and execution, international human rights are respected and where applicable, promoted. During project preparation, possible human rights issues have been identified by assessing whether  Jordan and Lebanon are cited in any Human Rights Council Special Procedures, and to confirm and understand possible issues through consultations with ‘experts.’ Communities have also been consulted about possible human rights issues with the purpose of design activities appropriately.

OHCHR has been consulted and mentioned that both Jordan and Lebanon have both not ratified core Human right CMW - International Convention on the Protection of the Rights of All Migrant Workers and Members of Their Families. Therefore, the project needs to ensure DPs and Lebanese and all other groups have equal access to work options and are equally treated / rewarded. This will be done through participatory planning process and by included standard clauses in all contract with contractors ensuring all beneficiary groups will have equal access and opportunities. Moreover, awareness about this will be raised through poster, explaining rights and grievance options.

Principle 5: Gender Equality and Women’s Empowerment.

Screening result: no potential risk

Explanation: the project ensures that gender equality and women’s and youth empowerment is ensured for all project activities. During project preparation, this has been done through detailed stakeholder mapping (see also principle 3) including identification of specific needs, limitations, constraints and requirements of women and youth. UN Women and UNICEF have also been consulted to specifically identify potential risks and needs of women. A specific ‘gender’ approach and baseline section has been developed. See annex 4. In this section, the legal and regulatory context with respect to gender equality and women’s empowerment in which the project takes place has been analysed, as well as cultural, traditional and religious context. Arrangements that ensure equal participation in project activities and consultations and equal access to benefits have also been identified in gender approach and baseline.

Principle 6: Core Labour Rights.

Screening result: no potential risk

Explanation: the project ensures that all project activities meet the core labour rights and that possible risks have been identified and if existing, prevented or mitigated. During project preparation, this was done by identifying possible compliance issues by analysing if Jordan and Lebanon ratified the conventions, to confirm and understand these possible issues through consultations with ILO and by describing how the project will address possible compliance issues. Communities have also been consulted about possible labour issues that could arise while executing project activities with the purpose of design activities appropriately.

ILO identified the following:

- Agriculture: Lebanon and Jordan have both not ratified C129 - Labour Inspection (Agriculture) Convention, 1969 (No. 129)

- Construction: Lebanon and Jordan have both not ratified C167 - Safety and Health in Construction Convention, 1988 (No. 167)

- Migrant workers: Lebanon and Jordan have both not ratified C143 - Migrant Workers (Supplementary Provisions) Convention, 1975 (No. 143)

- Women: Lebanon and Jordan have both not ratified: P089 - Protocol of 1990 to the Night Work (Women) Convention (Revised), 1948

Potential issue / risks:

- Convention 81 – labour inspection convention. Although ratified there is limited inspection capacity

- Increase in child labour (because refugees often work with whole family)

- Safety / harassment issues for women

Figures:

- Not many women in construction, but many in agriculture

Improvements and projects:

- Collective Bargaining Agreement (CBA) by 2019

- Shawish (mediator) protect wage of Syrian refugees

- Flexible work permit for Syrian refugees (not dependent on one employer)

Therefore, UN-Habitat need to ensure all contracts include standard clauses to avoid any risks regarding above and that safety measures are taken and inspections conducted.

Principle 7: Indigenous Peoples.

Screening result: no potential risk

Explanation: the project ensures that project activities are consistent with the rights and responsibilities set forth in the UN Declaration on the Rights of Indigenous Peoples by ensuring that possible issues are identified and mitigated / prevented. During project preparation, the project determined that no indigenous people are present in the project / programme target areas. This has been determined through stakeholder mapping (through desk research and expert and community consultations. Although Some Bedouins are now official Lebanese and Jordanians, no indigenous groups have been identified in target areas. Besides that, it has been analyzed if Jordan and Lebanon ratified the ILO Convention 169 and other applicable international instruments relating to indigenous peoples.

Principle 8: Involuntary Resettlement.

Screening result: no potential risk

Explanation: the project determined that no physical or economic displacement will take place due to the project/programme. This has been determined by mapping project target sites land ownership (private, public) and land use, also informally, and through consulting communities / users on the possible risk of resettlement and to get agreement on proposed interventions (i.e. no interventions will take place without the consent of inhabitants in the targeted areas). Land owners, private or public, have agreed with using their land for project activities. As for the wetlands, the target land is public land (belonging to the Litani River Authority) and no land use, even informally takes place in the area. Agriculture was practices but stopped because of water challenges (legal papers are present in the feasibility studies / ESIA). Regarding the construction of irrigation channels, these will also take place on public land and or in consent with the land owners, especially farmers, through the water use and agriculture associations. The other proposed project activities all take place in buildings or on the treatment plants premises. Public hearings and consultation in the target areas did not identify any concerns related to resettlement.

Principle 9: Protection of Natural Habitats.

Screening result: no potential risk

Explanation: the project ensures that no unjustified conversion or degradation of critical natural habitats will take place because of project activities. During project preparation, it has been checked if any critical natural habitats exist in the target location, including their location, characteristics and critical value (i.e. legal protection status, common knowledge or traditional knowledge), as well as possible negative impacts on these due to project activities. This has been done by checking IUCN Red list and by consulting IUCN (regional office)

Principle 10: Conservation of Biological Diversity.

Screening result: no potential risk

Explanation: the project ensures that any significant or unjustified reduction or loss of biological diversity because of project activities will be avoided. During project preparation, it has been checked if any important biodiversity exist in the target location, including their protection status and other recognised inventories as well as possible negative impacts on these due to project activities. According to the IUCN red list and UNESCO Man and the Biosphere Programme reserve, no sensitive biospheres are located in the target areas. This was confirmed through consultations with IUCN (regional office).

Principle 11: Climate Change.

Screening result: no potential risk

Explanation: the project will ensure that project activities will not result in any significant or unjustified increase in greenhouse gas emissions or other drivers of climate change.

Table 37: Identification of possible increase of greenhouse gases per project activity

| Output / activity | Activity that may increase greenhouse gases | Possible increase in greenhouse gases |
| --- | --- | --- |
| 3.5. Efficient treatment and reuse of wastewater in Jordan | - Energy use for some pumping | Although very limited, energy use could be increased because of pumping of water from WWTP to farm lands. To compensate for this, PV will be installed at the plants |

Principle 12: Pollution Prevention and Resource Efficiency.

Screening result: there may be pollution risks due to treatment practices at WWTPs

Explanation: the project aims to maximize energy efficiency and minimizing material resource and prevents waste and pollution due to project activities through analysis of possible risks of inefficiencies in energy and material resource use and waste and pollution risks of each activity – which has been done during project preparation. Irrigation of waste water from the Zahle WWTP for instance has been designed to serve farmers through a gravity system. However, these may be some risks of on-plant accidental spills, overflows, seepages and discharges of wastewater treated, which may contaminate soil, groundwater or surface water from WWTP.

Table 38: Identification of possible pollution risks per project activity

| Output / activity | Possible pollution risks | Description possible health risks / impacts |
| --- | --- | --- |
| 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon | Pollution. Contamination of soil, groundwater or surface water | On-plant accidental spills, overflows, seepages and discharges of wastewater treatment may contaminate soil, groundwater or surface water from WWTP |
| 3.5. Efficient treatment and reuse of wastewater in Jordan |  |  |

Principle 13: Public Health.

Screening result: there may be potential health risks due to used water

Explanation: the project will ensure that potentially significant negative impacts on public health are avoided. To avoid potential negative health impacts for project activities and other activities safety signs and equipment will be provided in line with core labour rights (155 and 187). Although the project intends to improve the quality already used for irrigation, water quality monitoring will take place. The same accounts for the rainwater harvesting and greywater treatment and reuse interventions.

Table 39: Identification of possible health risks per project activity

| Output / activity | Possible health risks | Description possible health risks / impacts |
| --- | --- | --- |
| 3.1. Rooftop rainwater harvesting in Lebanon | Safe water | Water quality from RWH and GWTR systems may not comply to standards |
| 3.2. Rooftop rainwater harvesting in Jordan |  |  |
| 3.3. Greywater treatment and reuse in Jordan |  |  |
| 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon | Improved water (safe water) | Treated waste water used for irrigation may not comply to quality standards / unmonitored irrigation water may reduce quality of crops |
| 3.5. Efficient treatment and reuse of wastewater in Jordan |  |  |

Principle 14: Physical and Cultural Heritage.

Screening result: no risk

Explanation: the project ensures that the alteration, damage, or removal of any physical cultural resources, cultural sites, and sites with unique natural values recognized as such at the community, national or international level due to project activities will be avoided. During project preparation, It has been checked if physical or cultural heritage sites are present or near project sites, as well as possible risks of impacts on these due to project activities. UNESCO listed Heritage sites in target area: Anjar has been identified as a heritage site in Lebanon (in the district of Zahle). However, this is not in the target areas.

Principle 15: Lands and Soil Conservation.

Screening result: no risks

Explanation: The project ensures no negative impacts lands and soil conservation will result from project activities. All proposed project activities aim to enhance sustainable land and soil use, especially for agriculture use. No major excavations will take place, except for the initial phase of constructing the wetlands in Bar Elias, but this is to enhance vegetation. A study of the targeted area was done, showing that the target area has low organic matter content, which is one indicator of soil fragility. The proposed intervention will reduce the loss or degradation of the soil, reducing any related risk.

  - Environmental and social impact assessment

For an overview of project activities’ potential risks and impact assessment result against the 15 AF principles, see below table.

Table 40: Overview of project activities’ screening and assessment results against the 15 AF risk areas / principles

| Output / activities | Potential risk / impact | Impact assessment |
| --- | --- | --- |
| 3.1. Rooftop rainwater harvesting in Lebanon | Safe water: Water quality from RWH and GWTR systems does not comply to standards | 20 RWH systems with following direct beneficiaries: 8,753 (visitors, students) |
| 3.2. Rooftop rainwater harvesting in Jordan |  | 86 RWH systems with following direct beneficiaries: 52,855 |
| 3.3. Greywater treatment and reuse in Jordan |  | 40 GWRT with following direct beneficiaries: 39,582 (same as under output 3.1.) |
| 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon | Improved water (safe water): Water used for irrigation does not comply to quality standards / unmonitored irrigation water may reduce quality of crops Pollution. On-plant accidental spills, overflows, seepages and discharges of wastewater treatment may contaminate soil, groundwater or surface water from WWTP | Output 3.4.1. The Zahle WWTP treats 18,000m3 and irrigate 110-116 hectares of farmland Output 3.4.2. The wetlands (60,000m2) treats 6,000m3 and will irrigate 40-70 hectares of farmland |
| 3.5. Efficient treatment and reuse of wastewater in Jordan |  | Output 3.5.1. Maerad WWTP will store 2000-3000 m3 of water and irrigate 60 dunum of farmland Output 3.5.2. Al Kaider WWTP will store 2000-3000 m3 of water and irrigate 60 dunum of farmland Output 3.5.3. Mafraq WWTP will irrigate 100 dunum of farmland Spills, overflows and seepages are at plant level and can be contained there |

Detailed country specific ESIA and ESMP for the proposed project activities in Jordan and Lebanon , especially the constructed wetland can be found on the ROAS website

  - Environmental and social management plan

Content:

- Allocated roles and responsibilities environmental and social risk management / implement of the ESMP

- Opportunities for adaptive management

- Arrangements to supervise executing entities for implementation of ESMP

- Budget provision to manage environmental and social risks / implement of the ESMP

- Measures to avoid, minimize, or mitigate potential risks

- Risks monitoring system / indicators

- Grievance mechanism

Allocated roles and responsibilities for environmental and social risk management / implementation of the ESMP

The Regional Project Supervision Unit will be responsibility for environmental and social risks management, including implementation of the Project ESMP. An AF and UN-H policies and reporting compliance expert will be part of the RPSU. This expert will also supervise Project Execution Entities on the implementation of the Project ESMP. Guidelines showing how to comply to the AF ESP and GP will be shared with all execution entities and they will be guided on process, including monitoring. Also, a detailed action plan to comply to ESP and GP will be developed during the project inception phase.

A Safeguarding system compliance expert will also be part of the RPSU. Monitoring staff part of the RPSU will require having expertise in social risk management and be familiar with the AF safeguarding system. The RPSU will be backstopped by UN-Habitat HQ, with experts on climate change, human rights, environmental and social risks managements and gender policies.

In both Lebanon and Jordan government stakeholders responsible for compliance to national environmental and social policies and standards will be part of the Regional- and National-level Steering Committees, as well as government gender focal points.

This ESMP will allow country-specific management of the potential risks and impacts identified under in country-specific ESIA and ESMP reports (see link at beginning of this document). It is worth noting that an MoU is needed with Litani River Authority (LRA) for the success of the wetland activities (output 3.4.2). LRA is offering the land, and will be responsible for the operation of the wetland. Based on public consultation, the municipality of Bar Elias is not capable of operating and maintaining the wetland due to lack of financial resources, as well as technical know-how.

All project-related ToR’s and contracts will include clauses stating contractors will need to comply to the AF ESP, especially principle 1 (law), 4 (human rights), 5 (gender) and 6 and 13 (labour and safety) and the AF GP. This includes:

- Principle 1: References to standards and laws to which the activity will need to comply will be included in all legal agreements with all sub-contractors, including steps and responsibilities for compliance.

- Principle 4: References to relevant Humans rights declarations will be included in all legal agreements with all sub-contractors.

- Principle 5: Reference to relevant gender policies

- Principe 6: Employment and working conditions following ILO standards will be included in legal agreements with all sub-contractors.

- Principle 13: Ensure that ICSC international health and safety standards are clearly accessible and understood. e.g. by putting clearly visible signs detailing health and safety standards to be located at projects sites and by supplying protective equipment.

Opportunities for adaptive management

When changes in project activities or additional activities are required, these will need to go through a new risks screening and impact assessment process in compliance with AF, UN-habitat and national policies and standards. When this is required, this will be led by the RPSU and the Regional-level Project Steering Committee would need to approve the changes. As for opportunities, when allocated budgets for e.g. installing RWH systems allow targeted additional buildings for installing RWH systems, this would be possible following above process. Possible additional target buildings have already been identified.

Arrangements to supervise executing entities for implementation of ESMP

Table 41: Capacity of potential executing entities to carry-out gender responsive activities

| Potential executing entity | Skills and expertise to provide gender mainstreaming inputs | Specific requirements execution entities for compliance | Capacity building needs |
| --- | --- | --- | --- |
| UNICEF (Lebanon and Jordan) | Yes (UN core value) | - Appoint ESP a compliance and gender focal point - Capacity to comply to the AF ESP and implementation of the ESMP guided by UN-Habitat - Capacity to comply to the AF GP (see annex 4). | - Awareness on requirements - Share guidelines for execution entities to comply and to ensure ‘opportunities’ are identified and exploited |
| UN-ESCWA (Lebanon) | Yes (UN core value) |  |  |
| Litany River Authorities (Lebanon) | Limited (as government entity) | - Appoint ESP a compliance and gender focal point - Capacity to comply to the AF ESP and implementation of the ESMP guided by UN-Habitat - Capacity to comply to the AF GP (see annex 4). | - Awareness on requirements - Share guidelines for execution entities to comply and to ensure ‘opportunities’ are identified and exploited - Support development baseline and approach before project start + reporting requirements |
| Bekaa Water Establishment (Lebanon) |  |  |  |
| Lebanese Agriculture Research Institute (Lebanon) |  |  |  |
| WAJ / Yarmouk (Jordan) |  |  |  |
| BADIA FUND (Jordan) |  |  |  |
| Companies / consultancy firms | Limited (as company) | - Appoint ESP a compliance and gender focal point - Capacity to comply to the AF ESP and implementation of the ESMP guided by UN-Habitat - Capacity to comply to the AF GP (see annex 4). |  |
| JOHUD (Jordan) | Some (as NGO / institute) |  |  |
| Permaculture Research Institute (Jordan) |  |  |  |

Budget provision to manage environmental and social risks / implement of the ESMP

Dedicated safeguard compliance staff time is allocated under project execution fees for USD 42,000. Also, dedicated AF ESP and GP compliance staff time is allocated under MIE management fee for ROAS of USD 114,000. These persons will ensure compliance and develop ESP and GP compliance guidelines and action plans for execution entities and guide these execution entities through the process, including baselines and reporting requirements. Besides that measures are budgeted, through the execution entities, to supervise and monitoring proposed project activities, including e.g. water sampling, remote monitoring system of RWH and GWTR systems, etc. Costs for risks mitigation measures are integrated in the budget, including e.g. PV installation and water quality monitoring.

Measures to avoid, minimize, or mitigate potential risks

Table 42: Overview of project activities’ screening and assessment results against the 15 AF risk areas / principles, including measures to avoid or mitigate risks / impacts

| Project outputs / activities | Potential risk / impact | Impact assessment | Measures to avoid or mitigate risks / impacts | M & E arrangements |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Indicator and method | Responsibility and frequency |
| 3.1. Rooftop rainwater harvesting in Lebanon | Principle 13: Safe water: Water quality from RWH and GWTR systems does not comply to standards | 20 RWH systems with following direct beneficiaries: 8,753 (visitors, students) | Rainwater collected will be treated using sand and carbon filter, a micro filter, and chlorine. This will ensure water quality compliance. Note that tap water is not used for drinking or cooking. Water and roofs will be regularly monitored, especially at the start of the rainy season; Filter will be changed annually, as per supplier recommendation. The chlorine tank should not be empty so there will be no pumping of air that impacts water quality; Students and building staff will be made aware (through curriculum) of requirements of using water + involved in operation and maintenance; Remote monitoring systems will be installed | Water quality monitoring; Awareness raising campaign; O & M (training) reports with attendance lists and photos; checking of filters and chlorine tank Water quality monitoring; Awareness raising campaign; O & M (training) reports with attendance lists and photos; checking of filters and chlorine tank; Remote monitoring systems will be installed | UN-H in cooperation with execution entities / government entities and building management Check (compliance to tap water quality standards) – at least every 3 months Check filters and chlorine tank - annually |
| 3.2. Rooftop rainwater harvesting in Jordan |  | 86 RWH systems with following direct beneficiaries: 52,855 (visitors, students) |  |  |  |
| 3.3. Greywater treatment and reuse in Jordan |  | 40 GWRT with following direct beneficiaries: 39,582 (same as under output 3.1.) |  |  |  |
| 3.4. Efficient treatment and reuse of wastewater, incl. through wetlands, in Lebanon | Principle 13: Improved water (safe water): Water used for irrigation does not comply to quality standards / unmonitored irrigation water may reduce quality of crops Principle 12: Pollution. On-plant accidental spills, overflows, seepages and discharges of wastewater treatment may contaminate soil, groundwater or surface water from WWTP | Output 3.4.1. The Zahle WWTP treats 18,000m3 and irrigate 110-116 hectares of farmland Output 3.4.2. The wetlands (60,000m2) treats 6,000m3 and will irrigate 40-70 hectares of farmland | Although the project intervention aims to increase the quality of water for irrigation, regular testing of water quality is required and irrigation will only begin after testing; Farmers will be made aware of requirements for use + involved in operation and maintenance; For the wetlands, visual inspection of existence of mosquito breeding sites. In case of their presence, introduction of tilapia fish that feeds on the eggs. Carry out regular inspections and routine tests to avoid spills, overflows, seepages and discharge of low-quality water (see also water quality testing below); include detailed risks mitigation measures identified in country-specific ESIA-ESMP reports in construction, operation and maintenance plans; | Water quality monitoring of the effluent from the WWTP and wetlands. The level of treatment is tertiary. This needs to be checked on a regular basis. Checking mosquitos Monitoring of wastewater handling and possible spills, overflows and seepages. Construction and O & M report addressing above | UN-H in cooperation with execution entities / government entities Quality check (compliance with FAO guidelines for irrigation) – monthly Check standards for water quality, treatment and construction - monthly |
| 3.5. Efficient treatment and reuse of wastewater in Jordan |  | Output 3.5.1. Maerad WWTP will store 2000-3000 m3 of water and irrigate 60 dunum of farmland Output 3.5.2. Al Kaider WWTP will store 2000-3000 m3 of water and irrigate 60 dunum of farmland Output 3.5.3. Mafraq WWTP will irrigate 100 dunum of farmland Spills, overflows and seepages are at plant level and can be contained there |  |  |  |

* For more details see country-specific ESIA reports

Risks monitoring system / indicators

The environmental and social risks management approach includes monitoring of potential risks and implementation of risks mitigation measures. This monitoring program commensurate with project activities and will report on the monitoring results to the Fund in the mid-term, annual, and terminal performance reports. Monitoring will be done to ensure that actions are taken in a timely manner and to determine if actions are appropriately mitigating the risk / impact or if they need to be modified in order to achieve the intended outcome. Annual reporting will include information about the status of implementation of this ESMP, including those measures required to avoid, minimize, or mitigate environmental and social risks. The reports shall also include, if necessary, a description of any corrective actions that are deemed necessary.

The Regional Project Supervision Unit will be responsibility for environmental and social risks management, including monitoring of the implementation of the Project ESMP. An AF and UN-H policies and reporting compliance expert will be part of the RPSU. A Safeguarding system compliance expert will also be part of the RPSU. Monitoring staff part of the RPSU will require having expertise in social risk management and be familiar with the AF safeguarding system. Gender specific indicators and targets have been developed as shown in the results framework and annex 4. Specific budgets for for risks monitoring are covered by M & E staff time under the execution fee (USD 63,000 total).

Table 43: monitoring arrangements for general risks management

| Action | Indicator and method | Responsibility and frequency |
| --- | --- | --- |
| Monitoring of capacity execution entities to comply | - Guidelines and action plans shared - Monitoring reports comply to requirements | RPSU; within half a year from inception RPSU; when reports are required |
| Implementation of grievance mechanism | - Grievance mechanism information is at target locations (buildings, etc.) - Grievance mechanism information is shown on UN-Habitat project website | RPSU in coordination with execution entities; within half a year from inception RPSU in coordination with execution entities; within half a year from inception |
| Monitoring of measures to avoid or mitigate risks / impacts per output | - See table 42 above | RPSU in coordination with execution entities; when reports are required |

Grievance mechanism

UN-Habitat in coordination with the execution entities will implement a grievance mechanism in the target areas, which will allow an accessible, transparent, fair and effective means of communicating if there are any concerns regarding project design and implementation. Project employees, and people benefitting / affected by the project will be made aware of the grievance mechanism for any criticism or complaint of an activity.

This mechanism considers the special needs of different groups as well as gender considerations and potential environmental and social risks, especially human rights (as shown on posters). A combination of mailboxes (at community / building level) and telephoning options offer an immediate way for employees and people affected by the project to safely express their concerns. The options will allow local languages and offer the opportunity for and people affected by the project to complain or provide suggestions on how to improve project design and implementation, which will be reviewed and taken up by the project implementation team.

Project staff and execution entities will be made aware of the procedures for receiving messages and on the reporting of any grievances. In addition, monitoring activities allow project participants to voice their opinions or complaints as they may see fit.

The address and e-mail address of the Adaptation Fund will also be made public (i.e. project website, Facebook and mailbox) for anyone to raise concerns regarding the project. For country-specifics recommendations regarding the grievance mechanisms, see country specific ESIA-ESMPs.

ANNEX 6: Gender and youth approach and baseline

Purpose

The purpose of this specific ‘gender annex’ is to demonstrate (in an overview) how this project will comply to the AF GP. A gender approach and data baseline has been established, which is necessary at the project start against which implementation progress and results can be measured.

In line with UN-Habitat’s ESSP, the approach includes the identification and of promotion of economic, social and environmental benefits and opportunities for women and youth for each project activity (which can be seen as an additional safeguard area).

During project preparation a ‘gender assessment’ has been conducted to identify potential project gender equality and women's and youth empowerment issues, but also opportunities. The outcomes are summarized below, as well as arrangements that will be taken during project implementation to comply to the AF GP, including to show how the project contributes to improving gender equality, the empowerment of women and youth and the project interventions’ suitability to meet the adaptation needs of targeted women and men and youth.

Methodology

During the project preparation phase, potential gender equality and women’s and youth empowerment challenges and opportunities have been identified through initial data analysis / desk research, surveys and focus group discussions with women, youth and other groups. Through these methods, specific women and youth needs and perceptions were identified, as well as potential gender-related risks and impacts, including possible concerns regarding proposed project activities.

Specific considerations and phases

- Determinants for gender-responsive stakeholder consultations

Table 44: Stakeholders consulted to develop gender approach

| Type of stakeholder | Specific stakeholder |
| --- | --- |
| National government | #### Lebanon: Ministry of Social Affairs (MoSa) – to be invited to the SC - Jordan: Ministry of social development - to be invited to the SC |
| UN agencies | - UN Women - UNICEF |
| Community level | - Community consultations and focus group discussions with women and youth |

*See also part II.I

- Initial Gender Assessment

  - Data baseline – overview of disaggregated data (beneficiaries) in target areas.

Table 45: Data baseline – women and youth

| Project outputs | Lebanon |  |  |  | Jordan |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Direct |  | Indirect |  | Direct |  | Indirect |  |
|  | Women | Youth | Women | Youth | Women | Youth | Women | Youth |
| 1.1. | 192 | 72 | 217,475 | 23,733 |  |  |  |  |
| 1.2. | 96 | 36 | 84,815 | 9,256 |  |  |  |  |
| 1.3. |  |  |  |  | 180 | 67 | 415,44 | 259,107 |
| 2.1. | 27,689 | 2,950 | 154,582 | 16,548 |  |  |  |  |
| 2.2. |  |  |  |  | 26,420 | 19,385 | 415,44 | 259,107 |
| 2.3 |  |  |  |  | 21,940 | 15,646 |  |  |
| 2.4.1 | 416 | 85 | 94,705 | 10,140 |  |  |  |  |
| 2.4.2 | 600 | 300 | 35,514 | 3,802 |  |  |  |  |
| 2.5 |  |  |  |  | 5 | 2 | 5,342 | 2,972 |
| 2.6.1 | 864 | 93 | 94,705 | 10,140 |  |  |  |  |
| 2.6.2 | 320 | 34 | 35,514 | 3,802 |  |  |  |  |
| 2.7.1 |  |  |  |  | 200 | 150 | 4528 | 2474 |
| 2.7.2. |  |  |  |  | 180 | 120 | 814 | 498 |
| 2.8. |  |  |  |  | 150 | 45 | 11,500 | 60 |
| 3.1. | 27,689 | 2,950 | 154,582 | 16,548 |  |  |  |  |
| 3.2. |  |  |  |  | 26,420 | 19,385 | 415,44 | 259,107 |
| 3.3. |  |  |  |  | 21,940 | 15,646 |  |  |
| 3.4.1. | 2,013 | 216 | 94,705 | 10,140 |  |  |  |  |
| 2.4.2 | 1,184 | 127 | 35,514 | 3,802 |  |  |  |  |
| 2.5.1 |  |  |  |  | 31 | 20 | 3,789 | 1,980 |
| 2.5.2 |  |  |  |  | 31 | 20 | 739 | 494 |
| 2.5.3 |  |  |  |  | 35 | 20 | 814 | 498 |
| 3.6.1 | 2,293 | 540 | : 130,219 | 13,941 |  |  |  |  |
| 3.6.2. |  |  |  |  |  |  |  |  |
| 3.7.1 |  |  |  |  | 62 | 40 | 4,528 | 2,474 |
| 3.7.2 |  |  |  |  | 35 | 20 | 814 | 498 |
| 3.8. |  |  |  |  | 150 | 45 | 11,500 | 60 |
| 4.1. | 80 | 30 | Whole Mena region |  |  |  |  |  |
| 4.2. | 80 | 30 |  |  |  |  |  |  |
| 4.3. | 80 | 30 |  |  |  |  |  |  |
| Total | 80 | 30 |  |  |  |  |  |  |

  - Context:

Table 46: analysis of gender-specific legal and cultural / religious context

|  | Jordan | Lebanon |
| --- | --- | --- |
| Analysis of legal status of women | Jordan has seen important changes with regards to gender equality over the last decades. Work on women’s rights reached new levels following the ratification of the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) in 1992 and the establishment of the Jordanian National Commission for women (JNCW) in the same year. The indicators for women’s education and health show notable improvements. However, women’s participation in the formal labour market is low. Moreover, women are still not equal to men before the law. There have been several reforms of the Personal Status Law (the latest reform took place in 2010). Violence against women is not sufficiently addressed. The gender gap in politics persists despite introduced quotas for women. | Article 8 of the Lebanese Constitution asserts the equality of rights and duties of all citizens, regardless of gender.[1] Lebanon ratified the Convention on the Elimination of All forms of Discrimination against Women (CEDAW) in 1997 with reservations to Article 9(2), regarding nationality; several subparagraphs of Article 16(1), related to personal status laws; and Article 29(1), on the settlement of disputes.[2] Lebanon has published CEDAW in the official Gazette, giving it primacy over national laws, one of the few Arab countries to do so. The country has not yet ratified the Optional Protocol. |
| Analysis of cultural/religious status of women | Country falls into group 5 countries: has low equality in HDI achievements between women and men: absolute deviation from gender parity greater than 10 percent (HDI 95 out of 189) and scores ‘high’ on level of discrimination of women on the OECD gender index (with access to resources, civil liberties, and son bias). | Country falls into group 5 countries: has low equality in HDI achievements between women and men: absolute deviation from gender parity greater than 10 percent (HDI 80 out of 189) and scores ‘high’ on level of discrimination of women on the OECD gender index (with especially access to resources being an issue). |

  - Differentiated climate change impacts on men and women and their differentiated capacities do adopt to these, gender division of labour and gender-based power structures.

Table 47: Differentiated climate change impacts on men and women

| Country | Sector / Livelihood relevant to the project | Climate change impact | Gender and youth equality and empowerment issues, incl. specific Vulnerabilities / barriers to adapt | Capacity to adapt and opportunities for promoting a ‘women’ and ‘youth’ as agents of change |
| --- | --- | --- | --- | --- |
| Lebanon | Agriculture | Drought / less work | High dependency on agriculture sector for income; cultural and traditional barriers to negotiate salary and work conditions | Women organization |
|  | Water (domestic) | Drought / less work | Time consuming and involves safety risk (including harassment) to collect water and high financial burden to get water | Involve women and youth in water harvesting activities |
| Jordan | Agriculture | Drought / less work | High dependency on agriculture sector for income; cultural and tranditional barriers to negotiate salary and work conditions | Women organization |
|  | Water (domestic) | Drought / less work | Time consuming to collect water and high financial burden to get water. Physical and psychological stress to do house work (cleaning, laundry, etc.) once a week and mostly at night. | Collect water at home (through water harvesting) |

  - Capacity gaps affecting GP compliance

Table 48: Capacity of potential executing entities to carry-out gender responsive activities.

| Potential executing entity | Skills and expertise to provide gender mainstreaming inputs | Specific requirements execution entities for compliance | Capacity building needs |
| --- | --- | --- | --- |
| UNICEF (Lebanon and Jordan) | Yes (UN core value) | - Appoint gender focal point - Target women and youth for awareness and capacity building activities - Identity specific women and youth needs in roll-out project activities - Where realistic, use quota targets for women and youth participation in project activities - Highlight specific gender and youth considerations in knowledge management - Have a participatory (women and youth monitoring system) | - Awareness on requirements - Share guidelines for execution entities to comply |
| UN-ESCWA (Lebanon) | Yes (UN core value) |  |  |
| Litany River Authorities (Lebanon) | Limited (as government entity) | - Appoint gender focal point - Target women and youth for awareness and capacity building activities - Identity specific women and youth needs in roll-out project activities - Where realistic, use quota targets for women and youth participation in project activities - Have a participatory (women and youth monitoring system) | - Awareness on requirements - Share guidelines for execution entities to comply and to ensure ‘opportunities’ are identified and exploited - Develop baseline and approach before project start + report |
| Bekaa Water Establishment (Lebanon) |  |  |  |
| Lebanese Agriculture Research Institute (Lebanon) |  |  |  |
| WAJ / Yarmouk (Jordan) |  |  |  |
| BADIA FUND (Jordan) |  |  |  |
| Companies / consultancy firms | Limited (as company) | - Appoint gender focal point - Target women and youth for awareness and capacity building activities - Identity specific women and youth needs in roll-out project activities - Where realistic, use quota targets for women and youth participation in project activities - Highlight specific gender and youth considerations in knowledge management - Have a participatory (women and youth monitoring system) |  |
| JOHUD (Jordan) | Some (as NGO / institute) |  |  |
| Permaculture Research Institute (Jordan) |  |  |  |

  - Opportunities for promoting a ‘women’ and ‘youth’ as agents of change

Through community-level consultations, it was found that women in Jordan and Lebanon (from both host communities and DPs) have knowledge regarding the water use and (urban) farming. The project aims to utilizing women’s traditional knowledge by targeting women in community level skill building and trainings. Enhancing women and youth’s capacities for efficient water harvesting and grey water treatment and re-use will help address their vulnerabilities to water scarcity. In Jordan, permaculture training would secure a source of livelihoods for women. Opportunities include:

  - Have women, youth and Syrians participate in assessment and planning processes + monitoring

  - Include women and youth considerations / roles in strategies and plans

  - Target and strengthen women organizations

  - Women to be involved with O & M RWH in buildings

  - Youth to work with women on O & M RWH in buildings, esp. schools

  - Women and Youth to be involved with GWTR in mosques and schools

  - Women to be involved in permaculture activities as consultations have shown that they see it as a source of income and can develop business cases.

  - Youth to be target and if possible, lead awareness raising campaigns on adaptation to water scarcity.

- Project planning and design.

Table 49: Gender baseline, goals and activities. A detailed action plan will be developed at inception phase

| Project outputs | Disaggregated beneficiaries, gender specific issues and needs / baseline | Key gender goals (to improve equality) | Entry points (to integrate gender considerations / empower women / youth) | Suitable interventions to meet specific needs and built on women and youth skills and knowledge | Additional activities needed to ensure gender perspective, incl. potential risk mitigation measures | Specific ‘gender’ output Indicator | Specific ‘gender’ targets | Budget required and allocated |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1. | Limited participation women and youth and roles are not specified in plans | Women and youth to be involved in assessment and planning | Women and youth groups | Involve women and youth groups and have specific gender considerations in plans | Use quota if needed Check women and youth considerations in plans | % women and youth participation in assessment and planning Women and youth considerations in plans | Women: 40 % Youth: 15 % Specific mentioning | A dedicated safeguard compliance staff time is allocated under project execution fees for USD 42,000 Dedicated AF ESP and GP compliance staff time is allocated under MIE management fee for ROAS of USD 114,000 These persons will ensure compliance and develop ESP and GP compliance guidelines for execution entities (with support from UN-H HQ) |
| 1.2. |  |  |  |  |  |  |  |  |
| 1.3. |  |  |  |  |  |  |  |  |
| 2.1. | Women and youth should get a chance to be involved with RWH and GWTR activities | Involve women and youth in O & M and replication options; Youth to be involved in awareness | Women and / or youth focus point / lead in buildings |  | Follow-up on selected focal point | Focal point identified % youth participating in awareness campaigns | 1 per building Youth: 30 % |  |
| 2.2. |  |  |  |  |  |  |  |  |
| 2.3 |  |  |  |  |  |  |  |  |
| 2.6. | Farmers and workers, incl. Syrians and youth are targeted | Ensure Syrians and Lebanese are equally involved | Workers participate in water associations | Youth to be targeted for modern irrigation technique use capacity building | Use quota if needed | % Syrians and youth participation | Syrian: 15 % Youth: 30 % |  |
| 2.7. |  |  |  |  |  |  |  |  |
| 2.8. | Students are targeted of which most female | Females to participate in activities and curriculum | Female considerations in knowledge management | Female students to work with Syrian women | Follow-up on cooperation | % female students | Female: 60 % |  |
| 3.1. | Women and youth need to be involved with RWH and GWTR | Involve women and youth in O & M of systems | Women and / or youth focus point / lead in buildings |  | Follow-up on selected focal point | Focal point identified | 1 per building |  |
| 3.2. |  |  |  |  |  |  |  |  |
| 3.3. |  |  |  |  |  |  |  |  |
| 3.6. | Farmers and workers, incl. Syrians and youth are targeted | Ensure Syrians and Lebanese are equally involved | Workers participate, if possible, in project works | Youth to be targeted for modern irrigation technique establishment | Use quota if needed | % Syrians and youth participation | Syrian: 15 % Youth: 30 % |  |
| 3.7. |  |  |  |  |  |  |  |  |
| 3.8. | Employees could be female | Select (partially) female workers | Selection process |  | Follow-up on selection process | % female employees | 50 % |  |
| 4.1. | Limited involvement women | Women to participate in meetings | Quota / Steering committee | Have specific gender considerations in knowledge management | Use quota if needed | Women and youth considerations in KM | Specific mentioning |  |
| 4.2. |  |  |  |  |  |  |  |  |
| 4.3. | Women roles and youth are not specified in plans and knowledge management | Women and youth roles to be identified | Consider gender and youth issues and needs | Have specific gender considerations in knowledge management | Check women and youth considerations in plans | Women and youth considerations in plans / KM | Specific mentioning |  |

- Project implementation

UN-Habitat aims to have a gender responsive and adaptable management approach in place which, when needed, allows adjustment based on learning from earlier decisions and interventions and received feedback. This is done through having gender expertise and focal points in place, whom should identify challenges, barriers or restrictions that arise during project/programme implementation, which might hinder the equal participation of men and women in activities.

Capacities of execution entities will be built so they are able to provide gender mainstreaming inputs and identify any challenges that arise during project/programme implementation, which might hinder the equal participation of men and women in activities. This requires appointing a gender focal point and having quota targets for women and youth participation in project activities. Gender focal points from the government will be part of the steering committees.

The project Grievance mechanism established will be capable to accept grievances and complaints specifically related to gender equality and women's empowerment

- Performance Monitoring and Evaluation

The gender responsive management approach includes gender responsive monitoring and evaluation, which is participatory and where ‘gender disaggregated data’ will be collected and analysed. Where possible, women and youth will be encouraged to participate in monitoring activities.

- Knowledge Management, Information Sharing and Reporting

UN-Habitat aims to have a gender responsive knowledge management approach in place,  where specific gender considerations are highlighted through reporting on the project/programme’s commitment to gender equality and women’s empowerment in all outreach, communication and information sharing efforts.

ANNEX 6: Budget notes

Table 50: Budget notes

| Outputs | Activities |  | Notes / Staff | TOTAL | Year | Year | Year | Year |  | No |  | Rate | Year | Year | Year | Year |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 | 2 | 3 | 4 |  |  |  |  | 1 | 2 | 3 | 4 | T |
|  |  |  |  |  |  |  |  |  |  |  |  |  | 12 | 12 | 12 | 12 | 48 |
| Project components |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 Territorial planning and development strategy / guidelines at district level with climate change and gender mainstreamed (Lebanon) | Phase 1: assessment | Launching and discussing assessment approach and outcomes | Workshop | 4,000 | 4,000 | - | - | - |  | 1 |  | 2,000 | 2 |  |  |  | 2 |
|  |  | General methodology and framework | Spatial / urban planner | 28,000 | 28,000 | - | - | - |  | 2 |  | 3,500 | 4 |  |  |  | 4 |
|  |  | Climate change dynamics and mapping and analysis | Climate change expert | 7,000 | 7,000 | - | - | - |  | 1 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Urbanization dynamics mapping and analysis | Climate change expert + GIS expert | 7,000 | 7,000 | - | - | - |  | 1 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Agricultural dynamics mapping and analysis | Agriculture expert | 7,000 | 7,000 | - | - | - |  | 1 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Water issues mapping and analysis | Water expert | 7,000 | 7,000 | - | - | - |  | 1 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Soil issues mapping and analysis | Hydrology expert | 7,000 | 7,000 | - | - | - |  | 1 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Complementary field investigations | Field expert | 21,000 | 21,000 | - | - | - |  | 3 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Transversal analysis | Spatial / urban planner | 14,000 | 14,000 | - | - | - |  | 2 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Drafting phase 1 report: Assessment outcomes | Spatial / urban planner | 1,500 | 1,500 | - | - | - |  | 1 |  | 1,500 | 1 |  |  |  | 1 |
|  | Phase 2: planning scenarios | Identifying and projecting possible scenarios | Spatial / urban planner + GIS expert | 21,000 | 21,000 | - | - | - |  | 3 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Discussing and adopting most probable scenario | Spatial / urban planner + Workshop | 9,000 | 9,000 | - | - | - |  | 2 |  | 3,500 | 1 |  |  |  | 1 |
|  |  | Defining main needed adaptation responses to this scenario | Spatial / urban planner - CC, Agri, Wa exp | 28,000 | 28,000 | - | - | - |  | 4 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Setting a monitoring framework (follow up indicators, etc.) | Spatial / urban planner | 3,500 | 3,500 | - | - | - |  | 1 |  | 3,500 | 1 |  |  |  | 1 |
|  |  | Contingency roadmap for sudden changes in adopted scenario | Spatial / urban planner - CC, Agri, Wa exp | 14,000 | 14,000 | - | - | - |  | 4 |  | 3,500 | 1 |  |  |  | 1 |
|  |  | Drating Phase 2 report: Planning / development scenarios | Spatial / urban planner | 3,500 | 3,500 | - | - | - |  | 1 |  | 3,500 | 1 |  |  |  | 1 |
|  | Phase 3: implement strategy / guidelines | Strategy / guidelines for BWE | Spatial / urban planner | 14,000 | 14,000 | - | - | - |  | 2 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Strategy / guidelines for DGU | Spatial / urban planner | 14,000 | 14,000 | - | - | - |  | 2 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Strategy / guidelines MoA | Spatial / urban planner | 14,000 | 14,000 | - | - | - |  | 2 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Training BWE, DGU, MoA on use of guidelines | Spatial / urban planner | 14,000 | 14,000 | - | - | - |  | 2 |  | 3,500 | 2 |  |  |  | 2 |
|  |  | Drafting Phase 3 report: Strategy / guidelines | Spatial / urban planner | 3,500 | 3,500 | - | - | - |  | 1 |  | 3,500 | 1 |  |  |  | 1 |
|  |  | Presenting and discussing outcomes | Workshop | 2,000 | 2,000 | - | - | - |  | 1 |  | 2,000 | 1 |  |  |  | 1 |
|  |  | Communication / publication | Printing, etc. | 5,000 | 5,000 | - | - | - |  | 1 |  | 5,000 | 1 |  |  |  | 1 |
| Sub-total |  |  |  | 249,000 | 249,000 | - | - | - |  |  |  |  |  |  |  |  |  |
| Output 1.2. Urban master plans at municipal level with climate change and gender mainstreamed (Lebanon) | Phase 1: assessment | Launching, participatory and assessment session | Workshop | 64,000 | 64,000 | - | - | - |  | 8 |  | 2,000 | 4 |  |  |  | 4 |
|  |  | Mapping dynamics in 8 municipalities | Spatial / urban planner / GIS expert | 56,000 | 49,000 | 7,000 | - | - |  | 2 |  | 3,500 | 7 | 1 |  |  | 8 |
|  |  | CC / Water/ Agri / Soil risks and opportunities | CC, Wa, Agri, Hydro exp | 72,000 | 60,000 | 12,000 | - | - |  | 4 |  | 3,000 | 5 | 1 |  |  | 6 |
|  |  | Drafting Phase 1 assessment reports for the 8 municipalities | Spatial / urban planner | 21,000 | - | 21,000 | - | - |  | 3 |  | 3,500 |  | 2 |  |  | 2 |
|  | Phase 2: plan | Development orientations and land use strategies | Spatial / urban planner | 28,000 | - | 28,000 | - | - |  | 2 |  | 3,500 |  | 4 |  |  | 4 |
|  |  |  | Workshop | 16,000 | - | 16,000 | - | - |  | 8 |  | 2,000 |  | 1 |  |  | 1 |
|  |  | Drafting Phase 2 proposition strategies for the 8 municipalities | Spatial / urban planner | 21,000 | - | 21,000 | - | - |  | 3 |  | 3,500 |  | 2 |  |  | 2 |
|  | Phase 3a: Complement | Planning complementarity at the level of the Central Bekaa | Spatial / urban planner | 21,000 | - | 21,000 | - | - |  | 3 |  | 3,500 |  | 2 |  |  | 2 |
|  |  |  | Workshop | 4,000 | - | 4,000 | - | - |  | 2 |  | 2,000 |  | 1 |  |  | 1 |
|  |  | Drafting Phase 3 report: complementary | Spatial / urban planner | 3,500 | - | 3,500 | - | - |  | 1 |  | 3,500 |  | 1 |  |  | 1 |
|  | Phase 3b: Implement | Localized action plans and conceiving potential urban design interventions | Spatial / urban planner | 10,500 | - | 10,500 | - | - |  | 1 |  | 3,500 |  | 3 |  |  | 3 |
|  |  |  | Urban Designer | 10,500 |  | 10,500 | - | - |  | 1 |  | 3,500 |  | 3 |  |  | 3 |
|  |  |  | Water Expert | 3,500 |  | 3,500 | - | - |  | 1 |  | 3,500 |  | 1 |  |  | 1 |
|  |  |  | Agricultural Expert |  |  | 3,500 | - | - |  | 1 |  | 3,500 |  | 1 |  |  | 1 |
|  |  |  | CC and DRR Expert | 3,500 | - | 3,500 | - | - |  | 1 |  | 3,500 |  | 1 |  |  | 1 |
|  |  |  | Field investigators |  |  | 9,000 | - | - |  | 2 |  | 1,500 |  | 3 |  |  | 3 |
|  |  | Drafting Phase 4 report: action plans and feasibility assessments | Spatial / urban planner | 7,000 | - | 7,000 | - | - |  | 1 |  | 3,500 |  | 2 |  |  | 2 |
|  |  | Communication / publication | Printing, etc. | 12,000 | - | 12,000 | - | - |  | 8 |  | 2,000 |  | 1 |  |  | 1 |
| Sub-total |  |  |  | 366,000 | 173,000 | 193,000 | - | - |  |  |  |  |  |  |  |  |  |
| Output 1.3. Urban master plans at municipal level with climate change and gender mainstreamed (Jordan) | Phase 1: assessment | Launching, participatory and assessment session | Workshop | 64,000 | 64,000 | - | - | - |  | 8 |  | 2,000 | 4 |  |  |  | 4 |
|  |  | Mapping dynamics in 2 municipalities (Mafraq; Irbid) | Spatial / urban planner / GIS expert | 56,000 | 49,000 | 7,000 | - | - |  | 2 |  | 3,500 | 7 | 1 |  |  | 8 |
|  |  | CC / Water/ Agri / Soil risks and opportunities | CC, Wa, Agri, Hydro exp | 72,000 | 60,000 | 12,000 | - | - |  | 4 |  | 3,000 | 5 | 1 |  |  | 6 |
|  |  | Drafting Phase 1 assessment reports for the 2 municipalities | Spatial / urban planner | 21,000 | - | 21,000 | - | - |  | 3 |  | 3,500 |  | 2 |  |  | 2 |
|  | Phase 2: plan | Development orientations and land use strategies | Spatial / urban planner | 28,000 | - | 28,000 | - | - |  | 2 |  | 3,500 |  | 4 |  |  | 4 |
|  |  |  | Workshop | 16,000 | - | 16,000 | - | - |  | 8 |  | 2,000 |  | 1 |  |  | 1 |
|  |  | Drafting Phase 2 proposition strategies for the 2 municipalities | Spatial / urban planner | 21,000 | - | 21,000 | - | - |  | 3 |  | 3,500 |  | 2 |  |  | 2 |
|  | Phase 3a: Complement | Planning complementarity at the water authorities level | Spatial / urban planner | 21,000 | - | 21,000 | - | - |  | 3 |  | 3,500 |  | 2 |  |  | 2 |
|  |  |  | Workshop | 4,000 | - | 4,000 | - | - |  | 2 |  | 2,000 |  | 1 |  |  | 1 |
|  |  | Drafting Phase 3 report: complementary | Spatial / urban planner | 3,500 | - | 3,500 | - | - |  | 1 |  | 3,500 |  | 1 |  |  | 1 |
|  | Phase 3b: Implement | Llocalized action plans and conceiving potential urban design interventions | Spatial / urban planner | 10,500 | - | 10,500 | - | - |  | 1 |  | 3,500 |  | 3 |  |  | 3 |
|  |  |  | Urban Designer | 10,500 |  | 10,500 | - | - |  | 1 |  | 3,500 |  | 3 |  |  | 3 |
|  |  |  | Water Expert | 3,500 |  | 3,500 | - | - |  | 1 |  | 3,500 |  | 1 |  |  | 1 |
|  |  |  | Agricultural Expert |  |  | 3,500 | - | - |  | 1 |  | 3,500 |  | 1 |  |  | 1 |
|  |  |  | CC and DRR Expert | 3,500 | - | 3,500 | - | - |  | 1 |  | 3,500 |  | 1 |  |  | 1 |
|  |  |  | Field investigators |  |  | 9,000 | - | - |  | 2 |  | 1,500 |  | 3 |  |  | 3 |
|  |  | Drafting Phase 4 report: action plans and feasibility assessments | Spatial / urban planner | 7,000 | - | 7,000 | - | - |  | 1 |  | 3,500 |  | 2 |  |  | 2 |
|  |  | Communication / publication | Printing, etc. | 12,000 | - | 12,000 | - | - |  | 8 |  | 2,000 |  | 1 |  |  | 1 |
| Sub-total |  |  |  | 366,000 | 173,000 | 193,000 | - | - |  |  |  |  |  |  |  |  |  |
| TOTAL Component 1 |  |  |  | 981,000 | 595,000 | 386,000 | - | - |  |  |  |  |  |  |  |  |  |
| Output 2.1 Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1: Rooftop Rain Water Harvesting (RWH) in Lebanon | Phase 1: assessment | Detailed technical assessment of target buildings (UNICEF) | Site assessments | 2,000 | 2,000 | - | - | - |  | 1 |  | 100 | 20 |  |  |  | 20 |
|  |  |  | RWH specialist / field engineer | 3,000 | 3,000 | - | - | - |  | 1 |  | 3,000 | 1 |  |  |  | 1 |
|  | Phase 2: plan | Detailed technical design of systems (UNICEF) | RWH specialist | 12,000 | 12,000 | - | - | - |  | 1 |  | 3,000 | 4 |  |  |  | 4 |
|  | Phase 4: O & M | Awareness raising and capacity building focused on water scarcity challenges in target buidlings (LARI/ Private Sector) | Awareness raising campaign in target buildings about climate change-related water scarcity challenges and adaptation options, incl. RWH through religious & governmental buildings, and educational & health facilities | 25,000 | 5,000 | 10,000 | 10,000 | - |  | 1 |  | 5,000 | 1 | 2 | 2 |  | 5 |
|  |  | Awareness raising and capacity building to operate and maintain project activities (LARI/ Private Sector) | Training sessions / workshops on O&M for the target building staff, and municipalities' staff + Operation & Maintenance manuals for target Municipalities | 45,000 | - | 15,000 | 15,000 | 15,000 |  | 1 |  | 1,500 |  | 10 | 10 | 10 | 30 |
|  |  |  | Evaluating water use for urban usages study | 15,000 | - | - | - | 15,000 |  | 1 |  | 15,000 |  |  |  | 1 | 1 |
|  |  |  | Operation & maintenance plans for target buidings | 12,600 | - | 6,300 | 6,300 | - |  | 1 |  | 150 |  | 42 | 42 |  | 84 |
|  |  |  | Operation & maintenance plan at municipal / ministerial level | 3,000 | - | - | 3,000 | - |  | 1 |  | 3,000 |  |  | 1 |  | 1 |
|  |  |  | Central and remote sensor and control unit for each site (for monitoring) | 20,000 | - | 10,000 | 10,000 | - |  | 1 |  | 1,000 |  | 10 | 10 |  | 20 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to repicate and scale-up project activities | Replication / upscaling plan and guidelines to operate, maintain, sustain and replicate the RWH systems beyond the project | 15,000 | - | - | - | 15,000 |  | 1 |  | 15,000 |  |  |  | 1 | 1 |
|  | Technical support and coordination | Sub-project Coordination and technical support (UNICEF) | Sub-project coordination / communication (50 %) | 24,800 | 6,200 | 6,200 | 6,200 | 6,200 |  | 0.5 |  | 3,100 | 4 | 4 | 4 | 4 | 16 |
|  |  |  | Technical support to execute above activities (50 %) | 15,000 | 3,750 | 3,750 | 3,750 | 3,750 |  | 0.5 |  | 2,500 | 3 | 3 | 3 | 3 | 12 |
|  |  |  | Logistics, admin and accountancy (50 %) | 3,000 | 750 | 750 | 750 | 750 |  | 0.5 |  | 1,500 | 1 | 1 | 1 | 1 | 4 |
| Sub-total |  |  |  | 177,400 | 28,200 | 47,500 | 50,500 | 51,200 |  |  |  |  |  |  |  |  |  |
| Output 2.2. Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.1: Rooftop Rain Water Harvesting (RWH) in Jordan | Phase 1: assessment | Detailed technical assessment of target buildings (84, of which 18 rehabilitation) | Site assessments (coordinate with output 2.3) | 4,200 | 4,200 | - | - | - |  | 1 |  | 50 | 84 |  |  |  | 84 |
|  |  |  | RWH specialist / field engineer (coordinate with output 2.3) | 6,000 | 6,000 | - | - | - |  | 1 |  | 1,500 | 4 |  |  |  | 4 |
|  | Phase 2: plan | Detailed technical design of systems (84, of which 18 rehabilitation) | RWH specialist / field engineer (coordinate with output 2.3) | 9,000 | 9,000 | - | - | - |  | 1 |  | 1,500 | 6 |  |  |  | 6 |
|  | Phase 4: O & M | Awareness raising and capacity building to operatate and maintain systems (84, of which 40 both RWH and GWTR) in target buildings | Training sessions / workshops on O&M for the target building staff, official departments and directorates, ministries' and municipalities' staff (coordinate with output 2.3) | 56,400 | - | 25,200 | 25,200 | 6,000 |  | 1 |  | 600 |  | 42 | 42 | 10 | 94 |
|  |  |  | Operation & maintenance plans for target buidings (coordinate with output 2.3) | 12,600 | - | 6,300 | 6,300 | - |  | 1 |  | 150 |  | 42 | 42 |  | 84 |
|  |  |  | Operation & maintenance plan at municipal / ministerial level (coordinate with output 2.3) | 3,000 | - | - | 3,000 | - |  | 1 |  | 3,000 |  |  | 1 |  | 1 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to repicate and scale-up project activities | Under output 2.3. | - | - | - | - | - |  |  |  |  |  |  |  |  | 0 |
|  | Technical support and coordination | Sub-project Coordination and technical support (Johud) | Sub-project coordination (50 %) | 30,000 | 7,500 | 7,500 | 7,500 | 7,500 |  | 0.5 |  | 2,500 | 6 | 6 | 6 | 6 | 24 |
|  |  |  | Technical support to execute activities (50 %) | 15,000 | 3,750 | 3,750 | 3,750 | 3,750 |  | 0.5 |  | 2,500 | 3 | 3 | 3 | 3 | 12 |
|  |  |  | Logistics, admin and accountancy (50 %) | 3,000 | 750 | 750 | 750 | 750 |  | 0.5 |  | 1,500 | 1 | 1 | 1 | 1 | 4 |
| Sub-total |  |  |  | 139,200 | 31,200 | 43,500 | 46,500 | 18,000 |  |  |  |  |  |  |  |  |  |
| Output 2.3. Community organization, awareness and capacity building + operation, maintenance and replication / upscaling plans for concrete adaptation output 3.3: Grey Water Treatment and Reuse (GWTR) in Jordan | Phase 1: assessment | Detailed technical assessment of target buildings (40) | Site assessments (coordinate with output 2.2) | 2,000 | 2,000 | - | - | - |  | 1 |  | 50 | 40 |  |  |  | 40 |
|  |  |  | GWTR specialist / field engineer (coordinate with output 2.2) | 6,000 | 6,000 | - | - | - |  | 1 |  | 1,500 | 4 |  |  |  | 4 |
|  | Phase 2: plan | Detailed technical design of systems (40) | GWTR specialist / field engineer (coordinate with output 2.2) | 9,000 | 9,000 | - | - | - |  | 1 |  | 1,500 | 6 |  |  |  | 6 |
|  | Phase 4: O & M | Awareness raising and capacity building to operatate and maintain system (84, of which 40 both RWH and GWTR) in target buildings | Awareness raising campaign in target municipalities and target buildings about climate change-related water scarcity challenges and adaptation options, incl. RWH and GWR through Imams and curriculum in schools (coordinate with output 2.2) | 42,000 | - | 21,000 | 21,000 | - |  | 1 |  | 500 |  | 42 | 42 |  | 84 |
|  |  |  | Under output 2.2. | - | - | - | - | - |  |  |  |  |  |  |  |  | 0 |
|  |  |  | Under output 2.2. | - | - | - | - | - |  |  |  |  |  |  |  |  | 0 |
|  |  |  | Under output 2.2. | - | - | - | - | - |  |  |  |  |  |  |  |  | 0 |
|  |  |  | Central and remote sensor and control unit for each site (for monitoring) (coordinate with output 2.2) | 84,000 | - | 42,000 | 42,000 | - |  | 1 |  | 1,000 |  | 42 | 42 |  | 84 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to repicate and scale-up project activities | Replication / upscaling plan and guidelines to operate, maintain, sustain and replicate the GWTR systems beyond the project, incl school curriculum (coordinate with output 2.2) | 15,000 | - | - | - | 15,000 |  | 1 |  | 15,000 |  |  |  | 1 | 1 |
|  | Technical support and coordination | Sub-project coordination and technical support (UNICEF Jordan) | Sub-project coordination (100 %) | 40,000 | 10,000 | 10,000 | 10,000 | 10,000 |  | 1 |  | 2,500 | 4 | 4 | 4 | 4 | 16 |
|  |  |  | Technical support to execute above activities (100 %) | 30,000 | 7,500 | 7,500 | 7,500 | 7,500 |  | 1 |  | 2,500 | 3 | 3 | 3 | 3 | 12 |
|  |  |  | Logistics, admin and accountancy (100 %) | 6,000 | 1,500 | 1,500 | 1,500 | 1,500 |  | 1 |  | 1,500 | 1 | 1 | 1 | 1 | 4 |
| Sub-total |  |  |  | 234,000 | 36,000 | 82,000 | 82,000 | 34,000 |  |  |  |  |  |  |  |  |  |
| Output 2.4.1 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.4: Efficient treatment and reuse of wastewater,from Zahle WWTP, in Lebanon | Phase 1: assessment | Detailed technical assessment of the irrigation canal and surrounding agricultural areas (RTO) | Site assessments + Surveying public opinion of farmers in accepting reused wastewater | 9,000 | 9,000 | - | - | - |  | 1 |  | 1,500 | 6 |  |  |  | 6 |
|  |  |  | Civil/ Agricultural Engineer | 13,200 | 13,200 | - | - | - |  | 1 |  | 2,200 | 6 |  |  |  | 6 |
|  | Phase 2: plan | Detailed technical design of the open canal | Civil/ Agricultural Engineer | 13,200 | 13,200 | - | - | - |  | 1 |  | 2,200 | 6 |  |  |  | 6 |
|  | Phase 4: O & M | Surveys and studies developed for understanding adaptation measures in Zahle (BWE/ Private Sector) | Development of public awareness to encourage acceptance of treated waste water and to focus on water scarcity issues in Zahle for 1,000 farmers | 25,000 | 5,000 | 10,000 | 10,000 | - |  | 1 |  | 5,000 | 1 | 2 | 2 |  | 5 |
|  |  | Awareness raising and capacity building to operatate and maintain project activities (LRA/ Private Sector) | Training sessions / workshops / Manuals and Tools on O&M for the BWE and the Municipality of Zahle | 4,500 | - | 1,500 | 1,500 | 1,500 |  | 1 |  | 1,500 |  | 1 | 1 | 1 | 3 |
|  |  |  | Regular effluent sampling and testing of the Zahle WWTP | 50,400 | 14,400 | 14,400 | 14,400 | 7,200 |  | 1 |  | 1,200 | 12 | 12 | 12 | 6 | 42 |
|  |  |  | Operation & maintenance plans for target farmers | 4,000 | - | - | 2,000 | 2,000 |  | 1 |  | 2,000 |  |  | 1 | 1 | 2 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to replicate and scale-up project activities | Replication / upscaling plan and guidelines to operate, maintain, sustain and replicate wastewater reuse and to ensure proper tariffs through a socio-economic study (Private Sector) | 25,000 | - | - | 25,000 | - |  | 1 |  | 25,000 |  |  | 1 |  | 1 |
|  | Technical support and coordination | Sub-project Coordination and technical support (RTO) | Sub-project coordination (33 %) | 10,800 | 3,600 | 3,600 | 3,600 | - |  | 0.3 |  | 3,000 | 4 | 4 | 4 |  | 12 |
|  |  | Supervision of the awareness campaigns implementation and development (RTO) | Community Mobilizer (33 %) | 8,100 | 2,700 | 2,700 | 2,700 | - |  | 0.3 |  | 1,500 | 6 | 6 | 6 |  | 18 |
|  |  | Sub-total Zahle WWTP |  | 163,200 | 61,100 | 32,200 | 59,200 | 10,700 |  |  |  |  |  |  |  |  |  |
| Output 2.4.2 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.4: Efficient treatment and reuse of wastewater,through wetlands, in Lebanon | Phase 1: assessment | Detailed technical assessment of plot allocated for Wetlands (UNICEF) | Site assessments - Water Quality Sampling and Testing of Ghezayel River (BWE/ Private Sector) | 15,000 | 15,000 | - | - | - |  | 1 |  | 5,000 | 3 |  |  |  | 3 |
|  |  |  | FWS specialist / field engineer | 18,000 | 18,000 | - | - | - |  | 1 |  | 3,000 | 6 |  |  |  | 6 |
|  | Phase 2: plan | Detailed technical design of the FWS constructed Wetland in Bar Elias (UNICEF) | FWS specialist | 27,000 | 27,000 | - | - | - |  | 1 |  | 3,000 | 9 |  |  |  | 9 |
|  | Phase 4: O & M | Awareness raising and capacity building focused on water scarcity challenges and Waste Water reuse in Bar Elias (LRA/ Private Sector) | Development of public awareness to encourage acceptance of treated waste water and to focus on water scarcity issues in Bar Elias for more than 3,000 farmers | 25,000 | 5,000 | 10,000 | 10,000 | - |  | 1 |  | 5,000 | 1 | 2 | 2 |  | 5 |
|  |  | Awareness raising and capacity building to operatate and maintain project activities (LRA/ Private Sector) | Operation and maintenance cost of constructed Wetland in Bar Elias (monitoring FWS (water quality, microbial diversity, dissolved oxygen, electrical conductivity, total suspended solids, chemical oxygen demand, TKN)) | 30,000 | - | - | 10,000 | 20,000 |  | 1 |  | 10,000 |  |  | 1 | 2 | 3 |
|  |  |  | Training sessions / workshops / guidelines booklet on O&M for the LRA and Bar Elias staff | 4,500 | - | - | 4,500 | - |  | 1 |  | 4,500 |  |  | 1 |  | 1 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to repicate and scale-up project activities (LRA) | Replication / upscaling plan and guidelines to operate, maintain, sustain and replicate Wetlands all along the Litany River stream for 10 Municipalities in coordination with LRA | 15,000 | - | - | - | 15,000 |  | 1 |  | 1,500 |  |  |  | 10 | 10 |
|  | Technical support and coordination | Sub-project Coordination and technical support (UNICEF) | Sub-project coordination / communication (50 %) | 18,600 | 6,200 | 6,200 | 6,200 | - |  | 0.5 |  | 3,100 | 4 | 4 | 4 | 4 | 12 |
|  |  |  | Technical support to execute above activities (50 %) | 15,000 | 3,750 | 3,750 | 3,750 | 3,750 |  | 0.5 |  | 2,500 | 3 | 3 | 3 | 3 | 12 |
|  |  |  | Logistics, admin and accountancy (50 %) | 6,000 | 1,500 | 1,500 | 1,500 | 1,500 |  | 0.5 |  | 1,500 | 1 | 1 | 1 | 1 | 8 |
|  |  | Sub-total Wetlands |  | 153,100 | 71,200 | 16,200 | 30,700 | 35,000 |  |  |  |  |  |  |  |  |  |
| Sub-total |  |  |  | 316,300 | 132,300 | 48,400 | 89,900 | 45,700 |  |  |  |  |  |  |  |  |  |
| Output 2.5. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.5: Efficient treatment and reuse of wastewater in Jordan | Phase 3: Implement | Concrete intervention see output 3.5 |  | - | - | - | - | - |  | 1 |  |  |  |  |  |  | 0 |
|  | Phase 4: O & M | Operatate and maintain project activities. | Operation & maintenance plans for proposed interventions. Some spare parts are provided under ouput 3.5 | 6,000 | - | - | 6,000 | - |  | 1 |  | 6,000 |  |  | 1 |  | 1 |
|  | Phase 5: Replicate + Scale-up | Capacity building to repiicate and scale-up sub-project activities | Replication / upscaling plan and guidelines to operate, maintain, sustain and replicate cc resilient WWTPs beyond the project | 10,000 | - | - | - | 10,000 |  | 1 |  | 10,000 |  |  |  | 1 | 1 |
|  | Technical support and coordination | In kind |  | - | - | - | - | - |  | 1 |  |  |  |  |  |  | 0 |
| Sub-total |  |  |  | 16,000 | - | - | 6,000 | 10,000 |  |  |  |  |  |  |  |  |  |
| Output 2.6.1 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.6.1 Water-use-efficient irrigation of treated wastewater for fruit trees in Lebanon from Zahle WWTP, Lebanon | Phase 1: assessment | Detailed technical assessment of agricultural fruit lands and irrigation systems (RTO) | Site assessments and visits to farmers | 6,000 | 6,000 | - | - | - |  | 1 |  | 100 | 60 |  |  |  | 60 |
|  |  |  | Civil/ Agricultural engineer | 4,400 | 4,400 | - | - | - |  | 1 |  | 2,200 | 2 |  |  |  | 2 |
|  | Phase 2: plan | Detailed technical design of the drip irrigation systems | Irrigation specialist | 5,000 | 5,000 | - | - | - |  | 1 |  | 5,000 | 1 |  |  |  | 1 |
|  | Phase 4: O & M | Awareness raising and capacity building trainings (LARI) | Workshop on installing and operating drip irrigation systems with practical field demonstration | 15,000 | 7,500 | 7,500 | - | - |  | 1 |  | 7,500 | 1 | 1 |  |  | 2 |
|  |  | Awareness raising and capacity building to operate and maintain project activities (LARI/ Private Sector) | Awareness raising campaign in Zahle about climate change-related water scarcity challenges and adaptation options, incl. Fertigation awareness for fuit trees through workshops | 8,000 | - | 4,000 | 4,000 | - |  | 1 |  | 4,000 |  | 1 | 1 |  | 2 |
|  |  |  | Development of existing agricultural cooperatives, technical assistance in selecting crops, irrigation methods (LARI) | 15,000 | - | - | 15,000 | - |  | 1 |  | 15,000 |  |  | 1 |  | 1 |
|  |  |  | Training sessions / workshops / Tools on O&M for the target farmers | 2,500 | - | - | 2,500 | - |  | 1 |  | 2,500 |  |  | 1 |  | 1 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to replicate and scale-up project activities (LARI/ Private Sector) | Replication / upscaling plan and guidelines to operate, maintain, sustain and replicate smart and efficient drip irrigation techniques and to investigate permaculture guidelines and testing in the Central Bekaa area | 25,000 | - | - | 25,000 | - |  | 1 |  | 25,000 |  |  | 1 |  | 1 |
|  | Technical support and coordination | Sub-project Coordination and technical support (RTO) | Project coordindination (33 %) | 43,200 | 10,800 | 10,800 | 10,800 | 10,800 |  | 0.3 |  | 3,000 | 12 | 12 | 12 | 12 | 48 |
|  |  | Supervision of the awareness campaigns implementation and development (RTO) | Community Mobilizer (33 %) | 18,000 | 4,500 | 4,500 | 4,500 | 4,500 |  | 0.3 |  | 1,500 | 12 | 12 | 12 | 12 | 48 |
|  |  | Sub-total irrigtaion of fruit trees |  | 142,100 | 38,200 | 26,800 | 61,800 | 15,300 |  |  |  |  |  |  |  |  |  |
| Output 2.6.2 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.6.2.Water-use-efficient irrigation of treated wastewater for potato crops in Lebanon n | Phase 1: assessment | Detailed technical assessment of agricultural potato lands and irrigation systems (RTO) | Site assessments and visits to farmers | 6,000 | 6,000 | - | - | - |  | 1 |  | 100 | 60 |  |  |  | 60 |
|  |  |  | Civil/ Agricultural engineer | 4,400 | 4,400 | - | - | - |  | 1 |  | 2,200 | 2 |  |  |  | 2 |
|  | Phase 2: plan | Detailed technical design of the drip irrigation systems | Irrigation specialist | 5,000 | 5,000 | - | - | - |  | 1 |  | 5,000 | 1 |  |  |  | 1 |
|  | Phase 4: O & M | Awareness raising and capacity building trainings (LARI) | Workshop on replacing sprinklers with drip with practical field demonstration | 10,000 | 5,000 | 5,000 | - | - |  | 1 |  | 5,000 | 1 | 1 |  |  | 2 |
|  |  | Awareness raising and capacity building to operate and maintain project activities (LARI/ Private Sector) | Awareness raising campaign in Zahle about climate change-related water scarcity challenges and adaptation options, incl. Fertigation awareness for potato crops through workshops | 6,000 | - | 3,000 | 3,000 | - |  | 1 |  | 3,000 |  | 1 | 1 |  | 2 |
|  |  |  | Development of existing agricultural cooperatives, technical assistance in selecting crops, irrigation methods (LARI) | 15,000 | - | - | 15,000 | - |  | 1 |  | 15,000 |  |  | 1 |  | 1 |
|  |  |  | Training sessions / workshops / Tools on O&M for the target farmers | 2,000 | - | - | 2,000 | - |  | 1 |  | 2,000 |  |  | 1 |  | 1 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to replicate and scale-up project activities (LARI/ Private Sector) | Replication / upscaling plan and guidelines to operate, maintain, sustain and replicate smart and efficient drip irrigation techniques and to investigate permaculture guidelines and testing in the Central Bekaa area | 25,000 | - | - | 25,000 | - |  | 1 |  | 25,000 |  |  | 1 |  | 1 |
|  | Technical support and coordination | Sub-project Coordination and technical support (RTO) | Project coordination (33 %) | 43,200 | 10,800 | 10,800 | 10,800 | 10,800 |  | 0.3 |  | 3,000 | 12 | 12 | 12 | 12 | 48 |
|  |  | Supervision of the awareness campaigns implementation and development (RTO) | Community Mobilizer (33 %) | 18,000 | 4,500 | 4,500 | 4,500 | 4,500 |  | 0.3 |  | 1,500 | 12 | 12 | 12 | 12 | 48 |
|  |  | Sub-total irrigation of potato crops |  | 134,600 | 35,700 | 23,300 | 60,300 | 15,300 |  |  |  |  |  |  |  |  |  |
| Sub-total |  |  |  | 276,700 | 73,900 | 50,100 | 122,100 | 30,600 |  |  |  |  |  |  |  |  |  |
| Output 2.7.1 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7:Water-use Efficient irrigation of treated wastewater from Maerad and Al Kaider WWTPs in Jordan | Phase 1: assessment | Formulate a rehabilitation study for individual farm (40) end-user/Groups based on agreed-upon climate change resilient/irrigation water need/use, cropping patterns | Preparation visits | 4,000 | 4,000 | - | - | - |  | 1 |  | 100 | 40 |  |  |  | 40 |
|  |  |  | Stakeholder sessions / workshops | 2,800 | 2,800 | - | - | - |  | 1 |  | 700 | 4 |  |  |  | 4 |
|  | Phase 2: plan | Water user associations established (Al-Akaidr and Al Maerad) | Preparation visits | 1,200 | 1,200 | - | - | - |  | 1 |  | 100 | 12 |  |  |  | 12 |
|  |  |  | Stakeholder sessions / workshops | 2,800 | 2,800 | - | - | - |  | 1 |  | 700 | 4 |  |  |  | 4 |
|  | Phase 3: Implement | Concrete intervention see output 3.7.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
|  | Phase 4: O & M | Awareness raising and capacity building to operatate and maintain project activities | Capacity building of 58-60 water association members to run the association | 30,000 | 30,000 | - | - | - |  | 1 |  | 1,000 | 30 |  |  |  | 30 |
|  |  |  | Capacty building of 100 farmworkers on handling reclaimed water | 30,000 | - | 30,000 | - | - |  | 1 |  | 1,000 |  | 30 |  |  | 30 |
|  |  |  | Operation & maintenance plans for target irrigation systems at 40 farms | 8,000 | - | 8,000 | - | - |  | 1 |  | 200 |  | 40 |  |  | 40 |
|  |  |  | Monitoring | 8,000 | - | - | 4,000 | 4,000 |  | 1 |  | 100 |  |  | 40 | 40 | 80 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to repicate and scale-up project activities | Replication / upscaling plan and guidelines to operate, maintain, sustain and replicate the planning approach and irrigation interventions | 10,000 | - | - | - | 10,000 |  | 1 |  | 10,000 |  |  |  | 1 | 1 |
|  | Technical support and coordination | Sub-project Coordination and technical support (Johud) | Sub-project coordination (50 %) | 30,000 | 7,500 | 7,500 | 7,500 | 7,500 |  | 0.5 |  | 2,500 | 6 | 6 | 6 | 6 | 24 |
|  |  |  | Technical support to execute activities (50 %) | 15,000 | 3,750 | 3,750 | 3,750 | 3,750 |  | 0.5 |  | 2,500 | 3 | 3 | 3 | 3 | 12 |
|  |  |  | Logistics, admin and accountancy (50 %) | 3,000 | 750 | 750 | 750 | 750 |  | 0.5 |  | 1,500 | 1 | 1 | 1 | 1 | 4 |
|  |  | Sub-total Maerad and Al Kaider |  | 144,800 | 52,800 | 50,000 | 16,000 | 26,000 |  |  |  |  |  |  |  |  |  |
| Output 2.7.2 Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 3.7:Water-use Efficient irrigation of treated wastewater from Mafraq WWTP in Jordan | Phase 1: assessment | Formulate a rehabilitation study for individual farm (24) end-user/Groups based on agreed-upon climate change resilient/irrigation water need/use, cropping patterns | Preparation visits | 2,400 | 2,400 | - | - | - |  | 1 |  | 100 | 24 |  |  |  | 24 |
|  |  |  | Stakeholder sessions / workshops | 2,800 | 2,800 | - | - | - |  | 1 |  | 700 | 4 |  |  |  | 4 |
|  | Phase 2: plan | Water user associations established (Mafraq) | Preparation visits | 600 | 600 | - | - | - |  | 1 |  | 100 | 6 |  |  |  | 6 |
|  |  |  | Stakeholder sessions / workshops | 2,800 | 2,800 | - | - | - |  | 1 |  | 700 | 4 |  |  |  | 4 |
|  | Phase 3: Implement | Concrete intervention see output 3.7.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
|  | Phase 4: O & M | Awareness raising and capacity building to operatate and maintain project activities | Capacity building of 24 water association members to run the association | 15,000 | 15,000 | - | - | - |  | 1 |  | 1,000 | 15 |  |  |  | 15 |
|  |  |  | Capacty building of 50 farmworkers on handling reclaimed water | 15,000 | - | 15,000 | - | - |  | 1 |  | 1,000 |  | 15 |  |  | 15 |
|  |  |  | Operation & maintenance plans for target irrigation systems at 40 farms | 4,800 | - | 4,800 | - | - |  | 1 |  | 200 |  | 24 |  |  | 24 |
|  |  |  | Monitoring | 4,800 | - | - | 2,400 | 2,400 |  | 1 |  | 100 |  |  | 24 | 24 | 48 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to repicate and scale-up project activities | Replication / upscaling plan and guidelines to operate, maintain, sustain and replicate the planning approach and irrigation interventions | 10,000 | - | - | - | 10,000 |  | 1 |  | 10,000 |  |  |  | 1 | 1 |
|  | Technical support and coordination | Sub-project Coordination (Badia) | Sub-project coordination (100 %) | 30,000 | 7,500 | 7,500 | 7,500 | 7,500 |  | 1 |  | 2,500 | 3 | 3 | 3 | 3 | 12 |
|  |  |  | Technical support to execute activities (100 %) | 20,000 | 5,000 | 5,000 | 5,000 | 5,000 |  | 1 |  | 2,500 | 2 | 2 | 2 | 2 | 8 |
|  |  |  | Logistics, admin and accountancy (100 %) | 6,000 | 1,500 | 1,500 | 1,500 | 1,500 |  | 1 |  | 1,500 | 1 | 1 | 1 | 1 | 4 |
|  |  | Sub-total Mafraq |  | 114,200 | 37,600 | 33,800 | 16,400 | 26,400 |  |  |  |  |  |  |  |  |  |
| Sub-total |  |  |  | 259,000 | 90,400 | 83,800 | 32,400 | 52,400 |  |  |  |  |  |  |  |  |  |
| Output 2.8. Community organisation, awareness and capacity building + operation, maintenance and replication and upscaling plans for concrete adaptation output 2.8; permaculture demonstration | Phase 1: assessment | Detailed technical studies for systems integration (plant, animal, water, energy, soil and human) | Permaculture systems advisor (international) | 24,400 | 24,400 | - | - | - |  | 1 |  | 6,100 | 4 |  |  |  | 4 |
|  | Phase 2: plan | Detailed technical design for systems integration (plant, animal, water, energy, soil and human) | Permaculture systems advisor (international) | 24,400 | 24,400 | - | - | - |  | 1 |  | 6,100 | 4 |  |  |  | 4 |
|  | Phase 3: Implement | Concrete intervention see output 3.8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |
|  | Phase 4: O & M | Awareness raising and capacity building to operatate and maintain project activities | Workshops to involve surrounding communities (site visits and deisgn and operation training) | 10,000 | 3,000 | 3,000 | 2,000 | 2,000 |  | 1 |  | 1,000 | 3 | 3 | 2 | 2 | 10 |
|  |  |  | Operation & maintenance plan | 2,000 | - | 2,000 | - | - |  | 1 |  | 2,000 |  | 1 |  |  | 1 |
|  |  |  | Online Permaculture Design Certificate Course (28 modules, released weekly + final design exercise at JUST land or land owned by local community members. Cost per student | 170,000 | 42,500 | 42,500 | 42,500 | 42,500 |  | 50 |  | 850 | 1 | 1 | 1 | 1 | 4 |
|  | Phase 5: Replicate + Scale-up | Awareness raising and capacity building to repicate and scale-up project activities | Workshops to involve surrounding communities (site visits and replication training) | 4,000 | - | - | 2,000 | 2,000 |  | 1 |  | 1,000 |  |  | 2 | 2 | 4 |
|  |  |  | Replication / upscaling plan and guidelines, incl. permaculture landscape design plan for surrounding communities | 5,000 | - | - | - | 5,000 |  | 1 |  | 5,000 |  |  |  | 1 | 1 |
|  | Technical support and coordination | Sub-project Coordination (PRI) | Sub-project coordination / strategic advisor (internat) (100 %) | 48,800 | 12,200 | 12,200 | 12,200 | 12,200 |  | 1 |  | 6,100 | 2 | 2 | 2 | 2 | 8 |
|  |  |  | Technical support to execute activities (100 %) | 20,000 | 5,000 | 5,000 | 5,000 | 5,000 |  | 1 |  | 2,500 | 2 | 2 | 2 | 2 | 8 |
|  |  |  | Logistics, admin and accountancy (100 %) | 6,000 | 1,500 | 1,500 | 1,500 | 1,500 |  | 1 |  | 1,500 | 1 | 1 | 1 | 1 | 4 |
| Sub-total |  |  |  | 314,600 | 113,000 | 66,200 | 65,200 | 70,200 |  |  |  |  |  |  |  |  |  |
| TOTAL Component 2 |  |  |  | 1,733,200 | 505,000 | 421,500 | 494,600 | 312,100 |  |  |  |  |  |  |  |  |  |
| Output 3.1 Rooftop Rain Water Harvesting RWH) in Lebanon + show room | Phase 3: Implement (concrete measures) | Install and connect 20 large RWH systems (11 educational facilities, 7 religious buildings, 1 health facility, and 1 governmental building) with the water supply network, including the digging of rain-harvesting cisterns and mounting rectangular tanks 1,410 m3. | Collection System (Gutters, Drains, Pumps, Accessories) | 54,800 | - | 27,400 | 27,400 | - |  | 1 |  | 2,740 |  | 10 | 10 |  | 20 |
|  |  |  | Water Treatment systems (Media filter, Micro Filter, Chlorination tanks and dosage pumps) | 111,682 | - | 55,841 | 55,841 | - |  | 1 |  | 5,584 |  | 10 | 10 |  | 20 |
|  |  |  | Reinforced concrete water tanks (with excavations, waterproofing, ladders, valves, reinstatement, etc.) | 263,656 | - | 131,828 | 131,828 | - |  | 1 |  | 13,183 |  | 10 | 10 |  | 20 |
|  |  |  | Plastic Water tanks (inlcuding Excavation, subgrade, fencing and ladders) | 303,212 | - | 151,606 | 151,606 | - |  | 1 |  | 15,161 |  | 10 | 10 |  | 20 |
|  |  | Show room (1) with rainwater harvesting system and Water Savind Devices (WSD) | Installation of 1 complete system in Bekaa Water Establishment to enhance monitoring of RWH installed systems | 43,000 | - | - | 43,000 | - |  | 1 |  | 43,000 |  |  | 1 |  | 1 |
|  | Technical support | Supervision RWH system installation and maintenance (UNICEF Lebanon) | RWH engineer specialist / WASH officer (50 %) | 90,912 | 11,364 | 34,092 | 34,092 | 11,364 |  | 0.5 |  | 5,682 | 4 | 12 | 12 | 4 | 32 |
| Sub-total |  |  |  | 867,262 | 11,364 | 400,767 | 443,767 | 11,364 |  |  |  |  |  |  |  |  |  |
| Output 3.2. Rooftop Rain Water Harvesting (RWH) in Jordan + show room | Phase 3: Implement (concrete measures) | Install and connect 84 small RWH systems (of which 18 rehabilitation - 49 schools, 15 mosques, 20 residential) with the water supply network, including the digging of rain-harvesting cisterns and mounting rectangular tanks 30-60 m3. | Per system including tank, pumps, pipes and surface rehabilitation | 672,000 | - | 336,000 | 336,000 | - |  | 1 |  | 8,000 |  | 42 | 42 |  | 84 |
|  |  |  | Transportation | 8,820 | - | 4,410 | 4,410 | - |  | 1 |  | 105 |  | 42 | 42 |  | 84 |
|  |  | Show room (2) with RWH system, GWTR system and Water Saving Devices (WSD) | Installation of 2 complete systems in municipal government buildings to enhance awareness raising while | 100,000 | - | 100,000 | - | - |  | 1 |  | 50,000 |  | 2 |  |  | 2 |
|  | Technical support | Supervision RWH system installation and maintenance (Johud) | RWH enigneer specialist / WASH officer (50 %) | 40,000 | 5,000 | 15,000 | 15,000 | 5,000 |  | 0.5 |  | 2,500 | 4 | 12 | 12 | 4 | 32 |
| Sub-total |  |  |  | 820,820 | 5,000 | 455,410 | 355,410 | 5,000 |  |  |  |  |  |  |  |  |  |
| Output 3.3. Grey Water Treatment and Reuse (GWTR) in Jordan | Phase 3: Implement (concrete measures) | Install / construct and connect 40 GWTR systems with toilets and gardening water supply (35 schools, 5 mosques) | Per system including tank, pumps, pipes and surface rehabilitation | 320,000 | - | 160,000 | 160,000 | - |  | 1 |  | 8,000 |  | 20 | 20 |  | 40 |
|  |  |  | Transportation | 4,200 | - | 2,100 | 2,100 | - |  | 1 |  | 105 |  | 20 | 20 |  | 40 |
|  |  | Rehabilitation and modification of WASH blocks for greywater reuse in toilet flushing and for greeing purposes | Per block | 428,000 | - | 214,000 | 214,000 | - |  | 1 |  | 10,700 |  | 20 | 20 |  | 40 |
|  | Technical support | Supervision GWTR system and blocks installation and maintenance (UNICEF Jordan) | RWH engineer specialist / WASH officer (50 %) | 90,912 | 11,364 | 34,092 | 34,092 | 11,364 |  | 0.5 |  | 5,682 | 4 | 12 | 12 | 4 | 32 |
| Sub-total |  |  |  | 843,112 | 11,364 | 410,192 | 410,192 | 11,364 |  |  |  |  |  |  |  |  |  |
| Output 3.4.1. Efficient treatment and reuse of wastewater from Zahle WWTP, in Lebanon | Phase 3: Implement (concrete measures) | Reuse of the Zahle WWTP effluent for irrigation through diverting the plant's treated effluent to agricultural fields and treating sludge for fertilizers usage - 116 Hectares of Agricultural lands | Construction of a 3000 m open channel (1x1 meters with 0.25m thick walls) | 825,000 | - | 825,000 | - | - |  | 1 |  | 275 |  | 3000 |  |  |  |
|  | Technical support | Supervision of the irrigation system installation and maintenance (RTO) | Civil/ Agricultural Engineer (33%) | 21,120 | 3,960 | 7,920 | 7,920 | 1,320 |  | 0.3 |  | 2,200 | 6 | 12 | 12 | 2 | 32 |
|  |  | Sub-total Zahle WWTP |  | 846,120 | 3,960 | 832,920 | 7,920 | 1,320 |  |  |  |  |  |  |  |  |  |
| Output 3.4.2 Efficient treatment and reuse of wastewater through wetlands, in Lebanon | Phase 3: Implement (concrete measures) | Construction of 60,000 sqm of Free Water Surface (FWS) Wetland to improve irrigation water quality for farmers tapping into the heavily polluted Ghezayel tributary of the Litani river. | Eathworking | 313,268 | 31,327 | 281,941 | - | - |  | 1 |  | 313,268 | 0.1 | 0.9 |  |  | 1 |
|  |  |  | Berms | 222,768 | - | 222,768 | - | - |  | 1 |  | 222,768 |  | 1 |  |  | 1 |
|  |  |  | Planting | 125,307 | - | 125,307 | - | - |  | 1 |  | 125,307 |  | 1 |  |  | 1 |
|  |  |  | Piping, Pump and Structures | 284,700 | - | 284,700 | - | - |  | 1 |  | 284,700 |  | 1 |  |  | 1 |
|  |  |  | Trails, Signage | 113,880 | - | - | 113,880 | - |  | 1 |  | 113,880 |  |  | 1 |  | 1 |
|  | Technical support | Supervision RWH system installation and maintenance (UNICEF Lebanon) | Wetlands specialist / WaSH officer (50 %) | 90,912 | 17,046 | 34,092 | 34,092 | 5,682 |  | 0.5 |  | 5,682 | 6 | 12 | 12 | 2 | 32 |
|  |  | Sub-total Wetlands |  | 1,150,835 | 48,373 | 948,808 | 147,972 | 5,682 |  |  |  |  |  |  |  |  |  |
| Sub-total |  |  |  | 1,996,955 | 52,333 | 1,781,728 | 155,892 | 7,002 |  |  |  |  |  |  |  |  |  |
| Output 3.5. Efficient treatment and reuse of wastewater in Jordan | Phase 3: Implement (concrete measures) | Maerad WWTP upgrading for increased water quality and water storage capacity for irrigation purposes | Install Storage tank (3000) m3 and flow meters distribution collector and reuse pipeline to control the pumping of treated water to farmers and to increase the no. of farmers and areas which reuse treated water | 282,500 | - | 282,500 | - | - |  | 1 |  | 282,500 |  | 1 |  |  | 1 |
|  |  |  | Spare parts for equipment | 28,250 | - | 28,250 | - | - |  | 1 |  | 28,250 |  | 1 |  |  | 1 |
|  |  |  | Air Blower for aeration tank | 35,300 | - | 35,300 | - | - |  | 1 |  | 35,300 |  | 1 |  |  | 1 |
|  |  |  | Wheels for setting tanks | 2,850 | - | 2,850 | - | - |  | 1 |  | 2,850 |  | 1 |  |  | 1 |
|  |  |  | Excess sludge pump + repair kit | 5,600 | - | 5,600 | - | - |  | 1 |  | 5,600 |  | 1 |  |  | 1 |
|  |  |  | Polymer pump positive displacement | 2,800 | - | 2,800 | - | - |  | 1 |  | 2,800 |  | 1 |  |  | 1 |
|  |  |  | Two platforms around dewatering units | 1,400 | - | 1,400 | - | - |  | 1 |  | 1,400 |  | 1 |  |  | 1 |
|  |  |  | Replace inlet pipes to dewatering units from plastic to stainless steal | 1,400 | - | 1,400 | - | - |  | 1 |  | 1,400 |  | 1 |  |  | 1 |
|  |  |  | Supply and install Y strainer for feed line to dewatering machines | 707 | - | 707 | - | - |  | 1 |  | 707 |  | 1 |  |  | 1 |
|  |  |  | Supply new sludge screw to dewatering unit | 9,900 | - | 9,900 | - | - |  | 1 |  | 9,900 |  | 1 |  |  | 1 |
|  |  |  | Supply conveyer belt with motor and gearbox for dewatering | 5,650 | - | 5,650 | - | - |  | 1 |  | 5,650 |  | 1 |  |  | 1 |
|  |  |  | 4 VFD fans for dewatering unit | 9,900 | - | 9,900 | - | - |  | 1 |  | 1,150 |  | 1 |  |  | 1 |
|  |  |  | Supply Level meter for drainage tank | 2,100 | - | 2,100 | - | - |  | 1 |  | 2,100 |  | 1 |  |  | 1 |
|  |  |  | Supply one drainage pump 18.5 kw 8-25 m H and 20-125 l/s | 14,000 | - | 14,000 | - | - |  | 1 |  | 14,000 |  | 1 |  |  | 1 |
|  |  |  | Supply 2 flow meter for RAS, WAS pumps | 14,000 | - | 14,000 | - | - |  | 1 |  | 14,000 |  | 1 |  |  | 1 |
|  |  |  | Install PV to compensate for energy use | 10,000 | - | 10,000 | - | - |  | 1 |  | 10,000 |  | 1 |  |  | 1 |
|  |  | Sub-total Maerad |  | 426,357 | - | 426,357 | - | - |  |  |  |  |  |  |  |  |  |
|  |  | Al Akaider WWTP upgrading for increased water quality and water storage capacity for irrigation purposes | Install Sand trap and screen unit for inlet | 67,800 | - | 67,800 | - | - |  | 1 |  | 67,800 |  | 1 |  |  | 1 |
|  |  |  | Install 2 new pumps with control panel with level control with soft start with electrical crane + pipe network installing and fabrication | 113,000 | - | 113,000 | - | - |  | 1 |  | 113,000 |  | 1 |  |  | 1 |
|  |  |  | Install basket screen on inlet of storage tank to protect the pumps and ensure continues pumping for farmers | 1,400 | - | 1,400 | - | - |  | 1 |  | 1,400 |  | 1 |  |  | 1 |
|  |  |  | Chlorine unit for disinfection treated water | 14,100 | - | 14,100 | - | - |  | 1 |  | 14,100 |  | 1 |  |  | 1 |
|  |  |  | Maintain all gates and bridges for ponds | 7,000 | - | 7,000 | - | - |  | 1 |  | 7,000 |  | 1 |  |  | 1 |
|  |  |  | Install Storage tank (2000 ) m3 and flow meters distribution collector and reuse pipeline to control the pumping of treated water to farmers and to increase the no. of farmers and areas which reuse treated water | 198,000 | - | 198,000 | - | - |  | 1 |  | 198,000 |  | 1 |  |  | 1 |
|  |  |  | Clean anaerobic pond | 71,000 | - | 71,000 | - | - |  | 1 |  | 71,000 |  | 1 |  |  | 1 |
|  |  |  | Install new pipe line from inlet to anaerobic pond | 14,100 | - | 14,100 | - | - |  | 1 |  | 14,100 |  | 1 |  |  | 1 |
|  |  |  | Install PV to compensate for energy use | 10,000 | - | 10,000 | - | - |  | 1 |  | 10,000 |  | 1 |  |  | 1 |
|  |  | Sub-total Al Akaider |  | 496,400 | - | 496,400 | - | - |  |  |  |  |  |  |  |  |  |
|  |  | Mafraq WWTP upgrading for increased water quality for irrigation purposes | Spare parts for equipment | 28,250 | - | 28,250 | - | - |  | 1 |  | 28,250 |  | 1 |  |  | 1 |
|  |  |  | two Soft starter for pumps of lift station | 8,400 | - | 8,400 | - | - |  | 1 |  | 8,400 |  | 1 |  |  | 1 |
|  |  |  | Two aerator units for ponds | 12,125 | - | 12,125 | - | - |  | 1 |  | 12,125 |  | 1 |  |  | 1 |
|  |  |  | One irrigation pump (higher head for far area ) to increase the area which reuses treated water | 35,300 | - | 35,300 | - | - |  | 1 |  | 35,300 |  | 1 |  |  | 1 |
|  |  |  | One lifting pump, one primary sludge pump | 28,000 | - | 28,000 | - | - |  | 1 |  | 28,000 |  | 1 |  |  | 1 |
|  |  |  | Modify conveyor belt of screen by install new mechanical belt conveyor | 8,500 | - | 8,500 | - | - |  | 1 |  | 8,500 |  | 1 |  |  | 1 |
|  |  |  | Install PV to compensate for energy use | 10,000 | - | 10,000 | - | - |  | 1 |  | 10,000 |  | 1 |  |  | 1 |
|  |  | Sub-total Mafraq |  | 130,575 | - | 130,575 | - | - |  |  |  |  |  |  |  |  |  |
|  | Technical support | Supervisision WWTPs ugradings measures installation and maintenance (WAJ / Yarmouk) | In-kind |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-total |  |  |  | 1,053,332 | - | 1,053,332 | - | - |  |  |  |  |  |  |  |  |  |
| Output 3.6.1 Water-use-efficient irrigation of treated wastewater for fruit trees in Lebanon from Zahle WWTP, Lebanon | Phase 3: Implement (concrete measures) | Installation of drip irrigation systems (110 out of possible 116 ha) for fruit trees and vineyards | Drip Irrigation (including pumps and filters) | 908,600 | - | 908,600 | - | - |  | 1 |  | 8,260 |  | 110 |  |  | 110 |
|  |  |  | Sensors, automated tools (includes valves, regulators, fittings) | 2,200 | - | 2,200 | - | - |  | 1 |  | 20 |  | 110 |  |  | 110 |
|  | Technical support | Supervision of the irrigation system installation and maintenance (RTO) | Civil/ Agricultural Engineer (33%) | 18,150 | 2,904 | 8,712 | 4,356 | 2,178 |  | 0.3 |  | 2,200 | 4 | 12 | 6 | 3 | 25 |
|  |  | Sub-total irrigation from Zahle WWTP |  | 928,950 | 2,904 | 919,512 | 4,356 | 2,178 |  |  |  |  |  |  |  |  |  |
| Output 3.6.2 Water-use-efficient irrigation of treated wastewater for potato crops in Lebanon from Bar Elias wetland, Lebanon | Phase 3: Implement (concrete measures) | Installation of drip irrigation systems for (40 out of possible 70 ha) for potato plantations | Drip Irrigation (including pumps and filters) | 330,400 | - | 330,400 | - | - |  | 1 |  | 8,260 |  | 40 |  |  | 40 |
|  |  |  | Sensors, automated tools (includes valves, regulators, fittings) | 800 | - | 800 | - | - |  | 1 |  | 20 |  | 40 |  |  | 40 |
|  | Technical support | Supervision of the irrigation system installation and maintenance (RTO) | Civil/ Agricultural Engineer (33%) | 18,150 | 2,904 | 8,712 | 4,356 | 2,178 |  | 0.3 |  | 2,200 | 4 | 12 | 6 | 3 | 25 |
|  |  | Sub-total irrigation from Wetland |  | 349,350 | 2,904 | 339,912 | 4,356 | 2,178 |  |  |  |  |  |  |  |  |  |
| Sub-total |  |  |  | 1,278,300 | 5,808 | 1,259,424 | 8,712 | 4,356 |  |  |  |  |  |  |  |  |  |
| Output 3.7.1 Water-use Efficient irrigation of treated wastewater from Maerad and Alkaider WWTPs in Jordan | Phase 3: Implement (concrete measures) | Connect WWTPs stored water with farm lands | 4 KMs conveyor pipeline 6’ size | 120,000 | - | 120,000 | - | - |  | 1 |  | 30 |  | 4000 |  |  | 4000 |
|  |  |  | Installation 4000 m | 20,000 | - | 20,000 | - | - |  | 1 |  | 5 |  | 4000 |  |  | 4000 |
|  |  | Establish a new modern water irrigation system connecting main water irrigation pipe with farm lands (120 dunums) | For 120 dunum | 240,000 | - | 240,000 | - | - |  | 1 |  | 2,000 |  | 120 |  |  | 120 |
|  | Technical support | Supervisision irrigation system installation and maintenance (Johud) | Irrigation specialist / field engineer (50 %) | 26,400 | 4,800 | 14,400 | 3,600 | 3,600 |  | 0.4 |  | 3,000 | 4 | 12 | 3 | 3 | 22 |
|  |  | Sub-total irrigation from Mearad and Al Akaider |  | 406,400 | 4,800 | 394,400 | 3,600 | 3,600 |  |  |  |  |  |  |  |  |  |
| Output 3.7.2 Water-use Efficient irrigation of treated wastewater from Mafraq WWTP in Jordan | Phase 3: Implement (concrete measures) | Establish a new modern water irrigation system connecting water ponds with farm lands (100 dunum) | For 100 dunums | 200,000 | - | 200,000 | - | - |  | 1 |  | 2,000 |  | 100 |  |  | 100 |
|  |  |  | Establish new water ponds (15) with surface pumps and filters at farm lands | 150,000 | - | 150,000 | - | - |  | 1 |  | 10,000 |  | 15 |  |  | 15 |
|  | Technical support | Supervision irrigation system installation and maintenance (Badia) | Irrigation specialist / field engineer (100 %) | 48,000 | 6,000 | 36,000 | 3,000 | 3,000 |  | 1 |  | 3,000 | 2 | 12 | 1 | 1 | 16 |
|  |  | Sub-total irrigation from Mafraq |  | 398,000 | 6,000 | 386,000 | 3,000 | 3,000 |  |  |  |  |  |  |  |  |  |
| Sub-total |  |  |  | 804,400 | 10,800 | 780,400 | 6,600 | 6,600 |  |  |  |  |  |  |  |  |  |
| Output 3.8. Permaculture demonstration - closed loop water system in Jordan | Phase 3: Implement (concrete measures) | Bio-Fertilizer production | Compost turner | 30,000 | 30,000 | - | - | - |  | 1 |  | 30,000 | 1 |  |  |  | 1 |
|  |  |  | Tractor Massey Ferguson | 30,000 | 30,000 | - | - | - |  | 1 |  | 30,000 | 1 |  |  |  | 1 |
|  |  |  | Woodchipper | 4,000 | 4,000 | - | - | - |  | 1 |  | 4,000 | 1 |  |  |  | 1 |
|  |  |  | Compost tea brewer 20 litres | 2,000 | 2,000 | - | - | - |  | 1 |  | 2,000 | 1 |  |  |  | 1 |
|  |  |  | Microscope with display scree | 3,000 | 3,000 | - | - | - |  | 1 |  | 3,000 | 1 |  |  |  | 1 |
|  |  |  | Mulch bales | 8,800 | 1,600 | 2,400 | 2,400 | 2,400 |  | 50 |  | 4 | 8 | 12 | 12 | 12 | 44 |
|  |  |  | Manure (truck load) | 13,200 | 2,400 | 3,600 | 3,600 | 3,600 |  | 4 |  | 75 | 8 | 12 | 12 | 12 | 44 |
|  |  |  | Diesel average per litre | 880 | 160 | 240 | 240 | 240 |  | 10 |  | 2 | 8 | 12 | 12 | 12 | 44 |
|  |  | Crop Garden and Compost Egg laying Chickens | Poly tunnels | 9,450 | 9,450 | - | - | - |  | 3 |  | 3,150 | 1 |  |  |  | 1 |
|  |  |  | Irrigation | 550 | 550 | - | - | - |  | 1 |  | 550 | 1 |  |  |  | 1 |
|  |  |  | Chicken Caravan 30, 2 electric fences, solar electric energiser | 4,400 | 4,400 | - | - | - |  | 1 |  | 4,400 | 1 |  |  |  | 1 |
|  |  |  | Feed for 30 chickens | 1,288 | 322 | 322 | 322 | 322 |  | 1 |  | 322 | 1 | 1 | 1 | 1 | 4 |
|  |  |  | Hand tools, 2 wheelbarrows, 2 rakes, 2 shovels, 2 hoes, 2 pruners, 2 loppers, 2 pruning saws, 2 pitch forks | 300 | 300 | - | - | - |  | 1 |  | 300 | 1 |  |  |  | 1 |
|  |  |  | Seeds and Seedslings | 720 | 180 | 180 | 180 | 180 |  | 1 |  | 180 | 1 | 1 | 1 | 1 | 4 |
|  |  | Bees: Apiculture | 3 flow hives; 3 colonies; 3 hives full of bees; stainless steel spinner extractor; smoker; seperator; 3 top boxes; brush; suit; gloves; wax capping knife | 4,200 | 4,200 | - | - | - |  | 1 |  | 4,200 | 1 |  |  |  | 1 |
|  |  | Compost worms: vermicompost | 5 sub-od works farms | 1,000 | 1,000 | - | - | - |  | 1 |  | 1,000 | 1 |  |  |  | 1 |
|  |  | Olive Orchard Monoculture Conversion to Food Forest (1,000m2) | Irrigation | 550 | 550 | - | - | - |  | 1 |  | 550 | 1 |  |  |  | 1 |
|  |  |  | Chicken caraven 30, 2 electric net fence, solar electric energiser | 4,400 | 4,400 | - | - | - |  | 1 |  | 4,400 | 1 |  |  |  | 1 |
|  |  |  | Feed for 30 chickens | 1,288 | 322 | 322 | 322 | 322 |  | 1 |  | 322 | 1 | 1 | 1 | 1 | 4 |
|  |  |  | Trees | 720 | 180 | 180 | 180 | 180 |  | 1 |  | 180 | 1 | 1 | 1 | 1 | 4 |
|  |  |  | Seeds | 300 | 75 | 75 | 75 | 75 |  | 1 |  | 75 | 1 | 1 | 1 | 1 | 4 |
|  | Technical support | Supervisision Permeculture demonstration site installation and maintenance | Permaculture expert (National) | 120,000 | 48,000 | 24,000 | 24,000 | 24,000 |  | 1 |  | 2,000 | 24 | 12 | 12 | 12 | 60 |
|  |  |  | Agriculture labourers (National) | 57,600 | 14,400 | 14,400 | 14,400 | 14,400 |  | 2 |  | 600 | 12 | 12 | 12 | 12 | 48 |
|  |  |  | Strategic advise / expert (International) | 42,700 | 24,400 | 6,100 | 6,100 | 6,100 |  | 1 |  | 6,100 | 4 | 1 | 1 | 1 | 7 |
|  |  |  | Permaculture systems advisor (international) | 42,700 | 24,400 | 6,100 | 6,100 | 6,100 |  | 1 |  | 6,100 | 4 | 1 | 1 | 1 | 7 |
| Sub-total |  |  |  | 384,046 | 210,289 | 57,919 | 57,919 | 57,919 |  |  |  |  |  |  |  |  |  |
| TOTAL Component 3 |  |  |  | 8,048,227 | 306,958 | 6,199,172 | 1,438,492 | 103,605 |  |  |  |  |  |  |  |  |  |
| Output 4.1. Regional / international KM with focus on project lessons sharing and replication (incl. international seminars and regional platforms & policy dialogue) |  | UN- ESCWA seminars and knowledge sharing in Jordan or Lebanon: targeting regional steering committee members (national and city government officials) to participate | See output 4.2 (SC members travel) | - | - | - | - | - |  |  |  |  |  |  |  |  | 0 |
|  |  | International seminars / events focused specifically on climate change and urban development, incl. refugee crisis implications (AMFHUD ; WUF, COP side events (2x); AFSD; HLPF 2022 reviewing SDG 11 and 6 and HLPD 2023): targeting regional steering committee members (national and city government officials) + other key stakeholders to participate | International seminars / events focused on climate change, urban development and refugee crisis implications (incl. travel and daily allowance for accommodation, etc.) | 200,000 | 25,000 | 25,000 | 75,000 | 75,000 |  | 10 |  | 2,500 | 1 | 1 | 3 | 3 | 8 |
|  |  | Through Arab Centre for Climate Change Policies; set-up community of practices on climate change in urban areas with implications refugee crisis (with documentation of good practices and lessons; replication package; project video; knowledge products uploaded) linked to ACCCP knowledge platform | Communication outputs (publications, digital platform, video: project baseline and results, incl. human interest story) | 70,000 | 20,000 | 10,000 | 10,000 | 30,000 |  | 1 |  | 10,000 | 2 | 1 | 1 | 3 | 7 |
|  |  | For all above: | see output 4.2 (communication officer) | - | - | - | - | - |  |  |  |  |  |  |  |  | 0 |
| Sub-total |  |  |  | 270,000 | 45,000 | 35,000 | 85,000 | 105,000 |  |  |  |  |  |  |  |  |  |
| Output 4.2. Jordan and Lebanin KM with focus on project progress, best practices and lessons learned shared + capacity building |  | Jordan and Lebanon Project Steering committee meetings in Lebanon or Jordan (to align with ESCWA relevant events - see 4.1.) | SC workshop organisation | 64,000 | 16,000 | 16,000 | 16,000 | 16,000 |  | 1 |  | 8,000 | 2 | 2 | 2 | 2 | 8 |
|  |  | Platform / working space (electronic) used for project communication and sharing lessons (research; project best practice and lessonse learned, incl. field visits) | SC travel and daily allowance for accommodation, etc. (also covering ESCWA events as side events - see 4.1., where possible) | 184,400 | 55,320 | 36,880 | 36,880 | 55,320 |  | 20 |  | 922 | 3 | 2 | 2 | 3 | 10 |
|  |  |  | Project field visits | 14,000 | 2,000 | 4,000 | 4,000 | 4,000 |  | 1 |  | 2,000 | 1 | 2 | 2 | 2 | 7 |
|  |  | For all above: | Communication officer (see above) | 155,400 | 33,300 | 44,400 | 33,300 | 44,400 |  | 1 |  | 3,700 | 9 | 12 | 9 | 12 | 42 |
|  |  | For all above: | Admin / travel support | 16,000 | 4,000 | 4,000 | 4,000 | 4,000 |  | 1 |  | 2,000 | 2 | 2 | 2 | 2 | 8 |
| Sub-total |  |  |  | 433,800 | 110,620 | 105,280 | 94,180 | 123,720 |  |  |  |  |  |  |  |  |  |
| Output 4.3. Sub-national KM and Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities |  | Institutional set-up territorial observatories (in universities) in target areas | Spatial / urban planner | 28,000 | - | 28,000 | - | - |  | 2 |  | 3,500 |  | 4 |  |  | 4 |
|  |  |  | IT expert | 20,000 | - | 20,000 | - | - |  | 2 |  | 2,500 |  | 4 |  |  | 4 |
|  |  | Geo-referenced database and an online platform to share data produced and linked with ESCWA database | Database | 60,000 | - | 20,000 | 20,000 | 20,000 |  | 2 |  | 10,000 |  | 1 | 1 | 1 | 3 |
|  |  | Regional’ urban risks and vulnerabilities assessment, planning and management approach model for type 2 cities (including replication guidelines) | Spatial / urban planner | 21,000 | - | - | - | 21,000 |  | 1 |  | 3,500 |  |  |  | 6 | 6 |
|  |  |  | Communication / publication | 15,000 | - | - | - | 15,000 |  | 1 |  | 15,000 |  |  |  | 1 | 1 |
| Sub-total |  |  |  | 144,000 | - | 68,000 | 20,000 | 56,000 |  |  |  |  |  |  |  |  |  |
| Output 4.4. Incentive mechanism (financial) and regulatory framework to replicate and upscale rainwater harvesting activities |  | Identification of effective incentive mechanism (financial) and regulatory framework to repliacte and upscale (i.e. national programme) rainwater harvesting activities, esp. in Jordan | Consultant | 36,000 | - | - | 36,000 | - |  | 1 |  | 6,000 |  |  | 6 |  | 6 |
|  |  | Travel | 2 missions | 4,362 | - | - | - | 4,362 |  | 2 |  | 2,181 |  |  |  | 1 | 1 |
| Sub-total |  |  |  | 40,362 | - | - | 36,000 | 4,362 |  |  |  |  |  |  |  |  |  |
| TOTAL Component 4 |  |  |  | 888,162 | 155,620 | 208,280 | 235,180 | 289,082 |  |  |  |  |  |  |  |  |  |
| TOTAL Components |  |  |  | 11,650,589 | 1,562,578 | 7,214,952 | 2,168,272 | 704,787 |  |  |  |  |  |  |  |  |  |
| Project execution costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project execution |  | Jordan | Regional Project coordination (regional - international) | 264,000 | 66,000 | 66,000 | 66,000 | 66,000 |  | 1 |  | 11,000 | 6 | 6 | 6 | 6 | 24 |
|  |  |  | Admin / financial procurement (regional - national) | 84,000 | 21,000 | 21,000 | 21,000 | 21,000 |  | 1 |  | 1,750 | 12 | 12 | 12 | 12 | 48 |
|  |  |  | M & E and communication (regional - national) | 42,000 | 10,500 | 10,500 | 10,500 | 10,500 |  | 1 |  | 1,750 | 6 | 6 | 6 | 6 | 24 |
|  |  |  | Safeguarding system (AF) compliance (regional - national) | 42,000 | 10,500 | 10,500 | 10,500 | 10,500 |  | 1 |  | 1,750 | 6 | 6 | 6 | 6 | 24 |
|  |  |  | Spatial / urban planning (regional - national) | 90,000 | 36,000 | 18,000 | 18,000 | 18,000 |  | 1 |  | 3,000 | 12 | 6 | 6 | 6 | 30 |
|  |  |  | Engineer water / cc focused (regional - national) | 108,000 | 36,000 | 36,000 | 18,000 | 18,000 |  | 1 |  | 3,000 | 12 | 12 | 6 | 6 | 36 |
|  |  |  | National Project coordination (national) | 180,000 | 45,000 | 45,000 | 45,000 | 45,000 |  | 1 |  | 5,000 | 9 | 9 | 9 | 9 | 36 |
|  |  |  | Driver (national) | 16,800 | 4,200 | 4,200 | 4,200 | 4,200 |  | 1 |  | 1,400 | 3 | 3 | 3 | 3 | 12 |
|  |  | Travel | Related to Jordan staff travel | 26,172 | 6,543 | 6,543 | 6,543 | 6,543 |  | 1 |  | 2,181 | 3 | 3 | 3 | 3 | 12 |
|  |  | Lebanon | National Project coordination (national) | 180,000 | 45,000 | 45,000 | 45,000 | 45,000 |  | 1 |  | 5,000 | 9 | 9 | 9 | 9 | 36 |
|  |  |  | Admin / financial procurement (national) | 24,500 | 5,250 | 8,750 | 5,250 | 5,250 |  | 1 |  | 1,750 | 3 | 5 | 3 | 3 | 14 |
|  |  |  | M & E and communication (national) | 21,000 | 5,250 | 5,250 | 5,250 | 5,250 |  | 1 |  | 1,750 | 3 | 3 | 3 | 3 | 12 |
|  |  |  | Driver (national) | 16,800 | 4,200 | 4,200 | 4,200 | 4,200 |  | 1 |  | 1,400 | 3 | 3 | 3 | 3 | 12 |
|  |  | Travel | Related to Lebanon travel | 16,000 | 4,000 | 4,000 | 4,000 | 4,000 |  | 1 |  | 500 | 8 | 8 | 8 | 8 | 32 |
|  |  | Operations | Vehicle Operations & Maintenance | 12,000 | 3,000 | 3,000 | 3,000 | 3,000 |  | 2 |  | 250 | 6 | 6 | 6 | 6 | 24 |
|  |  |  | Office Rent | 32,000 | 8,000 | 8,000 | 8,000 | 8,000 |  | 2 |  | 2,000 | 2 | 2 | 2 | 2 | 8 |
|  |  |  | Communication | 26,000 | 2,000 | 2,000 | 2,000 | 20,000 |  | 1 |  | 2,000 | 1 | 1 | 1 | 10 | 13 |
|  |  |  | Office Supplies and Stationery | 12,000 | 3,000 | 3,000 | 3,000 | 3,000 |  | 2 |  | 250 | 6 | 6 | 6 | 6 | 24 |
|  |  | Final evaluation | Independent (lump sum) | 30,000 | - | - | - | 30,000 |  | 1 |  | 30,000 |  |  |  | 1 | 1 |
| TOTAL Execution costs |  |  |  | 1,223,272 | 315,443 | 300,943 | 279,443 | 327,443 |  |  |  |  |  |  |  |  |  |
| TOTAL Project costs |  |  |  | 12,873,861 | 1,878,021 | 7,515,895 | 2,447,715 | 1,032,230 |  |  |  |  |  |  |  |  |  |
| Project cycle management fee costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project cycle management |  | 1.25% | UN-H ROAS overall project supervision, incl. AF and UN-H policies (esp ESP and GP) and regulations compliance and regional admin, coordination and travel | 160,923 | 23,475 | 93,949 | 30,596 | 12,903 |  |  |  |  |  |  |  |  |  |
|  |  | 0.25% | UN-H ROAS M & E, incl. Travel | 32,185 | 4,695 | 18,790 | 6,119 | 2,581 |  |  |  |  |  |  |  |  |  |
|  |  | 7% | UN-H HQ Overall project supervision, incl .compliance to UN-H policies (gender, human rights, climate change, etc.) | 901,170 | 131,461 | 526,113 | 171,340 | 72,256 |  |  |  |  |  |  |  |  |  |
| TOTAL management fee |  | 8.50% |  | 1,094,278 | 159,632 | 638,851 | 208,056 | 87,740 |  |  |  |  |  |  |  |  |  |
| TOTAL amount of financing requested |  |  |  | 13,968,139 | 2,037,653 | 8,154,746 | 2,655,771 | 1,119,970 |  |  |  |  |  |  |  |  |  |

World Bank et all (2017, policy note September 14): Refugees in the middle east. Bringing an urban lens to the forced displacement challenge.

Ibid

UNDP / GEF (2018) Climate Change Adaptation in the Arab States Best practices and lessons learned. Online: https://reliefweb.int/report/world/climate-change-adaptation-arab-states-best-practices-and-lessons-learned

UNDP / GEF (2018) Climate Change Adaptation in the Arab States Best practices and lessons learned

Ibid

Ibid

The Syrian Arab Republic is the biggest sending country of refugees registered by UNHCR in the world (5.5 million out of a total of 18.5 million - UN-Habitat 2018. Migration and inclusive cities: A guide for Arab city leaders

International Organization for Migration. (2019) World Migration Report 2020. 2019 Edition. Switzerland: International Organization for Migration.

The Government of Lebanon and the United Nations. (2019) Lebanon crisis response plan 2017-2020 (2019 update). 2019 Edition. Lebanon: The Government of Lebanon and the United Nations.

Ibid

UNHCR fact sheet, October 2019.

See Jordan and Lebanon INDCs and Lebanon crisis response plan 2017-2020

https://video.ecc-platform.org/videos/links-between-migration-and-climate-change

UN 3RP: Regional Refugee & Resilience Plan 2018-2019.

Ibid.

UN for Lebanon annual report 2017

UNICEF Evaluation of the Water, Sanitation and Hygiene (WASH) Programme within the UNICEF Country Programme in Lebanon (2013-2016)

Ministry of Environment, EU and UNDP: Lebanon Environmental Assessment of the Syrian Conflict & Priority Interventions 2014

UNICEF Evaluation of the Water, Sanitation and Hygiene (WASH) Programme within the UNICEF Country Programme in Lebanon (2013-2016)

World Bank (2019) Population, total. [Online] Available from: https://data.worldbank.org/country/lebanon [Accessed 10 January, 2020]

World Bank (2019) Macro Poverty Outlook: Country-by-country Analysis and Projections for the Developing World. October 2019 Edition. World Bank

Amnesty International (2020) Lebanon Protests Explained: Mass demonstrations. Available from: https://www.amnesty.org/en/latest/news/2019/11/lebanon-protests-explained/ [Accessed 15 January, 2020]

https://www.worldbank.org/en/country/lebanon/overview

VASYR 2017: Vulnerability Assessment of Syrian Refugees in Lebanon

Ministry of Environment, EU and UNDP: Lebanon Environmental Assessment of the Syrian Conflict & Priority Interventions 2014

Regular Perception Surveys on Social Tensions throughout Lebanon (ARK, 2017), and Defining Community Vulnerability in Lebanon, REACH (2014).

https://data2.unhcr.org/en/situations/syria/location/71#_ga=2.248854471.1978193527.1540994637-1966626473.1540994637

Jordan TNC (2014)

Hashemite Kingdom of Jordan, UNICEF and UNDP (2015) Socio-economic inequality in Jordan

http://dosweb.dos.gov.jo/19-2-unemployment-rate-during-the-second-quarter-of-2019-2/

https://data.worldbank.org/indicator/SL.UEM.1524.ZS?locations=JO

Hashemite Kingdom of Jordan, UNICEF and UNDP (2015) Socio-economic inequality in Jordan

MWI (Ministry of Water and Irrigation, Jordan) (2009): Water for Life. Jordan’s Water Strategy.

National Climate Change Strategy of Jordan, 2013

Ministry of Water and Irrigation: Water Facts and Figures 2017

Jordan National Water Strategy 2016-2025

Ministry of Water and Irrigation: Water Facts and Figures 2017

Department of Statistics. Online. http://dosweb.dos.gov.jo/

https://tradingeconomics.com/jordan/government-debt-to-gdp

World Bank. Online: https://data.worldbank.org/country/jordan

https://data2.unhcr.org/en/situations/syria/location/36#_ga=2.22371195.1978193527.1540994637-1966626473.1540994637

Hashemite Kingdom of Jordan, UNICEF and UNDP (2015) Socio-economic inequality in Jordan

Ministry of Water and Irrigation: Water Facts and Figures 2017

Lebanon TNC (2016)

Ibid

Ministry of Environment and UNDP (2011) Lebanon Second National Communication on Climate Change – Public Health

Lebanon Third National Communication on Climate Change

Lebanon crisis response plan 2017-2020

Jordan TNC (2014)

Jordan’s Third National Communication Report to UNFCCC (2014)

Ibid

UNEP 2015: Climate Change in the Arab Region (Regional Coordination Mechanism Report)

UNDP/ National Centre for Security and Crises Management (NCSCM): Jordan National Disaster Risk Reduction (DRR) Strategy 2019-2022

Jordan Ministry of Water and Irrigation: Climate Change Policy for a Resilient Water Sector, 2016, page 3

UN-ESCWA et al. (2017) Arab Climate Change Assessment Report (RICCAR initiative)

World Bank et all (2017, policy note September 14): Refugees in the middle east. Bringing an urban lens to the forced displacement challenge

World Bank et all (2017, policy note September 14): Refugees in the middle east. Bringing an urban lens to the forced displacement challenge

See sections above

ILO (2016) Local Economic Development Strategy For Mafraq Governorate (2016-2018)

Jordan Third National Communication on Climate Change and Lebanon Third National Communication on Climate Change

Idem page 21

Idem

UNHCR (2015) Jordan Refugee Response Plan

UNHCR (2019) Vulnerability Assessment Framework https://data2.unhcr.org/en/documents/download/68856

UNHCR, UNICEF and WFP. (2019) VASyR 2019: Vulnerability Assessment of Syrian Refugees in Lebanon. 2019 Edition. Lebanon: UNHCR, UNICEF and WFP

Ibid

UN 3RP: Regional Refugee & Resilience Plan 2018-2019

Jordan in Figures 2017 - Page 7 http://dosweb.dos.gov.jo/DataBank/JordanInFigures/JORINFIGDetails2017.pdf

UNHCR - https://data2.unhcr.org/en/situations/syria/location/36

Ibid

Farajalla et al. (2014): Climate Change in Lebanon: High-order Regional Impacts from Agriculture http://website.aub.edu.lb/ifi/publications/Documents/working_papers/20140722_Higher_order_CC.pdf

Jordan Ministry of Water and Irrigation: Climate Change Policy for a Resilient Water Sector, 2016, page 3

http://www.lb.undp.org/content/dam/lebanon/docs/Energy%20and%20Environment/Publications/20171218%20Environmental%20safeguards%20EN.pdf

https://reliefweb.int/report/jordan/planning-ministry-launches-9-2million-project-adaptation-climate-change

3RP Regional Quarterly Dashboards March 2018. Online: https://data2.unhcr.org/fr/documents/download/63820

- Each Party shall designate and communicate to the secretariat the authority that will endorse on behalf of the national government the projects and programmes proposed by the implementing entities.

https://data2.unhcr.org/en/documents/download/67370

https://data2.unhcr.org/en/situations/syria/location/71#_ga=2.248854471.1978193527.1540994637-1966626473.1540994637

https://data2.unhcr.org/en/situations/syria/location/36#_ga=2.22371195.1978193527.1540994637-1966626473.1540994637

https://www.ohchr.org/EN/Countries/MENARegion/Pages/JOIndex.aspx

https://whc.unesco.org/en/list/&order=country#alphaG

https://www.genderindex.org/country/jordan/

https://www.genderindex.org/country/lebanon/

https://www.genderindex.org/country/jordan/

http://hdr.undp.org/en/composite/GDI

https://www.genderindex.org/country/lebanon/